|  |  |  | Application Form Selection: 2020 KA2 – Cooperation for innovation and the exchange of good practices – Capacity Building in the field of Higher Education |
| --- | --- | --- | --- |

Call for Proposals 2020 - EAC/A02/2019

Title of the Project / Acronym

DETAILEDDESCRIPTION OF THE PROJECT

JOINT PROJECTS

(To be attached to the e-Form)

Please note that, in accordance with Article 193 of the “Financial Regulation Applicable to the General Budget of the Union”, grants cannot be awarded retroactively. This means that activities covered by the grant can only be implemented as from the date on which the last party has signed the grant agreement.

As it might not in all cases be possible to sign the grant agreement for a selected proposal before the start date indicated in the application, the project planning should ideally cater for this possibility.

If your work plan does not allow for the necessary flexibility to adapt to such an event and/or if you have scheduled activities that must start on a particular date in the very early phase of the proposed action, you should provide a justification. The justification should explain the reasons why the activities in question cannot be postponed if the contract is not signed by 15 November 2020 or 15 January 2021) and need to take place on the foreseen date.

If this is the case for your project, you should specify below the following (max 3000 characters):

- the date on which the consortium would need to start its project activities covered by the grant. Only from this date on costs covered by the EU grant can be incurred;

- a detailed justification.The justification should explain why the activities foreseen (and their corresponding costs) cannot be delayed and why such a delay would jeopardise the project’s implementation.

Start date of project activity(ies): Activity(ies) and Justification:

# PART D – Relevance of the Project

# D.1 Why does the consortium undertake this project?

- Which problem(s) will the project address in theparticipating Partner Countries? Why are these problems pressing?

- Please explain the result of the need analysis carried out for each Partner Country and for each Partner institution and provide qualitative and quantitative evidence for your results.Please refer also to studies carried out and feasibility analyses undertaken. In particular explain for each institution,why the support from the CBHEactionis required.(limit 10.000 characters)

Problems and needs identifyed at the level of the Partner Country: [country 1]: - Partner institution […] needs and support required - Partner institution […] needs and support required Problems and needs identifyed at the level of the Partner Country: [country 2]: - Partner institution […] needs and support required - Partner institution[ …] needs and support required

(Please add Partner Countries/partners as appropriate)

Please identify the target groups and their needs in each Partner Country and in each Partner Country institution.(limit 8.000 characters)

Partner Country […] - Partner institution[...] - Partner institution[...] Partner Country [...] - Partner institution[...] - Partner institution [...]

(Please add partner countries/partners as appropriate)

How will the project address the relevant thematic national/regional priorities (see https://eacea.ec.europa.eu/erasmus-plus/funding/capacity-building-higher-education-2019_en) set by the Programme for its target country (ies)/region(s)? (limit 8.000 characters)

Partner Country /Region [...] Partner Country /Region [...]

(Please add Partner Countries/regions as appropriate)

# D.2 Aims and objectives

- What does the proposal aim at in general? What are the project’s specific objectives?

- Explain how the specific objectives of the project address theproblems mentioned in Part D1 and the needs of each target group in each Partner Country. Demonstrate also that the set objectives are realistic and feasible in the national and institutional context(s).

(limit 8.000 characters)

Aims and specific objectives: [...] Partner Country [...] Partner Country

(Please add Partner Countries/regions as appropriate)

Please explain how the planned activities and the expected results meet the needs of the identified target groupsin the Partner Countries(limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

How will the project and its results contribute effectively to the objectives of the action Capacity-Building in the Field of Higher Educationin eachtargetedPartner Country? (limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

How do the project's objectives fit in with the modernisation and internationalisation agenda of the targeted higher education institutions in the Partner Countries and with the development strategy for higher education in each Partner Country involved in the project? (limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries/partners as appropriate)

Please explain how the proposal will pay attention tothe issues of inclusion, diversity and socio-economically disadvantaged participantsand/or organisations in the Partner Countries. (limit 2.000 characters)

# D.3 Innovative character

Demonstrate why the proposal is innovative.

If it is complementary to previous/existing funded projects nationally or internationallyplease explain how the new proposal build on it/them and demonstrate its added value and why it is not a simple continuation thereof. (limit 2.000 characters)

If the proposal builds on any previous or existing EU-funded/non-EU funded national or international activities/projects in this field, please fill the following table for each of these projects.

☐

| Reference number |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) |  |  | Programme or initiative |  |
| Funded by |  |  |  |  |
| Title of the project |  |  |  |  |
| Coordinating organisation |  |  |  |  |
| Partner Countries /institutions targeted by this project |  |  |  |  |
| Website | http:// |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000characters). |  |  |  |  |

Please copy and paste tables as necessary

# D.4European added value

Why is there a need for cooperation with the Programme Countries in this area of activity and a funding via the Erasmus+ Programme?Why can the intended results not be achieved through national, regional or local funding in the Partner Countries? (limit 2.000 characters)

# D.5 Cross-regional cooperation

If your proposal is cross-regional, demonstrate the need for this cooperation between institutions from different regions.Please also explain the added value of this cross-regional cooperation for the targeted Partner Country institutions. (limit 2.000 characters)

# PART E – Quality of the Project Design and Implementation

# E.1 Project activities and methodology

Please provide a detailed description of the activities and the working methodology to be used for achieving the objectives (including major milestones, measurable indicators, etc.). (limit 6.000 characters)

Please demonstrate that the activities and the methodology mentioned are the most appropriate to achieve the envisaged results and that they are feasible. (limit 3.000 characters)

What concrete, tangible results are expected to be achieved at the end of the project's activities in each of the targetedPartner Countries? (limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

For all types of activities(curriculum development, modernisation of governance, management and functioning of HEIs; strengthening of relations between HEIs and the wider economic and social environment), for each Partner Country institution please provide information in Part F.2 Organisation and Activities.

# E.2Quality control and monitoring

Please explain what mechanisms willbe put in place for ensuring the quality of the project and how the evaluation will be carried out.If an external evaluation is foreseen, provide informationon the purpose and expected outcomes of this evaluation. Please define the specific quality measures established, as well as the benchmarks and indicators foreseen to verify the outcome of the action. Make sure that the information in this section is consistent with the project Logical Framework Matrix. (limit 3.000 characters)

# E.3 Budget and cost effectiveness

Please describe the strategy adopted to ensure that the proposed results and objectives will be achieved in the most economical way, and on time. Explain the principles of budget allocation amongst partners. Indicate the arrangements adopted for financial management. What sources of co-funding will be used?(limit 3.000 characters)

If your project involves any "exceptional costs" related to travel, pleasejustify them here. (limit 2.000 characters)

Please justify the equipment costs for each Partner Country Institution:

- why the Partner Countryinstitutions need themfor the implementation of the project;

- their relations with the content to be developed and the specific activities to be implemented) and

- the estimated timeframe for their purchase as well asthe estimated place where they will be located (limit 3.000 characters)

Partner Country[...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

Please complete the following Logical Framework Matrix:

☐

# E.4 Logical Framework Matrix – LFM

| Wider Objective:☒ What is the general objective, to which the project will contribute? | Indicators of progress: What are the key indicators related to the wider objective? | How indicators will be measured: What are the sources of information on these indicators? |  |  |
| --- | --- | --- | --- | --- |
| Specific Project Objective/s: What are the specific objectives, which the project shall achieve? | Indicators of progress: What are the quantitative and qualitative indicators showing whether and to what extent the project’s specific objectives are achieved? | How indicators will be measured: What are the sources of information that exist and can be collected? What are the methods required to get this information? | Assumptions & risks - What are the factors and conditions not under the direct control of the project, which are necessary to achieve these objectives? What risks have to be considered? | How the risks will be mitigated: |
| Outputs (tangible) and Outcomes (intangible): Please provide the list of concrete DELIVERABLES - outputs/outcomes (grouped in Workpackages), leading to the specific objective/s.: | Indicators of progress: What are the indicators to measure whether and to what extent the project achieves the envisaged results and effects? | How indicators will be measured: What are the sources of information on these indicators? | Assumptions & risks What external factors and conditions must be realised to obtain the expected outcomes and results on schedule? | How the risks will be mitigated: |
| Activities: What are the key activities to be carried out (grouped in Workpackages) and in what sequence in order to produce the expected results? | ### Inputs: What inputs are required to implement these activities, e.g. staff time, equipment, mobilities, publications etc.? |  | Assumptions ¦& risks What pre-conditions are required before the project starts? What conditions outside the project’s direct control have to be present for the implementation of the planned activities? | How the risks will be mitigated: |

Please complete the following work plan.☒

# E.5 Work Plan

On the following pages, please provide your work plan for each year of the proposed project

- Please use the model provided below.

- Please complete a one-page work plan for each project year.

- For each year of your proposal, please complete a work plan indicating the deadlines for each outcome and the period and location in which your activities will take place.

- If needed, please insert additional rows into the work plan tables.

- The same reference and sub-reference numbers as used in the logical framework matrix must be assigned to each outcome and related activities.

Examples:

Activity carried out in the Programme Country:         = (E.g. activity in France for two weeks in the first month of the project 2= under M1)

Activity carried out in the Partner Country (ies):        X (E.g., activity in Tunisia for three weeks in the second month of the project: 3X under M2)

# WORKPLAN for project year 1☒

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1 Procena potreba i studija izvodljivosti e-menadžment sistema | 20 | X | X | X | X |  | X |  |  |  |  |  |  |
|  | 1.2 Dizajn i arhitektura rešenja | 24 | X | X | X | X | X | X |  |  |  |  |  |  |
|  | 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima | 16 | X | X | X |  |  | X |  |  |  |  |  |  |
|  | 1.4 Analiza potreba privrede | 16 | X | X | X |  |  | X |  |  |  |  |  |  |
|  | 1.5 Analiza trenutnog stanja kurikuluma | 16 | X | X | X |  |  | X |  |  |  |  |  |  |
|  | 1.6 Primeri dobre prakse u implementaciji laboratorija I centara | 12 | X | X |  |  |  | X |  |  |  |  |  |  |
|  | 2.1 Razvoj prototipa | 24 |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 3.1 Studijske posete | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 3.2 Organizacija bisnis simulacija | 24 |  |  | X | X | X | X | X | X |  |  |  |  |
|  | 3.3 Panel Diskusije AI i Machine learning | 8 |  |  |  |  |  |  |  |  | X | X |  |  |
|  | 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju | 8 |  |  |  |  |  |  |  |  | X | X |  |  |
|  | 5.1 Defining third mission metrics | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 5.2 Internal monitoring | 16 |  |  | X | X | X | X |  |  |  |  |  |  |
|  | 5.3 Monitoring of defined metrics | 24 |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 6.1 Design of project visual identity | 24 | X | X | X | X | X | X |  |  |  |  |  |  |
|  | 6.2 Design/upgrade of web-site | 24 |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 7.1 Overall project managementt | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.2 Local management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.3 SC meetings | 48 | X | X | X | X | X | X | X | X | X | X | X | X |

# WORKPLAN for project year 2☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2 Strategija implementacije |  | X | X | X | X | X | X |  |  |  |  |  |  |
|  | 2.3 Ispitivanje i osiguranje kvaliteta |  |  |  | X | X | X | X | X | X |  |  |  |  |
|  | 2.4 Implementacija i uvođenje |  |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 4.2 Conduct a Needs Assessment | 12 | X | X | X |  |  |  |  |  |  |  |  |  |
|  | 4.3 Develop a Detailed Plan | 12 |  |  | X | X | X |  |  |  |  |  |  |  |
|  | 4.4 Procure Equipment and Software | 12 |  |  |  |  | X | X | X |  |  |  |  |  |
|  | 4.5 Prepare the Physical Space | 12 |  |  |  |  |  |  | X | X | X |  |  |  |
|  | 4.6 Install Equipment and Software | 4 |  |  |  |  |  |  |  |  |  | X |  |  |
|  | 4.7 Establish Cloud Infrastructure | 8 |  |  |  |  |  |  |  |  |  |  | X | X |
|  | 5.3 Monitoring of defined metrics | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 6.3 Defining institutional policies to promote third mission | 16 | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 6.4 Good practices on Tech. transfer and Innovation | 8 |  |  |  |  | X | X |  |  |  |  |  |  |
|  | 6.5 10 Info days and other events | 12 |  |  |  |  |  |  | X | X | X |  |  |  |
|  | 6.6 Final Conference on university third mission | 4 |  |  |  |  |  |  |  |  |  | X |  |  |
|  | 7.1 Overall project management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.2 Local management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.3 SC meetings | 48 | X | X | X | X | X | X | X | X | X | X | X | X |

# WORKPLAN for project year 3☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.5 Evaluacija i kontinuirano poboljšanje | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 2.6 Usklađenost i sigurnost | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 2.7 Održivost i skalabilnost | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 4.8 Conduct a Soft Launch | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 4.9 Organize an Official Launch Event | 8 |  |  | X | X |  |  |  |  |  |  |  |  |
|  | 5.3 Monitoring of defined metrics | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.1 Overall project management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.2 Local management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.3 SC meetings | 48 | X | X | X | X | X | X | X | X | X | X | X | X |

Please complete the information on each work package for your project

# E.6 Work packages

Please enter the different project activities you intend to carry out in your project. Make sure that the information in this section is consistent with the project Logical Framework Matrix.

| Work package type and ref.nr ☒ | PREPARATION |  |  | 1 |
| --- | --- | --- | --- | --- |
| Title | Analiza trenutnog stanja, potreba i dobrih praksi |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 1.1 Procena potreba i studija izvodljivosti e-menadžment sistema 1.2 Dizajn i arhitektura rešenja 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima 1.4 Analiza potreba privrede 1.5 Analiza trenutnog stanja kurikuluma 1.6 Primeri dobre prakse u implementaciji laboratorija I centara |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Procena potreba i studija izvodljivosti e-menadžment sistema |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | X Event x Report X Service/Product |  |
|  | Description | Act. 1.1.1 first activity of the project is to establish the needs for the development of a new IT system at the partner universities. This process will be conducted through interviews and focus groups over one month. The planning phase involves identifying relevant stakeholders, defining the objectives of the discussions, and developing a structured set of questions to guide the sessions. In the recruitment phase, a diverse group of participants from each partner university will be selected to provide a comprehensive understanding of the IT needs. Sessions will be scheduled at convenient times, and formal invitations will be sent to the selected participants, detailing the purpose, time, and location of the meetings. During the execution phase, focus groups and interviews will be conducted. Facilitators will ensure all participants have the opportunity to speak, and sessions will be recorded for accurate data analysis. Transcriptions and detailed notes will be used to capture the discussions. In the data analysis phase, the recordings from the focus groups and interviews will be transcribed, and common themes, issues, and requirements will be identified. A summary report will be created to highlight the key findings and insights gathered from the sessions. Act.1.1.2. The final reporting phase will involve drafting a omprehensive report detailing the identified needs and equirements for the new IT system. The draft report will be reviewed by key stakeholders, feedback will be incorporated, and a final report will be produced. The expected deliverable is a needs assessment report that provides a clear understanding of the current IT infrastructure issues and specific needs of the partner universities. This will enable informed decision-making and enhance collaboration among the universities. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | Englesh |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff X☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | XNational ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Dizajn i arhitektura rešenja |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act 1.2.1 The second activity of the project is to select the appropriate blockchain technology for the e-management system, to be completed over one month. The process begins with defining the specific requirements for the blockchain technology, such as security and scalability, followed by thorough research on available options. Next, a set of evaluation criteria is developed to assess the technologies, focusing on factors like security features, performance, cost, and ease of integration. From the initial research, a shortlist of the most suitable blockchain technologies is created for further evaluation. In the assessment phase, a detailed technical analysis of each shortlisted technology is conducted, including security assessments and performance benchmarks. Blockchain experts are consulted for additional insights and recommendations. Pilot projects are then set up to test the shortlisted technologies in a controlled environment, with feedback collected from technical teams and stakeholders on their performance and usability. Act. 1.2.2 Finally, the data and feedback from the pilot tests are analyzed to determine the strengths and weaknesses of each technology. A final decision is made on the most appropriate blockchain technology based on the evaluation criteria and pilot test results. The deliverables include an evaluation report and a selection report, with expected outcomes being an informed decision on the blockchain technology and clear documentation of the selection process. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Analiza postojećeg stanja stručne prakse na univerzitetima |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act. 1.3.1 The third activity involves gathering and analyzing data about the number and types of practices available in national universities, to be completed in two months. The process begins with defining objectives and creating structured questionnaires and interview guides to collect relevant data from students and partner organizations. Act. 1.3.2 Next, students from various universities and several companies are selected , ensuring a diverse and representative sample. Interviews are then scheduled and conducted, with all sessions recorded or detailed notes taken to capture the information accurately. Supplementary data from university records and internship databases is also collected to enhance the findings. Act. 1.3.3 For the analysis of partnerships and internships in the third activity, the deliverables include a detailed report on the effectiveness of existing partnerships with companies, a report on the number and types of internships available to students, and an assessment of the current processes for matching students with internships. The outputs consist of raw data collected from interviews with students and partner companies, transcriptions or detailed notes from these interviews, and a summary of key findings from the analysis of this data. Act 1.3.4 The results are a clearer understanding of the effectiveness of current partnerships, insights into the availability of internships and any gaps, and recommendations for improving the processes for connecting students with internships. This approach ensures thorough analysis and actionable insights for better partnerships and enhanced internship opportunities for students. Act. 1.3.5 In the data analysis phase, the recorded interviews are transcribed, and both qualitative and quantitative methods are used to identify common themes and insights. A summary report is created to highlight key findings on the number and types of practices available. The final reporting phase involves compiling the findings into a comprehensive report, which is reviewed by stakeholders for feedback and revisions before being finalized. The deliverables include the data collection instruments and a comprehensive report summarizing the findings. The expected results are a detailed understanding of the current state of internship and practice opportunities in national universities and the identification of gaps and opportunities for improvement. This systematic approach ensures accurate data collection and valuable insights into the available practices. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Analiza potreba privrede za stažiranjima |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act. 1.4.1 The fourth activity involves conducting virtual meetings with industry partners and exploring internships offered by small and medium businesses. This task, scheduled to last one month, begins with identifying potential industry partners and defining the objectives of the virtual meetings and interviews. Structured questions are then developed to guide these sessions. In the recruitment phase, key representatives from the identified businesses are selected to participate, and meetings are scheduled at convenient times. Formal invitations are sent out, detailing the purpose, time, and format of the meetings. During the execution phase, virtual meetings are facilitated using video conferencing tools, ensuring all participants have the opportunity to speak, and recordings are made for accurate data analysis. Individual interviews with industry representatives are also conducted, with detailed notes taken. Act. 1.4.2 The data analysis phase involves transcribing the recordings from the meetings and interviews, identifying common themes and opportunities, and summarizing the findings in a report. In the reporting phase, a comprehensive report is drafted, reviewed by stakeholders for feedback, and finalized. Act. 1.4.3 The deliverables include meeting agendas and structured questions, as well as a comprehensive report summarizing the findings. The expected outputs are recorded sessions and a summary of the findings. The results of this activity will be an enhanced understanding of current internship opportunities offered by small and medium businesses, along with identified areas for potential collaboration and improvement. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Analiza trenutnog stanja kurikuluma |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | The fifth activity involves analyzing the current state of the curriculum over three months. This begins with defining the objectives of the analysis, such as identifying strengths and weaknesses and aligning the curriculum with industry standards. Act. 1.5.1. Surveys are then developed and distributed to faculty, students, and industry partners, with responses collected and analyzed. Act.1.5.2. Next, relevant academic literature, industry reports, and case studies are gathered to identify current trends and academic standards. Act. 1.5.3. For the analysis of relevant literature, industry reports, and case studies in the fifth activity, the deliverables include a literature review report summarizing the findings, an annotated bibliography detailing key insights and trends, and a trend analysis summary highlighting best practices in Software Engineering and Business Informatics. The outputs consist of the collected documents, detailed analysis notes from the reviewed materials, and a thematic analysis identifying common themes and patterns. The results provide a thorough understanding of current trends and best practices, insights into gaps between academic practices and industry needs, and data-driven recommendations for curriculum improvements. This approach ensures comprehensive analysis and valuable insights to inform the curriculum enhancement process. Act. 1.5.4. Student performance data, including grades, graduation rates, and employment outcomes, are analyzed to pinpoint areas of strength and weakness. Act. 1.5.6. The current curriculum is then thoroughly reviewed to identify gaps and outdated materials. Act, 1,5,7 A parallel analysis compares the existing curriculum with industry standards to find misalignments and areas for improvement. Act. 1.5.8. The findings from all these phases are compiled into a comprehensive report. This draft report is reviewed by stakeholders, revised based on feedback, and finalized with actionable recommendations for curriculum improvements. The deliverables include the survey instruments and a detailed report summarizing the findings. The outputs consist of collected data, literature reviews, and analysis summaries. The results provide a thorough understanding of the curriculum’s strengths and weaknesses, alignment with industry standards, and recommendations for improvement. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Primeri dobre prakse u implementaciji laboratorija I centara |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act 1.6.1 Create a detailed research framework that outlines the key criteria and metrics for analyzing good practices. This includes defining the scope of the analysis, the specific areas of focus (such as AI labs, Cloud Computing labs, and digital learning centers), and the methodologies to be used for data collection and analysis. Act 1.6.2 Gather existing reports, publications, and case studies related to the laboratories and centers at the selected universities. This involves accessing academic databases, university websites, and industry publications to compile relevant documents that provide insights into the setup, operations, and achievements of these facilities. Act 1.6.3 Design structured interview questions and survey instruments aimed at gathering in-depth information from faculty, administrators, and lab managers at the selected EU universities. Conduct virtual interviews and distribute surveys to collect qualitative and quantitative data on best practices, challenges, and innovative approaches used in their laboratories and centers. Act 1.6.4 Organize and conduct virtual tours of the laboratories and centers at the partner universities. Use video conferencing tools to observe the facilities in operation, noting the layout, equipment, and processes. Record observations and gather additional insights from live demonstrations and interactions with on-site personnel. Act 1.6.5 Analyze the data collected from desk research, interviews, surveys, and virtual tours. Identify common themes, successful strategies, and innovative practices. Use qualitative analysis methods to draw meaningful conclusions and highlight best practices that can be replicated or adapted for Serbian universities. Act 1.6.6 Compile all findings into a comprehensive report. The report should summarize the best practices identified, provide detailed case studies from each partner university, and offer recommendations for implementing similar practices in Serbian universities. Review the draft report with key stakeholders, incorporate their feedback, and finalize the document for dissemination. This systematic approach ensures a thorough and detailed analysis of good practices in EU university laboratories and centers, providing actionable insights for enhancing similar facilities in Serbian universities. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☐ | DEVELOPMENT |  |  | 2 |
| --- | --- | --- | --- | --- |
| Title | Razvoj modernih IT tehnologija na srpskim univerzitetima |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 2.1 Razvoj prototipa 2.2 Strategija implementacije 2.3 Ispitivanje i osiguranje kvaliteta 2.4 Implementacija i uvođenje 2.5 Evaluacija i kontinuirano poboljšanje 2.6 Usklađenost i sigurnost 2.7 Održivost i skalabilnost |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Razvoj prototipa |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.1.1 Razvijanje minimalno održivog proizvoda (MVP): Start by defining the core functionalities required for the MVP, focusing on essential features that address the primary needs of users. Assemble a development team to design and build the MVP, ensuring it meets the identified requirements. Conduct internal reviews and iterations to refine the MVP before moving to initial testing. 2.1.2 Provođenje početnog testiranja korisnika i prikupljanje povratne informacije: Launch the MVP for a selected group of users, including faculty, students, and IT staff, to test its functionalities. Collect feedback through surveys, interviews, and usage data to identify any issues or areas for improvement. Analyze the feedback to make necessary adjustments and enhancements to the MVP. |  |  |  |
|  | Due date | M12 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Strategija implementacije |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.2.1 Razvijanje kompletanog sistema: Expand the MVP into a complete system by integrating additional features and functionalities based on the feedback received. Ensure that the system is scalable, secure, and user-friendly. Document the development process and create user manuals and training materials to support system adoption. 2.2.2 Integracija sa postojećim univerzitetskim sistemima: Plan and execute the integration of the new system with existing university IT infrastructure. Conduct compatibility tests and resolve any integration issues. Work closely with university IT departments to ensure a smooth and seamless integration process. |  |  |  |
|  | Due date | M18 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Ispitivanje i osiguranje kvaliteta |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.2.1 Razvijanje kompletnog sistema: Expand the MVP into a complete system by integrating additional features and functionalities based on the feedback received. Ensure that the system is scalable, secure, and user-friendly. Document the development process and create user manuals and training materials to support system adoption. 2.2.2 Integracija sa postojećim univerzitetskim sistemima: Plan and execute the integration of the new system with existing university IT infrastructure. Conduct compatibility tests and resolve any integration issues. Work closely with university IT departments to ensure a smooth and seamless integration process. |  |  |  |
|  | Due date | M20 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Implementacija i uvođenje |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.4.1 Instalacija pilot sistema: Roll out the system as a pilot in select departments or faculties to monitor its performance in a real-world environment. Collect feedback from users during the pilot phase to identify any remaining issues or areas for improvement. 2.4.2 Instalacija sistema u svim relevantnim institucijama: Based on the success of the pilot deployment, scale the system implementation to all relevant institutes and departments. Provide training sessions and support to ensure smooth adoption and usage across the university. |  |  |  |
|  | Due date | M24 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Evaluacija i kontinuirano poboljšanje |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.5.1 Praćenje i procena performanse sistema: Continuously monitor the system’s performance using analytics tools and user feedback. Evaluate key performance indicators (KPIs) to assess the system’s effectiveness and identify any areas for further improvement. 2.5.2 Implementacija poboljšanja na osnovu povratnih informacija: Regularly update the system to address any issues and implement improvements based on user feedback. Ensure that updates are well-documented and communicated to all users to maintain transparency and user satisfaction. |  |  |  |
|  | Due date | M30 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Usklađenost i sigurnost |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.6.1 Provera usklađenosti i sigurnosne revizije: Perform regular compliance checks and security audits to ensure the system adheres to regulatory standards and best practices. Document the findings and take corrective actions as necessary. 2.6.2 Ažuriranje sigurnosnih protokola i dokumentacije o usklađenosti po potrebi: Update security protocols and compliance documentation to reflect any changes in regulations or security practices. Ensure that all updates are communicated to relevant stakeholders and incorporated into the system. |  |  |  |
|  | Due date | M31 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.7. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Održivost i skalabilnost |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.7.1 Definisanje rasporeda održavanja i ažuriranja: Develop a maintenance and update schedule to ensure the system remains functional and up-to-date. Plan for regular system checks, software updates, and hardware maintenance to prevent any downtime. 2.7.2 Priprema budućih iteracija proizvoda: Design system features and infrastructure that can accommodate future growth and increased demand. Ensure that the system is scalable and flexible to adapt to evolving technological and user requirements. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☐ | DEVELOPMENT |  |  | 3 |
| --- | --- | --- | --- | --- |
| Title | Osavremenjivanje stručnih praksi |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 3.1 Studijske posete 3.2 Organizacija bisnis simulacija 3.3 Panel Diskusije AI i Machine learning 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.1 Studijske posete |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | #### 3.1.1 Posete univerzitetima i institucijama radi provere njihovih praksi u poslovnoj simulaciji 3.1.1.1 Zakazivanje posete: Planirajte i dogovorite termine poseta univerzitetima i institucijama. Kontaktirajte relevantne kontakte za usklađivanje rasporeda i potvrdu posete. 3.1.1.2 Organizovanje logistike: Organizujte sve potrebne logističke aspekte posete, uključujući prevoz, smeštaj i obroke za učesnike. Osigurajte da svi logistički zahtevi budu ispunjeni. 3.1.1.3 Razvoj potrebnog materijala: Pripremite sve materijale koji će biti potrebni tokom posete, kao što su vodiči, brošure i informacije o instituciji koju posećujete. 3.1.1.4 Kreiranje informacionog materijala: Razvijte informativne materijale koji će pomoći učesnicima da bolje razumeju i pripreme se za posetu. Ovi materijali trebaju sadržavati ključne informacije o instituciji i njenim praksama. 3.1.1.5 Razvoj agende za posetu, uključujući detaljni raspored aktivnosti: Kreirajte detaljnu agendu posete koja uključuje sve planirane aktivnosti, kao i raspored za svakog učesnika. Osigurajte da svi ključni aspekti budu obuhvaćeni i da vreme bude efikasno iskorišćeno. 3.1.1.6 Priprema pozadinske informacije o domaćoj organizaciji, uključujući njenu misiju i ključne ličnosti: Pripremite informacije o organizaciji koja posjećuje, uključujući njenu misiju, ciljeve i ključne osobe. Ove informacije će pomoći učesnicima da steknu bolju predstavu o kontekstu i ciljevima posete. 3.1.1.7 Priprema obrazovnog materijala: Izradite obrazovne materijale koji će biti korišćeni tokom posete, uključujući prezentacije, radne listove i druge resurse koji mogu pomoći u učenju i razumevanju praksi. 3.1.1.8 Sprovođenje obilaska objekta, ističući ključne oblasti interesa i operacija: Organizujte obilazak objekta koji će uključivati sve ključne oblasti interesovanja i operacije koje su relevantne za studije i praksu poslovne simulacije. 3.1.1.9 Priprema prezentacija od strane ključnih ličnosti, fokusirajući se na teme relevantne za studentske studije i interese vezane za karijeru: Organizujte prezentacije od strane ključnih osoba u instituciji koje će se fokusirati na teme od interesa za studente i njihove karijere. 3.1.1.10 Organizacija interaktivnih aktivnosti, kao što su Q&A sesije, demonstracije ili praktične radionice, radi angažovanja studenata i poboljšanja razumevanja: Planirajte interaktivne aktivnosti koje će omogućiti studentima da postavljaju pitanja, učestvuju u demonstracijama i radionica kako bi unapredili svoje razumevanje tema. 3.1.1.11 Priprema za neformalne sesije: Organizujte neformalne sesije, kao što su mrežne aktivnosti ili susreti u neformalnom okruženju, kako bi se podstaklo neformalno učenje i umrežavanje među studentima i predstavnicima institucije. 3.1.1.12 Posete univerzitetima i institucijama radi observacije njihovih praksi u diskusijama za Poslovnu Informatiku: Uvrstite posete univerzitetima i institucijama koje se specijalizuju za poslovnu informatiku, s ciljem posmatranja i analize njihovih praksi i metoda u oblasti diskusija i obrazovanja. 3.1.1.13 Učestvovanje u radionicama i konferencijama koje se fokusiraju na najbolje prakse u visokom obrazovanju i poslovnoj informatici: Učestvujte u relevantnim radionicama i konferencijama koje se bave najboljim praksama u visokom obrazovanju i poslovnoj informatici, kako biste dobili uvid u najnovije trendove i prakse. 3.1.1.14 Sprovođenje virtuelnih poseta i prisustvo onlajn demonstracijama naprednih e-menadžment sistema i IT infrastrukture: Organizujte i učestvujte u virtuelnim posetama i onlajn demonstracijama koje prikazuju napredne e-menadžment sisteme i IT infrastrukture, kako biste proširili razumevanje o ovim tehnologijama. #### 3.1.2 Studijske posete panel diskusijama 3.1.2.1 Zakazivanje posete: Planirajte i dogovorite termine poseta univerzitetima i institucijama. Kontaktirajte relevantne kontakte za usklađivanje rasporeda i potvrdu posete. 3.1.2.2 Organizovanje logistike: Organizujte sve potrebne logističke aspekte posete, uključujući prevoz, smeštaj i obroke za učesnike. Osigurajte da svi logistički zahtevi budu ispunjeni. 3.1.2.3 Razvoj potrebnog materijala: Pripremite sve materijale koji će biti potrebni tokom posete, kao što su vodiči, brošure i informacije o instituciji koju posećujete. 3.1.2.4 Kreiranje informacionog materijala: Razvijte informativne materijale koji će pomoći učesnicima da bolje razumeju i pripreme se za posetu. Ovi materijali trebaju sadržavati ključne informacije o instituciji i njenim praksama. 3.1.2.5 Razvoj agende za posetu, uključujući detaljni raspored aktivnosti: Kreirajte detaljnu agendu posete koja uključuje sve planirane aktivnosti, kao i raspored za svakog učesnika. Osigurajte da svi ključni aspekti budu obuhvaćeni i da vreme bude efikasno iskorišćeno. 3.1.2.6 Priprema pozadinske informacije o domaćoj organizaciji, uključujući njenu misiju i ključne ličnosti: Pripremite informacije o organizaciji koja posjećuje, uključujući njenu misiju, ciljeve i ključne osobe. Ove informacije će pomoći učesnicima da steknu bolju predstavu o kontekstu i ciljevima posete. 3.1.2.7 Priprema obrazovnog materijala: Izradite obrazovne materijale koji će biti korišćeni tokom posete, uključujući prezentacije, radne listove i druge resurse koji mogu pomoći u učenju i razumevanju praksi. 3.1.2.8 Sprovođenje obilaska objekta, ističući ključne oblasti interesa i operacija: Organizujte obilazak objekta koji će uključivati sve ključne oblasti interesovanja i operacije koje su relevantne za studije i praksu poslovne simulacije. 3.1.2.9 Priprema prezentacija od strane ključnih ličnosti, fokusirajući se na teme relevantne za studentske studije i interese vezane za karijeru: Organizujte prezentacije od strane ključnih osoba u instituciji koje će se fokusirati na teme od interesa za studente i njihove karijere. 3.1.2.10 Organizacija interaktivnih aktivnosti, kao što su Q&A sesije, demonstracije ili praktične radionice, radi angažovanja studenata i poboljšanja razumevanja: Planirajte interaktivne aktivnosti koje će omogućiti studentima da postavljaju pitanja, učestvuju u demonstracijama i radionica kako bi unapredili svoje razumevanje tema. 3.1.2.11 Priprema za neformalne sesije: Organizujte neformalne sesije, kao što su mrežne aktivnosti ili susreti u neformalnom okruženju, kako bi se podstaklo neformalno učenje i umrežavanje među studentima i predstavnicima institucije. 3.1.2.12 Posete univerzitetima i institucijama radi observacije njihovih praksi u diskusijama za Poslovnu Informatiku: Uvrstite posete univerzitetima i institucijama koje se specijalizuju za poslovnu informatiku, s ciljem posmatranja i analize njihovih praksi i metoda u oblasti diskusija i obrazovanja. 3.1.2.13 Učestvovanje u radionicama i konferencijama koje se fokusiraju na najbolje prakse u visokom obrazovanju i poslovnoj informatici: Učestvujte u relevantnim radionicama i konferencijama koje se bave najboljim praksama u visokom obrazovanju i poslovnoj informatici, kako biste dobili uvid u najnovije trendove i prakse. 3.1.2.14 Sprovođenje virtuelnih poseta i prisustvo onlajn demonstracijama naprednih e-menadžment sistema i IT infrastrukture: Organizujte i učestvujte u virtuelnim posetama i onlajn demonstracijama koje prikazuju napredne e-menadžment sisteme i IT infrastrukture, kako biste proširili razumevanje o ovim tehnologijama. |  |  |  |
|  | Due date | M2 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.2 Organizacija bisnis simulacija |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.2.1 Identifikacija specifičnih obrazovnih ciljeva: Definišite obrazovne ciljeve koje želite postići kroz poslovnu simulaciju. Ovi ciljevi treba da budu jasni, merljivi i relevantni za učesnike. 3.2.2 Određivanje opsega simulacije: Odredite opseg simulacije, uključujući sve ključne aspekte i aktivnosti koje će biti deo simulacije, kako bi se postigli zadati obrazovni ciljevi. 3.2.3 Razvoj detaljnog poslovnog scenarija: Kreirajte detaljan poslovni scenario koji će biti korišćen tokom simulacije, uključujući sve relevantne informacije, izazove i situacije koje će učesnici morati da reše. 3.2.4 Kreiranje priče: Razvijte priču koja će voditi simulaciju, uključujući sve glavne događaje i prelome u scenariju koji će omogućiti učesnicima da se uključe i reaguju na situacije. 3.2.5 Angažovanje facilitator-a i mentora: Regrutujte i angažujte facilitatora i mentora koji će voditi simulaciju i pružati podršku učesnicima tokom procesa. 3.2.6 Razvoj skripti: Izradite skripte koje će biti korišćene tokom simulacije, uključujući uputstva za facilitatora i učesnike, kao i scenarije za različite situacije. 3.2.7 Kreiranje pozadinskih materijala: Pripremite sve pozadinske materijale koji će biti potrebni za simulaciju, kao što su izvodi iz izveštaja, poslovni dokumenti i drugi resursi koji pomažu u razumevanju scenarija. 3.2.8 Dizajniranje i kreiranje digitalnih platformi: Razvijte i dizajnirajte sve digitalne platforme koje će biti korišćene tokom simulacije, uključujući softverske alate i interfejse za učesnike. 3.2.9 Priprema fizičkih materijala: Organizujte sve fizičke materijale koji će biti korišćeni tokom simulacije, kao što su radni listovi, brošure i drugi materijali koji pomažu u realizaciji simulacije. 3.2.10 Promocija događaja simulacije: Promovišite događaj simulacije kroz različite kanale, kako biste privukli učesnike i osigurali visoku prijavu. 3.2.11 Postavljanje procesa registracije: Organizujte i postavite proces registracije za učesnike, uključujući online prijave i potvrde. 3.2.12 Organizovanje orijentacionih sesija: Pripremite i organizujte orijentacione sesije za učesnike kako bi se upoznali sa svim aspektima simulacije i pripremili se za ulogu koju će igrati. 3.2.13 Distribucija pripremnih materijala: Podelite pripremne materijale učesnicima pre početka simulacije kako bi se mogli pripremiti i upoznati sa sadržajem. 3.2.14 Organizovanje fizičkog i virtuelnog prostora: Pripremite i organizujte fizički i virtuelni prostor u kojem će se simulacija odvijati, uključujući sve tehničke i logističke aspekte. 3.2.15 Testiranje svih tehničkih sistema i alata: Testirajte sve tehničke sisteme i alate koji će biti korišćeni tokom simulacije, kako biste osigurali da sve funkcioniše besprekorno. 3.2.16 Održavanje uvodne sesije: Organizujte uvodnu sesiju za sve učesnike kako biste ih uputili u ciljeve i tok simulacije, kao i pružili sve potrebne informacije. 3.2.17 Facilitation of the simulation: Facilitirajte simulaciju, osiguravajući da svi učesnici imaju priliku da učestvuju i da se simulacija odvija prema planu. 3.2.18 Praćenje interakcija i napretka studenata: Pratite interakcije i napredak studenata tokom simulacije, pružajući povratne informacije i podršku kada je potrebno. 3.2.19 Održavanje sesija za refleksiju: Organizujte sesije za refleksiju nakon simulacije, kako bi učesnici mogli da analiziraju i diskutuju o svojim iskustvima i naučenim lekcijama. |  |  |  |
|  | Due date | M8 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.3 Panel Diskusije AI i Machine learning |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.3.1 Postavljanje prostora: Pripremite prostor za panel diskusiju, uključujući sve tehničke i logističke aspekte, kao što su sedišta, audio-vizuelna oprema i osvjetljenje. 3.3.2 Razvoj promotivnih materijala: Izradite promotivne materijale za panel diskusiju, kao što su plakati, brošure i objave na društvenim mrežama, kako biste privukli učesnike i publiku. 3.3.3 Dobrodošlica učesnicima i predstavljanje panelista i moderatora: Pripremite dobrodošlicu za učesnike i predstavite paneliste i moderatora, obezbeđujući da svi prisutni imaju sve potrebne informacije. 3.3.4 Facilitacija panel diskusije, osiguravajući da ostane na pravom putu i pokriva ključne teme: Vodite diskusiju, pazeći da se fokusira na ključne teme i da se svi panelisti uključe u razgovor na konstruktivan način. 3.3.5 Omogućavanje vremena za pitanja publike i interakciju sa panelistima: Obezbedite vreme za pitanja publike i interakciju sa panelistima, kako bi se omogućila dublja razmena mišljenja i informacija. |  |  |  |
|  | Due date | M10 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.4.1 Postavljanje prostora: Organizujte i pripremite prostor za panel diskusiju o blockchain tehnologiji, uključujući tehničke i logističke aspekte. 3.4.2 Razvoj promotivnih materijala: Kreirajte promotivne materijale za panel diskusiju, kako biste informisali i privukli publiku i potencijalne učesnike. 3.4.3 Dobrodošlica učesnicima i predstavljanje panelista i moderatora: Pripremite dobrodošlicu i predstavite paneliste i moderatora, pružajući sve relevantne informacije o njihovim iskustvima i stručnosti. 3.4.4 Facilitacija panel diskusije, osiguravajući da ostane na pravom putu i pokriva ključne teme: Vodeći diskusiju, osigurajte da se pokrivaju ključne teme o blockchain tehnologiji i njenim primenama u poslovanju. 3.4.5 Omogućavanje vremena za pitanja publike i interakciju sa panelistima: Planirajte vreme za pitanja publike i omogućite interakciju između publike i panelista, kako bi se omogućila dublja rasprava i razmena mišljenja. |  |  |  |
|  | Due date | M10 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Work package type and ref.nr ☐ | DEVELOPMENT |  |  | 4 |
| --- | --- | --- | --- | --- |
| Title | 4. Formiranje laboratorije za digitalnu transformaciju |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps 4.2 Conduct a Needs Assessment 4.3 Develop a Detailed Plan 4.4 Procure Equipment and Software 4.5 Prepare the Physical Space 4.6 Install Equipment and Software 4.7 Establish Cloud Infrastructure 4.8 Conduct a Soft Launch 4.9 Organize an Official Launch Event |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.1.1 Identifikacija i regrutovanje ključnih aktera - Počnite sa identifikacijom ključnih aktera, uključujući univerzitetske profesore, industrijske stručnjake, IT profesionalce i studente sa relevantnim interesovanjima i stručnostima. - Zakažite inicijalne sastanke kako biste razgovarali o ciljevima projekta i potencijalnim ulogama aktera. - Zvanično ih angažujte za projekat pružanjem detaljnog pregleda odgovornosti i očekivanih doprinosa. 4.1.2 Dodela uloga i odgovornosti unutar tima - Definišite specifične uloge kao što su projektni menadžer, tehnički vođa, softverski vođa i koordinator operacija. - Jasno dokumentujte i komunicirajte ove uloge svakom članu tima. - Organizujte redovne timske sastanke kako bi svaki član razumeo svoje zadatke i rokove, i kako bi se koordinisale aktivnosti između odeljenja (IT, nabavka, administracija). |  |  |  |
|  | Due date | M14 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.2 Conduct a Needs Assessment |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.2.1 Prikupljanje inputa od fakulteta, studenata i industrijskih partnera o željenim funkcijama laboratorije i centra - Sprovođenje anketa ili fokus grupa kako biste prikupili uvide od fakulteta, studenata i industrijskih partnera o njihovim potrebama i očekivanjima od laboratorije (npr. pristup AI alatima, cloud servisima ili radionicama). - Dokumentujte ključne željene funkcije i analizirajte kako se one uklapaju sa aktuelnim trendovima u AI, mašinskom učenju i DevOps-u. 4.2.2 Procena trenutnog stanja objekata, opreme i resursa dostupnih na univerzitetu - Pregledajte postojeće objekte i infrastrukturu univerziteta. - Sprovedite analizu nedostataka kako biste utvrdili koja oprema, softver i alati su već dostupni, a šta je potrebno dodatno nabaviti. - Pripremite izveštaj koji opisuje trenutno stanje resursa i potrebne nadogradnje za laboratoriju. |  |  |  |
|  | Due date | M15 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.3 Develop a Detailed Plan |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.3.1 Kreiranje sveobuhvatnog plana koji obuhvata ciljeve, opseg, vremenski okvir, budžet i resurse potrebne za osnivanje laboratorije i centra - Nacrtajte detaljan projektni plan koji obuhvata opseg laboratorije (AI, DevOps, mašinsko učenje itd.), ciljeve projekta (obuka studenata, podrška istraživanju) i razradu ključnih faza. - Uspostavite vremenski okvir sa specifičnim prekretnicama kao što su nabavka, postavljanje, testiranje i lansiranje. - Razvijte detaljan budžet, uzimajući u obzir opremu, softverske licence, osoblje, treninge i događaje. 4.3.2 Osigurajte da plan uključuje detaljne specifikacije - Uključite tehničke specifikacije za potrebnu opremu (servere, radne stanice, mrežne uređaje), softver (AI alati, cloud platforme) i sigurnosnu infrastrukturu. - Konsultujte se sa IT stručnjacima i dobavljačima kako biste finalizirali te specifikacije i osigurali da odgovaraju potrebama projekta i budu skalabilne za buduću ekspanziju. |  |  |  |
|  | Due date | M17 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.4 Procure Equipment and Software |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.4.1 Identifikacija i odabir dobavljača - Istražite potencijalne dobavljače opreme i softvera. Razmotrite faktore kao što su cena, tehnička podrška, kompatibilnost sa postojećom infrastrukturom i skalabilnost. - Zatražite ponude i pregovarajte o ugovorima sa preferiranim dobavljačima, osiguravajući da ispunjavaju univerzitetske smernice za nabavku. 4.4.2 Kupovina i nabavka potrebne opreme i softverskih licenci - Nakon što odaberete dobavljače, pošaljite narudžbenice za potrebni hardver i softver. - Koordinirajte se sa finansijskim i nabavnim odeljenjima univerziteta kako biste osigurali pravovremenu nabavku resursa. - Pratite vremenski okvir isporuke i instalacije sve opreme i softvera. |  |  |  |
|  | Due date | M19 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.5 Prepare the Physical Space |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.5.1 Identifikacija i osiguranje odgovarajuće lokacije na kampusu* - Identifikujte odgovarajući prostor na kampusu koji ima adekvatan prostor, napajanje, mrežnu povezanost i sigurnost za laboratoriju. - Osigurajte odobrenje od univerzitetske uprave za korišćenje ovog prostora. 4.5.2 Renoviranje i postavljanje fizičkog prostora - Ako je potrebno, renovirajte prostor kako bi ispunio tehničke zahteve (npr. instaliranje dodatnih električnih utičnica, poboljšanje ventilacije za servere). - Postavite prostor sa odgovarajućim nameštajem, tablama, projektorima i mrežnom infrastrukturom. |  |  |  |
|  | Due date | M21 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.6 Install Equipment and Software |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.6.1 Postavljanje servera, radnih stanica, mrežnih uređaja i druge hardverske opreme - Saradnja sa IT odeljenjem na instalaciji i konfigurisanju servera, radnih stanica i mrežnih uređaja. - Osigurajte pravilnu konfiguraciju mrežne sigurnosti, uključujući firewalle, VPN-ove i ograničen pristup osetljivim podacima i sistemima. 4.6.2 Instalacija i konfiguracija potrebnog softvera, uključujući cloud platforme, DevOps alate i druge relevantne aplikacije - Instalirajte i konfigurišite softvere za AI i mašinsko učenje, cloud servise (AWS, Azure) i DevOps alate (Jenkins, Docker). - Testirajte svaki softver kako biste osigurali njegovu besprekornu integraciju sa hardverskom i mrežnom postavkom. |  |  |  |
|  | Due date | M22 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.7. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.7 Establish Cloud Infrastructure |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.7.1 Postavljanje cloud naloga i konfiguracija cloud resursa - Kreirajte naloge kod cloud provajdera kao što su AWS, Azure ili Google Cloud. - Konfigurišite cloud infrastrukturu, uključujući postavljanje virtuelnih mašina, skladištenja i mrežnih resursa potrebnih za AI i DevOps projekte. 4.7.2 Implementacija sigurnosnih mera i kontrole pristupa radi zaštite cloud infrastrukture - Uspostavite stroge sigurnosne protokole, uključujući višefaktornu autentifikaciju, enkripciju podataka u tranzitu i mirovanju i kontrole pristupa za korisnike. - Postavite redovne backup-ove i nadzor cloud sistema kako biste sprečili neovlašćen pristup i osigurali bezbednost podataka. |  |  |  |
|  | Due date | M24 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.8. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.8 Conduct a Soft Launch |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.8.1 Organizovanje probnog lansiranja laboratorije i centra - Planirajte probno lansiranje pozivom male grupe korisnika (fakultet, studenti i industrijski partneri) kako bi koristili laboratorijske kapacitete. - Sprovedite uživo testiranje opreme i softvera kako biste identifikovali sve potencijalne probleme ili uska grla u sistemu. 4.8.2 Prikupljanje povratnih informacija od inicijalnih korisnika i prilagođavanje pre zvaničnog lansiranja - Prikupite povratne informacije od korisnika tokom probnog lansiranja o njihovom iskustvu sa alatima i infrastrukturom. - Koristite ove povratne informacije za prilagođavanja, kao što su fino podešavanje postavki pristupa, rešavanje problema sa performansama ili unapređenje korisničkog iskustva. |  |  |  |
|  | Due date | M26 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.9. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.9 Organize an Official Launch Event |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.9.1 Planiranje i organizacija zvaničnog događaja lansiranja - Isplanirajte veliki događaj koji uključuje univerzitetsku zajednicu, industrijske partnere i medije kako bi se zvanično otvorila laboratorija. - Pripremite agendu koja uključuje govore ključnih aktera, obilazak laboratorije i demonstracije tehnologija. 4.9.2 Predstavljanje laboratorijskih kapaciteta, demonstracija ključnih tehnologija i isticanje benefita za studente, fakultet i industrijske partnere |  |  |  |
|  | Due date | M28 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr☐ | QUALITY PLAN |  |  | 5 |
| --- | --- | --- | --- | --- |
| Title | 5 Developing QCM manual |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 5.1 Defining third mission metrics 5.2 Internal monitoring 5.3 Monitoring of defined metrics |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 5.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 5.1 Defining third mission metrics |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 5.1 Defining third mission metrics: Start by gathering a team of experts from within the institution, including representatives from administration, faculty, and any relevant departments, to define the third mission metrics. These metrics should capture the institution's broader impact on society, such as community engagement, technology transfer, and public outreach. Facilitate workshops and discussions to identify the most relevant metrics that align with the institution's mission and strategic goals. Once identified, document these metrics clearly, ensuring they are specific, measurable, achievable, relevant, and time-bound (SMART). This will form the foundation of the QCM (Quality Control and Monitoring) manual. |  |  |  |
|  | Due date | M2 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 5.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 5.2 Internal monitoring |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 5.2 Internal monitoring: Establish a system for internal monitoring of the defined third mission metrics. Develop processes and tools, such as templates and software, to regularly collect data related to each metric. Assign responsibilities to specific departments or individuals for data collection, analysis, and reporting. Conduct training sessions to ensure that all involved parties understand how to use the monitoring tools and follow the established procedures. Schedule regular internal audits or reviews to assess the effectiveness of the monitoring system and make adjustments as needed to improve accuracy and efficiency. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 5.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 5.3 Monitoring of defined metrics |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 5.3 Monitoring of defined metrics: Implement the monitoring system by starting the regular collection and analysis of data based on the third mission metrics. Set up a timeline for monitoring activities, including monthly or quarterly reporting, to track progress against the defined metrics. Create a feedback loop where the results are reviewed by relevant stakeholders, such as the management team, and used to inform decision-making and strategic planning. Adjust the metrics or monitoring approach if necessary, based on the findings and feedback, to ensure that they continue to reflect the institution's goals and societal impact effectively. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☒ | DISSEMINATION & EXPLOITATION |  |  | 6 |
| --- | --- | --- | --- | --- |
| Title | 6 Elaboration of Dissemination and Exploitation Plan |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 6.1 Design of project visual identity 6.2 Design/upgrade of web-site 6.3 Defining institutional policies to promote third mission 6.4 Good practices on Tech. transfer and Innovation 6.5 10 Info days and other events 6.6 Final Conference on university third mission |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.1 Design of project visual identity |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.1 Design of project visual identity: Begin by assembling a creative team that includes graphic designers, communication experts, and key project stakeholders to develop the project's visual identity. This identity should include a logo, color scheme, typography, and design elements that reflect the project's goals and values. Conduct brainstorming sessions to gather ideas and draft multiple design concepts. Once a few concepts are developed, present them to the broader project team for feedback. Refine the chosen design based on this feedback, and ensure that the final visual identity is versatile and suitable for various platforms, including print, digital, and merchandise. Document the visual identity guidelines in a style guide to ensure consistency across all project materials. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.2 Design/upgrade of web-site |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.2 Design/upgrade of website: With the visual identity established, work with web designers and developers to create or upgrade the project website. The website should be user-friendly, accessible, and aligned with the visual identity. Begin by defining the website's structure, including key sections such as project overview, news, events, resources, and contact information. Ensure that the website is optimized for search engines (SEO) and mobile devices. Collaborate with content creators to develop engaging and informative content for each section. Launch the website after thorough testing for functionality, speed, and usability. Regularly update the site with new content and features as the project progresses. |  |  |  |
|  | Due date | M12 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.3 Defining institutional policies to promote third mission |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.3 Defining institutional policies to promote third mission: Work with institutional leaders, policy experts, and legal advisors to define policies that promote the third mission of the university, which includes activities such as community engagement, technology transfer, and societal impact. Start by reviewing existing policies to identify gaps or areas for improvement. Conduct consultations with key stakeholders, including faculty, students, and industry partners, to gather input on policy priorities. Draft the new or revised policies, ensuring they align with the institution’s mission and strategic goals. Once the policies are finalized, they should be approved by the relevant governance bodies and communicated effectively to the entire university community. |  |  |  |
|  | Due date | M16 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.4 Good practices on Tech. transfer and Innovation |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.4 Good practices on Tech transfer and Innovation: Research and document good practices in technology transfer and innovation both within the institution and from other leading universities or organizations. Begin by conducting a literature review and case studies on successful tech transfer initiatives. Engage with industry partners and experts to gather insights on effective practices and potential pitfalls. Compile this information into a comprehensive report that includes recommendations for how these practices can be adapted and implemented within the institution. Share the report with relevant departments, such as research, innovation, and tech transfer offices, and use it as a basis for training and capacity-building workshops. |  |  |  |
|  | Due date | M18 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.5 10 Info days and other events |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.5 10 Info days and other events: Plan and organize a series of 10 information days and other events to promote the project’s objectives and engage the university community and external stakeholders. Start by developing a detailed event plan that includes the target audience, key messages, speakers, and activities for each event. Secure venues and arrange for logistical support, including audiovisual equipment, catering, and promotional materials. Use the project’s visual identity to brand these events consistently. Promote the events through the project website, social media, and email campaigns. During the events, gather feedback from participants to improve subsequent info days. Document the outcomes of each event and share them with stakeholders. |  |  |  |
|  | Due date | M21 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.6 Final Conference on university third mission |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.6 Final Conference on university third mission: Conclude the project with a high-profile final conference focused on the university's third mission. Begin by forming a conference planning committee that includes representatives from key stakeholder groups. Develop a comprehensive plan that outlines the conference theme, agenda, speakers, workshops, and networking opportunities. Identify and invite keynote speakers who are leaders in the field of university third mission activities. Promote the conference widely to ensure strong attendance from both the university community and external partners. During the conference, facilitate discussions on best practices, challenges, and future directions for third mission activities. Collect feedback and publish a conference report that highlights the key outcomes and recommendations. |  |  |  |
|  | Due date | M22 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☒ | MANAGEMENT |  |  | 7 |
| --- | --- | --- | --- | --- |
| Title | 7. Elaboration of Manual for contractual and financial management. |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 7.1 Overall project managementt 7.2 Local management 7.3 SC meetings |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes☒ | Work Package and Outcome ref.nr | 7.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 7.1 Overall project managementt |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 7.1 Overall project management: Start by establishing a framework for overall project management that will guide the project from inception to completion. This includes defining the project’s goals, deliverables, timelines, and key milestones. Develop a comprehensive project management plan that outlines roles and responsibilities, communication protocols, risk management strategies, and quality control measures. Utilize project management tools such as Gantt charts, project dashboards, and task management software to monitor progress and ensure that all aspects of the project are on track. Regularly review and update the project management plan to reflect any changes or developments, ensuring that all stakeholders are informed and aligned with the project’s objectives. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes☒ | Work Package and Outcome ref.nr | 7.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 7.2 Local management |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 7.2 Local management: For local management, create guidelines tailored to the specific needs and contexts of the local teams involved in the project. Begin by identifying local project coordinators who will oversee the day-to-day management of activities at each location. Provide these coordinators with a clear understanding of their roles, including managing local budgets, coordinating with the central project management team, and ensuring compliance with the project’s overall goals and standards. Develop a local management manual that includes procedures for reporting, communication, and decision-making at the local level. Schedule regular check-ins between local teams and the central management team to address any challenges and ensure consistency across all locations. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes☒ | Work Package and Outcome ref.nr | 7.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 7.3 SC meetings |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 7.3 SC meetings: To ensure effective governance and decision-making, plan and organize Steering Committee (SC) meetings at regular intervals throughout the project. Begin by establishing the SC’s composition, including key stakeholders such as project leaders, financial managers, and representatives from each partner institution. Develop a schedule for SC meetings, typically quarterly, and circulate it to all members in advance. For each meeting, prepare an agenda that covers project progress, financial management, risk assessment, and any key decisions that need to be made. Distribute relevant documents and reports to SC members ahead of time to facilitate informed discussions. During the meetings, ensure that minutes are taken to document decisions and action items, and follow up on these actions in subsequent meetings to ensure accountability and progress. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

# E.7 Consortium partners involved and human resources required to complete the work packages

Indicative input of consortium staff - The total number of days per staff category should correspond with the information provided in the budget tables.☐

| Work Package Ref.nr | Partner nr | Partner acronym | Country | Number of staff days☒ |  |  |  |  | Exact Role and tasks of each person in the work package |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Category 1 | Category 2 | Category 3 | Category 4 | Total |  |
| PREPARATION | P1 | DUNP | Serbia |  |  |  |  |  | Activity 1.1.1 Researcher for preparing the interviews 2 days, technical to process the interviews 5 days, administrative to deliver the interviews 2 days Activity 1.1.2 |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| DEVELOPMENT |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| QUALITY PLAN |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| DISSEMINATION & EXPLOITATION |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| MANAGEMENT |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |

Please insert rows as necessary

# PART F – Quality of the Project Team and Cooperation Arrangements

# F.1 Background of partnership and the proposal preparation

Please provide shortly the history of cooperation between partners (if any). How the idea of the project was developed and which/ who among partners contributed to the proposal development. (limit 3.000 characters)

If relevant, please explain how and to which extent the project benefits from the experience and participation of non–academic partners. (limit 3.000 characters)

Please explain the role and the participation of the Programme Country partners and their support in the development of the different activities (e.g. in the development of the curricula) and (limit 3.000 characters)

# F.2 Cooperation arrangements, management and communication

Please define the organisation of the implementation of the project and the division of tasks between the partners. Please explain the allocation of resources for each activity. Explain also how the tasks are distributed amongst the partners and how project "ownership" is ensured (limit 3.000 characters).

Please explain the overall project and partnership management making specific reference to the management plan and how decisions will be taken. Please describe how permanent and effective communication and reporting will be ensured as well as the measures put in place for conflict resolution (limit 2.000 characters).

# F.3 Organisations and activities

This part must be completed separately by each organisation participating in the project (applicant and partners with its affiliated entities (if any)).

☒

| Partner number ☒ |  |  |  |  | P1 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym |  |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List ofsubjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List ofsubjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project anddefine clear the activities to be held in your institution(limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment( only for Partner Country institutions) Please fill in if you are applying for this type of project anddefine clear the activities to be held in your institution(limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |

Please copy and paste tables as necessary

# F.4 List of Associated Partners

(Where applicable)

Capacity-building projects can involve associated partners who contribute to the implementation of specific project tasks/activities or support the dissemination and sustainability of the project. Associated Partners cannot be responsible for core activities of the project (e.g. management, coordination, monitoring, leader of a work group etc.).No financial contribution from the project grant will be allocated to these organisations.

☐

| Name of organisation | Type of institution | Website | City | Country | Role in the project | Activities and related Work Packages |
| --- | --- | --- | --- | --- | --- | --- |

Please insert rows as necessary

# PART G – Impact and Sustainability

# G.1 Expected impact of the project

Please explain which target groups will use the project outputs /products /results. Describe how the target groups will be reached and involved during the life of the project and afterwards and how the project will benefit the target group at local, regional, national and/or regional level. Please structure your description according to the different levels of impact and stakeholders.

☐

| # | Project results | Who will they impact at national, regional level? | How? |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

Please insert rows as necessary

Overview of short term impact indicators (during the project EU funding period)

☐

| Short term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |

Please insert rows as necessary

Overview of long term impact indicators (after the projects EU funding period)

☐

| Long term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |

Please insert rows as necessary

# G.2 Dissemination and exploitation strategy

Please explain how the dissemination will be organisedduring and after the project's lifetime. Define each target group and what communication channels will be used to reach them and when.

☒

| Target Group | Means of Communication to Reach These Target Groups | When | Indicators to measure the effectiveness of the means of communication |
| --- | --- | --- | --- |

Please insert rows as necessary

# G.3 Sustainability

Explain how exploitation activities will ensure optimal use of the results within the project's lifetime and afterwards. Explain how the impact of the project will be sustained beyond its lifetime. Please list the outcomes that you consider sustainable and describe the strategy to ensure their long lasting use beyond the project's lifetime. Also explain how the results will be mainstreamed and multiplied at national/regional level. Describe the strategy foreseen to attract co-funding and other forms of non-EU support for the project.

☐

| Sustainable Outcomes | Strategy to ensure their sustainability | Resources necessary to achieve this | Where will these resources be obtained? |
| --- | --- | --- | --- |

Please insert rows as necessary

# PART H - Other EU grants

Please list the projects for which the organisations involved in this application have received financial support from EU programmes.

☒

| Programme or initiative | Reference number | Beneficiary Organisation | Title of the Project |
| --- | --- | --- | --- |

Please insert rows as necessary.

Please list other EU grant proposalssubmitted by your organisation, or by any partner organisation in this project proposal. For each grant application, please mention the EU Programme concerned and the amount requested.

☐

| Programme concerned | Beneficiary Organisation | Amount requested |
| --- | --- | --- |

Please insert rows as necessary.

# PART I- Check List

Please make sure that you fully completed each part of this application form, as follows:

☒

☐	PART D - RELEVANCE OF THE PROJECT

☐	PART E - QUALITY OF THE PROJECT DESIGN AND IMPLEMENTATION

☐	E.4 Logical Framework Matrix

☐	E.5 Workplan

☐	E.6 Work packages

☐	PART F - Quality of the Project Team and Cooperation Arrangements

☐	PART G - Impact and Sustainability

☐	PART H - Other EU grants

☐	PART I - CHECK LIST

Please see Programme Guide, Part B for your action, Table A – Project Implementation (amounts in Euro per day) Programme Countries and Table B - Project Implementation (amounts in Euro per day) Partner Countries.