|  |  |  | Application Form Selection: 2020 KA2 – Cooperation for innovation and the exchange of good practices – Capacity Building in the field of Higher Education |
| --- | --- | --- | --- |

Call for Proposals 2020 - EAC/A02/2019

Title of the Project / Acronym

DETAILEDDESCRIPTION OF THE PROJECT

JOINT PROJECTS

(To be attached to the e-Form)

Please note that, in accordance with Article 193 of the “Financial Regulation Applicable to the General Budget of the Union”, grants cannot be awarded retroactively. This means that activities covered by the grant can only be implemented as from the date on which the last party has signed the grant agreement.

As it might not in all cases be possible to sign the grant agreement for a selected proposal before the start date indicated in the application, the project planning should ideally cater for this possibility.

If your work plan does not allow for the necessary flexibility to adapt to such an event and/or if you have scheduled activities that must start on a particular date in the very early phase of the proposed action, you should provide a justification. The justification should explain the reasons why the activities in question cannot be postponed if the contract is not signed by 15 November 2020 or 15 January 2021) and need to take place on the foreseen date.

If this is the case for your project, you should specify below the following (max 3000 characters):

- the date on which the consortium would need to start its project activities covered by the grant. Only from this date on costs covered by the EU grant can be incurred;

- a detailed justification.The justification should explain why the activities foreseen (and their corresponding costs) cannot be delayed and why such a delay would jeopardise the project’s implementation.

Start date of project activity(ies): Activity(ies) and Justification:

PART D – Relevance of the Project

D.1 Why does the consortium undertake this project?

- Which problem(s) will the project address in theparticipating Partner Countries? Why are these problems pressing?

- Please explain the result of the need analysis carried out for each Partner Country and for each Partner institution and provide qualitative and quantitative evidence for your results.Please refer also to studies carried out and feasibility analyses undertaken. In particular explain for each institution,why the support from the CBHEactionis required.(limit 10.000 characters)

Problems and needs identifyed at the level of the Partner Country: [country 1]: - Partner institution […] needs and support required - Partner institution […] needs and support required Problems and needs identifyed at the level of the Partner Country: [country 2]: - Partner institution […] needs and support required - Partner institution[ …] needs and support required

(Please add Partner Countries/partners as appropriate)

Please identify the target groups and their needs in each Partner Country and in each Partner Country institution.(limit 8.000 characters)

Partner Country […] - Partner institution[...] - Partner institution[...] Partner Country [...] - Partner institution[...] - Partner institution [...]

(Please add partner countries/partners as appropriate)

How will the project address the relevant thematic national/regional priorities (see https://eacea.ec.europa.eu/erasmus-plus/funding/capacity-building-higher-education-2019_en) set by the Programme for its target country (ies)/region(s)? (limit 8.000 characters)

Partner Country /Region [...] Partner Country /Region [...]

(Please add Partner Countries/regions as appropriate)

D.2 Aims and objectives

- What does the proposal aim at in general? What are the project’s specific objectives?

- Explain how the specific objectives of the project address theproblems mentioned in Part D1 and the needs of each target group in each Partner Country. Demonstrate also that the set objectives are realistic and feasible in the national and institutional context(s).

(limit 8.000 characters)

Aims and specific objectives: [...] Partner Country [...] Partner Country

(Please add Partner Countries/regions as appropriate)

Please explain how the planned activities and the expected results meet the needs of the identified target groupsin the Partner Countries(limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

How will the project and its results contribute effectively to the objectives of the action Capacity-Building in the Field of Higher Educationin eachtargetedPartner Country? (limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

How do the project's objectives fit in with the modernisation and internationalisation agenda of the targeted higher education institutions in the Partner Countries and with the development strategy for higher education in each Partner Country involved in the project? (limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries/partners as appropriate)

Please explain how the proposal will pay attention tothe issues of inclusion, diversity and socio-economically disadvantaged participantsand/or organisations in the Partner Countries. (limit 2.000 characters)

D.3 Innovative character

Demonstrate why the proposal is innovative.

If it is complementary to previous/existing funded projects nationally or internationallyplease explain how the new proposal build on it/them and demonstrate its added value and why it is not a simple continuation thereof. (limit 2.000 characters)

If the proposal builds on any previous or existing EU-funded/non-EU funded national or international activities/projects in this field, please fill the following table for each of these projects.

☐

| Reference number |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) |  |  | Programme or initiative |  |
| Funded by |  |  |  |  |
| Title of the project |  |  |  |  |
| Coordinating organisation |  |  |  |  |
| Partner Countries /institutions targeted by this project |  |  |  |  |
| Website | http:// |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000characters). |  |  |  |  |

Please copy and paste tables as necessary

D.4European added value

Why is there a need for cooperation with the Programme Countries in this area of activity and a funding via the Erasmus+ Programme?Why can the intended results not be achieved through national, regional or local funding in the Partner Countries? (limit 2.000 characters)

D.5 Cross-regional cooperation

If your proposal is cross-regional, demonstrate the need for this cooperation between institutions from different regions.Please also explain the added value of this cross-regional cooperation for the targeted Partner Country institutions. (limit 2.000 characters)

PART E – Quality of the Project Design and Implementation

E.1 Project activities and methodology

Please provide a detailed description of the activities and the working methodology to be used for achieving the objectives (including major milestones, measurable indicators, etc.). (limit 6.000 characters)

Please demonstrate that the activities and the methodology mentioned are the most appropriate to achieve the envisaged results and that they are feasible. (limit 3.000 characters)

What concrete, tangible results are expected to be achieved at the end of the project's activities in each of the targetedPartner Countries? (limit 6.000 characters)

Partner Country [...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

For all types of activities(curriculum development, modernisation of governance, management and functioning of HEIs; strengthening of relations between HEIs and the wider economic and social environment), for each Partner Country institution please provide information in Part F.2 Organisation and Activities.

E.2Quality control and monitoring

Please explain what mechanisms willbe put in place for ensuring the quality of the project and how the evaluation will be carried out.If an external evaluation is foreseen, provide informationon the purpose and expected outcomes of this evaluation. Please define the specific quality measures established, as well as the benchmarks and indicators foreseen to verify the outcome of the action. Make sure that the information in this section is consistent with the project Logical Framework Matrix. (limit 3.000 characters)

E.3 Budget and cost effectiveness

Please describe the strategy adopted to ensure that the proposed results and objectives will be achieved in the most economical way, and on time. Explain the principles of budget allocation amongst partners. Indicate the arrangements adopted for financial management. What sources of co-funding will be used?(limit 3.000 characters)

If your project involves any "exceptional costs" related to travel, pleasejustify them here. (limit 2.000 characters)

Please justify the equipment costs for each Partner Country Institution:

- why the Partner Countryinstitutions need themfor the implementation of the project;

- their relations with the content to be developed and the specific activities to be implemented) and

- the estimated timeframe for their purchase as well asthe estimated place where they will be located (limit 3.000 characters)

Partner Country[...]: Partner Country [...]:

(Please add Partner Countries as appropriate)

Please complete the following Logical Framework Matrix:

☐

E.4 Logical Framework Matrix – LFM

| Wider Objective:☒ What is the general objective, to which the project will contribute? | Indicators of progress: What are the key indicators related to the wider objective? | How indicators will be measured: What are the sources of information on these indicators? |  |  |
| --- | --- | --- | --- | --- |
| Specific Project Objective/s: What are the specific objectives, which the project shall achieve? | Indicators of progress: What are the quantitative and qualitative indicators showing whether and to what extent the project’s specific objectives are achieved? | How indicators will be measured: What are the sources of information that exist and can be collected? What are the methods required to get this information? | Assumptions & risks What are the factors and conditions not under the direct control of the project, which are necessary to achieve these objectives? What risks have to be considered? | How the risks will be mitigated: |
| Outputs (tangible) and Outcomes (intangible): Please provide the list of concrete DELIVERABLES - outputs/outcomes (grouped in Workpackages), leading to the specific objective/s.: | Indicators of progress: What are the indicators to measure whether and to what extent the project achieves the envisaged results and effects? | How indicators will be measured: What are the sources of information on these indicators? | Assumptions & risks What external factors and conditions must be realised to obtain the expected outcomes and results on schedule? | How the risks will be mitigated: |
| Activities: What are the key activities to be carried out (grouped in Workpackages) and in what sequence in order to produce the expected results? | Inputs: What inputs are required to implement these activities, e.g. staff time, equipment, mobilities, publications etc.? |  | Assumptions ¦& risks What pre-conditions are required before the project starts? What conditions outside the project’s direct control have to be present for the implementation of the planned activities? | How the risks will be mitigated: |

Please complete the following work plan.☒

E.5 Work Plan

On the following pages, please provide your work plan for each year of the proposed project

- Please use the model provided below.

- Please complete a one-page work plan for each project year.

- For each year of your proposal, please complete a work plan indicating the deadlines for each outcome and the period and location in which your activities will take place.

- If needed, please insert additional rows into the work plan tables.

- The same reference and sub-reference numbers as used in the logical framework matrix must be assigned to each outcome and related activities.

Examples:

Activity carried out in the Programme Country:         = (E.g. activity in France for two weeks in the first month of the project 2= under M1)

Activity carried out in the Partner Country (ies):        X (E.g., activity in Tunisia for three weeks in the second month of the project: 3X under M2)

WORKPLAN for project year 1☒

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1 Analiza trenutnog stanja | 4 | X |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2 Razvoj novih curriculuma | 4 |  | X |  |  |  |  |  |  |  |  |  |  |
|  | 3.3 Osavremenjivanje kurikuluma AI i mačinsko programiranje | 8 | x | x |  |  |  |  |  |  |  |  |  |  |
|  | 3.4 Osavremenjivanje kurikuluma | 4 |  |  | x |  |  |  |  |  |  |  |  |  |

WORKPLAN for project year 2☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |

WORKPLAN for project year 3☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |

Please complete the information on each work package for your project

E.6 Work packages

Please enter the different project activities you intend to carry out in your project. Make sure that the information in this section is consistent with the project Logical Framework Matrix.

| Work package type and ref.nr ☒ | PREPARATION |  |  | 1 |
| --- | --- | --- | --- | --- |
| Title | Osavremenjivanje trenutnih kurikulum PI I SI u nacionalnim partmerskim institucijama |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 3.1 Analiza trenutnog stanja 3.2 Razvoj novih curriculuma 3.3 Osavremenjivanje kurikuluma AI i mačinsko programiranje 3.4 Osavremenjivanje kurikuluma |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Analiza trenutnog stanja |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.111.To effectively analyze the current state through focus groups and interviews, begin by clearly defining the objectives of the research. Develop open-ended questions that will help uncover detailed insights into the current usage of IT technologies, satisfaction with existing curricula, and identification of educational gaps. Select a diverse group of participants from among students, faculty, administrative staff, and external partners to ensure a broad range of perspectives. 3.1.1.2.Assign skilled moderators and interviewers to conduct the sessions, ensuring that discussions stay focused and all participants have the opportunity to voice their opinions. Record the sessions with participants' consent for accuracy, and take detailed notes to capture non-verbal cues and dynamics. After collecting the data, transcribe and summarize the recordings to identify key themes, insights, and patterns. Analyze this qualitative data to categorize responses and delve deeper into the trends and anomalies that emerge. 3.1.2.Compile the findings into a detailed report that outlines the methodologies used, the insights gathered, and actionable recommendations. This report should provide a clear understanding of stakeholders' perspectives on the current state and highlight areas for improvement. Additionally, prepare a summary presentation for project partners and stakeholders to showcase the key findings and how they will inform the project's next steps. |  |  |  |
|  | Due date | M1 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Razvoj novih curriculuma |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.2.1.The second activity in the project involves preparing and distributing presentation materials and summary documents to stakeholders, followed by gathering their feedback through organized consultations. Start by creating detailed, engaging presentation materials that clearly outline the findings from the initial analysis. These should be accompanied by summary documents that condense the key insights and preliminary recommendations. 3.2.2.Identify all relevant stakeholders, including academic staff, administrative bodies, and external partners, and distribute the materials through the most effective channels such as email, project websites, or direct meetings. Organize a series of meetings or workshops throughout the month to discuss these materials with the stakeholders, ensuring there is ample opportunity for in-depth discussion and feedback collection. 3.2.3.During these sessions, use feedback forms and conduct surveys to gather stakeholders' opinions, suggestions, and concerns. Also, meticulously record the minutes of each meeting to capture the essence of the discussions. After collecting all feedback, analyze and compile it into a comprehensive report that summarizes stakeholder reactions, concerns, and the overall acceptance of the findings. |  |  |  |
|  | Due date | M2 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Osavremenjivanje kurikuluma AI i mačinsko programiranje |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.3.1.The third activity of the project focuses on refining the curriculum change recommendations based on stakeholder feedback from previous consultations. Start by thoroughly reviewing all feedback to ensure that the recommendations align with educational needs and industry expectations. Update the curriculum recommendations to reflect a balance between current educational standards and future requirements. 3.3.2.Next, gather all relevant data to support the necessity and benefits of the proposed changes and compile this into an analytical report. This report should detail the data analysis and justify the curriculum recommendations, clearly showing the expected impact on educational outcomes. 3.3.3.Then, create a detailed implementation plan that outlines the specific steps required to enact the curriculum changes. This plan should include timelines, resources needed, and assign responsibilities to appropriate parties. To aid in visualization and planning, develop a Gantt chart or similar tool that represents the timeline and phases of the implementation process. 3.3.4.Simultaneously, prepare presentation materials that summarize the refined recommendations, the analytical support for these changes, and the detailed implementation plan. These materials should be designed to clearly communicate the project details and garner support from all stakeholders, ensuring they are comprehensive and compelling. |  |  |  |
|  | Due date | M2 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Osavremenjivanje kurikuluma AI i mačinsko programiranje |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.4.1.The fourth activity in the project involves the rollout of new or revised courses according to the established implementation plan. Start by coordinating with academic departments to ensure all course materials are prepared and available, and actively inform students about the new course offerings through various university channels to ensure high visibility and awareness. 3.4.2.Next, set up a monitoring system to track and record enrollments in these courses, capturing essential data such as student numbers and department details. Regular analysis of this enrollment data will help gauge the popularity and initial acceptance of the courses among students. 3.4.3.To gather initial reactions, develop feedback mechanisms like surveys or forms for students and faculty participating in the new courses. These feedback tools should ask about their experiences with course content, delivery methods, and any immediate challenges faced. Additionally, consider conducting interviews or focus groups with select participants for more detailed insights. |  |  |  |
|  | Due date | M3 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title |  |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description |  |  |  |  |
|  | Due date |  |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title |  |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description |  |  |  |  |
|  | Due date |  |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☐ | DEVELOPMENT |  |  | 2 |
| --- | --- | --- | --- | --- |
| Title | Analiza ciljeva za unapređenje programa stručnih praksi u oblasti Poslovne informatike |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks | 2.1.Tipovi praksi 2.2.Analiza trenutnog stanja 2.3. Studijske posete 2.4. Formulisanje strategije 2.5. Implementacija plana |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.1 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Tipovi praksi |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 1. Definišite Ciljeve Analize 1.1 Postavite jasne ciljeve za analizu trenutnih tipova praksi. 1.2 Razumeti kako različiti tipovi praksi funkcionišu i koji su njihovi efekti. 1.3 Proceni efikasnost i korisnost različitih praksi u obrazovanju ili profesionalnom razvoju. 1.4 Identifikujte nedostatke i oblasti koje treba poboljšati u primeni praksi. 2. Formulisanje Pitanja 2.1 Razvijajte pitanja koja će pružiti detaljne uvide o različitim tipovima praksi. 2.2 Kako različiti tipovi praksi utiču na vaš profesionalni ili obrazovni napredak? 2.3 Šta su ključne prednosti i mane trenutnih praksi? 2.4 Da li postoje specifične oblasti koje trenutno ne pokrivaju ponuđeni tipovi praksi? 2.5 Postavite dodatna pitanja za dublju analizu. 2.6 Koje su najveće prepreke u primeni trenutnih tipova praksi? 2.7 Kako se osećate u vezi sa nivoom podrške tokom prakse? 2.8 Koje promene u tipovima praksi bi vam bile najkorisnije? 3. Izbor Učesnika 3.1 Odaberite raznoliku grupu učesnika da biste obuhvatili sve aspekte različitih tipova praksi. 3.2 Uključite studente koji učestvuju u različitim vrstama praksi. 3.3 Uključite mentore i instruktore koji organizuju i nadgledaju prakse. 3.4 Uključite profesionalce koji su prošli kroz različite tipove praksi. 4. Organizacija i Vođenje Sesija 4.1 Angažujte kvalifikovane moderatore za vođenje fokus grupa i intervjua. 4.2 Osigurajte da diskusije budu fokusirane na specifične aspekte i tipove praksi. 4.3 Osigurajte da svi učesnici imaju priliku da izraze svoja mišljenja i iskustva. 4.4 Beležite sesije uz pristanak učesnika. 4.5 Snimajte audio ili video zapise sesija za preciznost i kasniju analizu. 4.6 Pravite detaljne beleške o neverbalnim signalima i dinamici sesije. 5. Prikupljanje i Analiza Podataka 5.1 Transkribujte snimke i organizujte podatke iz sesija. 5.2 Pripremite transkripte snimaka i sistematizujte odgovore. 5.3 Kategorizujte i kodirajte odgovore da biste identifikovali ključne teme u vezi sa tipovima praksi. 5.4 Analizirajte prikupljene podatke. 5.5 Identifikujte obrasce i ključne teme u odgovorima učesnika. 5.6 Proučite trendove i izazove u vezi sa različitim tipovima praksi i formulirajte preporuke za poboljšanje. 6. Izrada Izveštaja i Prezentacija 6.1 Pripremite sveobuhvatan izveštaj. 6.2 Opišite metodologiju istraživanja i pristup analizi tipova praksi. 6.3 Prezentujte ključne uvide, tematske analize i efikasnost različitih praksi. 6.4 Izložite konkretne preporuke za poboljšanje i optimizaciju praksi. 6.5 Kreirajte sažetu prezentaciju. 6.6 Vizualizujte ključne nalaze i preporuke na jasan i atraktivan način. 6.7 Istaknite sledeće korake i preporuke za unapređenje praksi. |  |  |  |
|  | Due date |  |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr☐ | QUALITY PLAN |  |  | 2.2 |
| --- | --- | --- | --- | --- |
| Title | Analiza trenutnog stanja |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description | 2.1. Definišite Ciljeve Istraživanja 1.1 Jasno definišite ciljeve analize trenutnog stanja kako biste usmerili istraživanje. 1.2 Razumeti trenutnu upotrebu IT tehnologija i resursa. 1.3 Proceni efikasnost postojećih obrazovnih kurseva i materijala. 1.4 Identifikujte praznine u obrazovanju i mogućnosti za poboljšanje. 2. Razvijanje Pitanja za Fokus Grupe i Intervjue 2.1 Razvijte otvorena pitanja koja će pomoći u otkrivanju detaljnih uvida. 2.2 Kako trenutno koristite IT tehnologije u vašem obrazovanju/poslu? 2.3 Kako ocenjujete kvalitet i relevantnost postojećih obrazovnih materijala? 2.4 Da li postoje specifične oblasti ili teme koje su nedovoljno pokrivene? 2.5 Razvijajte dodatna pitanja za otkrivanje dubljih uvida. 2.6 Koje su najveće prepreke ili izazovi sa trenutnim materijalima i tehnologijama? 2.7 Kako se osećate u vezi sa nivoom podrške i obuke koju trenutno dobijate? 2.8 Koje bi promene ili poboljšanja u resursima i metodama učenja bile najkorisnije? 3. Odabir Učesnika 3.1 Odaberite raznoliku grupu učesnika kako biste osigurali sveobuhvatan uvid. 3.2 Uključite studente različitih godina i predmeta. 3.3 Uključite nastavnike i akademske savetnike. 3.4 Uključite administrativno osoblje i spoljne partnere (ako je primenljivo). 4. Vođenje Sesija 4.1 Angažujte kvalifikovane moderatore za vođenje fokus grupa i intervjua. 4.2 Osigurajte da diskusije ostanu fokusirane na teme istraživanja. 4.3 Osigurajte da svi učesnici imaju priliku da izraze svoje mišljenje. 4.4 Beležite sesije uz pristanak učesnika. 4.5 Snimite audio ili video zapise sesija za tačnost. 4.6 Uz snimanje, pravite detaljne beleške o neverbalnim signalima i dinamici sesije. 5. Analiza Podataka 5.1 Transkribujte i organizujte podatke iz sesija. 5.2 Pripremite transkripte snimaka fokus grupa i intervjua. 5.3 Kategorizujte i kodirajte odgovore da biste identifikovali ključne teme i obrasce. 5.4 Analizirajte prikupljene podatke. 5.5 Identifikujte ključne teme i obrasce u odgovorima učesnika. 5.6 Proučite i analizirajte trendove i anomalije koje se pojavljuju u podacima. |  |  |  |
| Tasks |  |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

| Work package type and ref.nr☐ | QUALITY PLAN |  |  | 2.3. |
| --- | --- | --- | --- | --- |
| Title | Studijske posete |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description | 1. Postavljanje Okvira za Analizu 1.1 Utvrdite osnovne ciljeve analize studijskih poseta. 1.2 Razjasnite šta želite da postignete analizom studijskih poseta. 1.3 Definišite kako će analiza doprineti unapređenju obrazovnih i profesionalnih iskustava. 1.4 Istražite koje aspekte studijskih poseta treba detaljno razmotriti. 2. Razvijanje Ključnih Pitanja 2.1 Formulišite pitanja koja će istražiti efikasnost studijskih poseta. 2.2 Koji su glavni ciljevi studijskih poseta koje ste prisustvovali? 2.3 Kako ove posete utiču na vaše obrazovanje ili profesionalni razvoj? 2.4 Koje su prednosti i mane trenutnih studijskih poseta? 2.5 Postavite pitanja za dubinsku analizu. 2.6 Koji su najveći izazovi koje ste iskusili tokom studijskih poseta? 2.7 Kako ocenjujete kvalitet resursa i podrške tokom poseta? 2.8 Šta bi moglo unaprediti iskustvo studijskih poseta? 3. Izbor i Angažovanje Učesnika 3.1 Izaberite relevantne učesnike za istraživanje. 3.2 Uključite studente koji su učestvovali u studijskim posetama. 3.3 Angažujte organizatore i koordinatore studijskih poseta. 3.4 Uključite mentore i profesionalce sa iskustvom u ovim posetama. 4. Organizacija Istraživačkih Aktivnosti 4.1 Planirajte kako ćete voditi fokus grupe i intervjue. 4.2 Angažujte kvalifikovane moderatore za vođenje sesija. 4.3 Osigurajte da sesije obuhvate sve relevantne aspekte studijskih poseta. 4.4 Omogućite svim učesnicima da slobodno izraze svoja mišljenja. 4.5 Snimajte sesije uz odobrenje učesnika. 4.6 Prikupite beleške o ključnim tačkama i neverbalnim signalima tokom diskusije. 4.7 Organizujte podatke za kasniju analizu. 5. Obrada i Evaluacija Podataka 5.1 Transkribujte i sortirajte snimke sa sesija. 5.2 Organizujte podatke u smislu tematskih kategorija. 5.3 Identifikujte ključne teme i obrasce iz prikupljenih informacija. 5.4 Analizirajte prikupljene podatke. 5.5 Proučite obrasce u odgovorima i ključne nalaze. 5.6 Formulišite preporuke na osnovu analize. 6. Izrada Izveštaja i Prezentacija 6.1 Sastavite sveobuhvatan izveštaj o nalazima analize. 6.2 Opišite metodologiju i pristup istraživanju studijskih poseta. 6.3 Prezentujte ključne uvide i nalaze u vezi sa studijskim posetama. 6.4 Pripremite preporuke za poboljšanje iskustava sa studijskim posetama. 6.5 Pripremite sažetu prezentaciju za relevantne zainteresovane strane. 6.6 Uključite vizualne prikaze nalaza za bolju razumljivost. 6.7 Predložite konkretne korake za unapređenje na osnovu nalaza. |  |  |  |
| Tasks |  |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

| Work package type and ref.nr☐ | QUALITY PLAN |  |  | 2.4. |
| --- | --- | --- | --- | --- |
| Title | Formulisanje strategije |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description | 1. Postavljanje Osnovnih Ciljeva 1.1 Definišite dugoročne i kratkoročne ciljeve strategije. 1.2 Razjasnite šta želite da postignete formulisanjem strategije. 1.3 Utvrdite ključne rezultate koje strategija treba da postigne. 1.4 Identifikujte oblasti koje zahtevaju strateško usmeravanje. 2. Analiza Trenutne Situacije 2.1 Sprovodite analizu trenutnog stanja. 2.2 Istražite unutrašnje i spoljne faktore koji utiču na organizaciju. 2.3 Prikupite podatke o trenutnim izazovima i prilikama. 2.4 Ocenite resurse i kapacitete dostupne za implementaciju strategije. 2.5 Procenite konkurenciju i tržište. 2.6 Analizirajte snage, slabosti, prilike i pretnje (SWOT analiza). 2.7 Razumite trendove i promene u industriji ili sektoru. 3. Razvoj Strateških Opcija 3.1 Identifikujte moguće strateške pravce. 3.2 Razvijajte različite scenarije i opcije koje odgovaraju ciljevima. 3.3 Razmotrite različite pristupe i metode za postizanje ciljeva. 3.4 Evaluirajte prednosti i mane svake strateške opcije. 4. Izbor Najbolje Strategije 4.1 Uporedite i analizirajte razvijene strateške opcije. 4.2 Razmotrite izvodljivost, efikasnost i održivost svake opcije. 4.3 Donosite odluku o najprikladnijoj strategiji na osnovu analize. 4.4 Pripremite plan za implementaciju izabrane strategije. 5. Razvoj Akcionog Plana 5.1 Detaljno planirajte korake za implementaciju strategije. 5.2 Definišite konkretne zadatke, odgovorne osobe i rokove. 5.3 Postavite merila za praćenje napretka i uspeha. 5.4 Identifikujte potrebne resurse i budžet za sprovođenje strategije. 5.5 Razvijajte plan za upravljanje rizicima i kriznim situacijama. 5.6 Planirajte komunikaciju i obuku potrebnu za implementaciju. 6. Implementacija Strategije 6.1 Pokrenite implementaciju strategije prema akcionom planu. 6.2 Koordinirajte aktivnosti i nadgledajte sprovođenje. 6.3 Osigurajte da svi uključeni imaju jasnu ulogu i razumevanje strategije. 6.4 Obezbedite podršku i resurse za uspešnu implementaciju. 7. Praćenje i Evaluacija 7.1 Postavite mehanizme za praćenje napretka i izvršenja strategije. 7.2 Redovno proveravajte postignute rezultate u odnosu na ciljeve. 7.3 Analizirajte odstupanja i identifikujte potrebne korektivne mere. 7.4 Izvršite evaluaciju strategije i njenog uticaja na organizaciju. |  |  |  |
| Tasks |  |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

| Work package type and ref.nr☐ | QUALITY PLAN |  |  | 2.5. |
| --- | --- | --- | --- | --- |
| Title | Implementacija plana |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description | 1. Priprema za Implementaciju 1.1 Definišite jasne ciljeve za implementaciju. 1.2 Razjasnite šta želite da postignete tokom implementacije i opišite očekivane rezultate. 1.3 Identifikujte oblasti koje zahtevaju strateško usmeravanje i potrebne resurse (ljudi, finansije, tehnologija). 1.4 Ocenite postojeće kapacitete i pripremite tim za implementaciju, uključujući obuku i pripremu ključnih članova tima. 2. Razvoj Detaljnog Akcionog Plana 2.1 Razradite detaljan akcionog plan, definišući korake i zadatke za implementaciju. 2.2 Postavite ključne pokazatelje uspeha (KPI) za praćenje napretka i rezultate. 2.3 Planirajte komunikaciju i koordinaciju, razvijajući plan komunikacije za sve učesnike i zainteresovane strane. 2.4 Obezbedite redovne sastanke i izveštaje o napretku, uz identifikaciju potrebnih resursa i budžeta za sprovođenje strategije. 3. Pokretanje Implementacije 3.1 Pokrenite aktivnosti prema akcionom planu, inicirajući prvi korak implementacije prema planiranim zadacima. 3.2 Koordinirajte i nadgledajte aktivnosti, prateći napredak prema planu i pravite prilagođavanja ako je potrebno. 3.3 Rešavajte probleme i prepreke koje se pojave tokom implementacije, obezbeđujući pravilnu dokumentaciju i izveštavanje o ključnim aktivnostima i rezultatima. 4. Praćenje i Kontrola 4.1 Pratite napredak u odnosu na ciljeve koristeći KPI-e i druge metrike za merenje uspeha. 4.2 Uporedite stvarne rezultate sa planiranim ciljevima, analizirajte efikasnost i efektivnost sprovedenih aktivnosti. 4.3 Identifikujte neusaglašenosti i oblasti za poboljšanje, upravljajući rizicima i rešavajući probleme kroz razvijene planove za upravljanje rizicima. 5. Evaluacija i Izveštavanje 5.1 Evaluirajte rezultate implementacije u odnosu na ciljeve i KPI-e, identifikujući uspehe i oblasti koje zahtevaju dodatne napore. 5.2 Pripremite detaljan izveštaj o napretku, postignućima i izazovima, i podelite ga sa ključnim zainteresovanim stranama. 5.3 Prezentujte nalaze i preporuke za dalji rad, održavajući sastanke za predstavljanje rezultata i predlaganje strategija za buduće akcije. 6. Revizija i Prilagođavanje 6.1 Prilagodite plan na osnovu evaluacije i povratnih informacija, izvršavajući potrebne izmene kako bi odgovarale novim uslovima. 6.2 Implementirajte promene i poboljšanja, obezbeđujući da svi članovi tima budu obavešteni o novim pristupima i promenama. 6.3 Nastavite sa kontinuiranim praćenjem i poboljšanjima, razvijajući strategije za dugoročno uspešno sprovođenje i prilagođavanje. |  |  |  |
| Tasks |  |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

| Work package type and ref.nr☐ | QUALITY PLAN |  |  | 3 |
| --- | --- | --- | --- | --- |
| Title |  |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks |  |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title |  |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description |  |  |  |  |
|  | Due date |  |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☒ | DISSEMINATION & EXPLOITATION |  |  | 4 |
| --- | --- | --- | --- | --- |
| Title |  |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks |  |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title |  |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description |  |  |  |  |
|  | Due date |  |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☒ | MANAGEMENT |  |  | 5 |
| --- | --- | --- | --- | --- |
| Title |  |  |  |  |
| Related assumptions and risks |  |  |  |  |
| Description |  |  |  |  |
| Tasks |  |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation |  |  |  |  |
| Participating Organisation |  |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes☒ | Work Package and Outcome ref.nr | 5.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title |  |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description |  |  |  |  |
|  | Due date |  |  |  |  |
|  | Languages |  |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

E.7 Consortium partners involved and human resources required to complete the work packages

Indicative input of consortium staff - The total number of days per staff category should correspond with the information provided in the budget tables.☐

| Work Package Ref.nr | Partner nr | Partner acronym | Country | Number of staff days☒ |  |  |  |  | Exact Role and tasks of each person in the work package |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Category 1 | Category 2 | Category 3 | Category 4 | Total |  |
| PREPARATION |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| DEVELOPMENT |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| QUALITY PLAN |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| DISSEMINATION & EXPLOITATION |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| MANAGEMENT |  |  |  |  |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |

Please insert rows as necessary

PART F – Quality of the Project Team and Cooperation Arrangements

F.1 Background of partnership and the proposal preparation

Please provide shortly the history of cooperation between partners (if any). How the idea of the project was developed and which/ who among partners contributed to the proposal development. (limit 3.000 characters)

If relevant, please explain how and to which extent the project benefits from the experience and participation of non–academic partners. (limit 3.000 characters)

Please explain the role and the participation of the Programme Country partners and their support in the development of the different activities (e.g. in the development of the curricula) and (limit 3.000 characters)

F.2 Cooperation arrangements, management and communication

Please define the organisation of the implementation of the project and the division of tasks between the partners. Please explain the allocation of resources for each activity. Explain also how the tasks are distributed amongst the partners and how project "ownership" is ensured (limit 3.000 characters).

Please explain the overall project and partnership management making specific reference to the management plan and how decisions will be taken. Please describe how permanent and effective communication and reporting will be ensured as well as the measures put in place for conflict resolution (limit 2.000 characters).

F.3 Organisations and activities

This part must be completed separately by each organisation participating in the project (applicant and partners with its affiliated entities (if any)).

☒

| Partner number ☒ |  |  |  |  | P1 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym |  |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List ofsubjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List ofsubjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project anddefine clear the activities to be held in your institution(limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment( only for Partner Country institutions) Please fill in if you are applying for this type of project anddefine clear the activities to be held in your institution(limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |

Please copy and paste tables as necessary

F.4 List of Associated Partners

(Where applicable)

Capacity-building projects can involve associated partners who contribute to the implementation of specific project tasks/activities or support the dissemination and sustainability of the project. Associated Partners cannot be responsible for core activities of the project (e.g. management, coordination, monitoring, leader of a work group etc.).No financial contribution from the project grant will be allocated to these organisations.

☐

| Name of organisation | Type of institution | Website | City | Country | Role in the project | Activities and related Work Packages |
| --- | --- | --- | --- | --- | --- | --- |

Please insert rows as necessary

PART G – Impact and Sustainability

G.1 Expected impact of the project

Please explain which target groups will use the project outputs /products /results. Describe how the target groups will be reached and involved during the life of the project and afterwards and how the project will benefit the target group at local, regional, national and/or regional level. Please structure your description according to the different levels of impact and stakeholders.

☐

| # | Project results | Who will they impact at national, regional level? | How? |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

Please insert rows as necessary

Overview of short term impact indicators (during the project EU funding period)

☐

| Short term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |

Please insert rows as necessary

Overview of long term impact indicators (after the projects EU funding period)

☐

| Long term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |

Please insert rows as necessary

G.2 Dissemination and exploitation strategy

Please explain how the dissemination will be organisedduring and after the project's lifetime. Define each target group and what communication channels will be used to reach them and when.

☒

| Target Group | Means of Communication to Reach These Target Groups | When | Indicators to measure the effectiveness of the means of communication |
| --- | --- | --- | --- |

Please insert rows as necessary

G.3 Sustainability

Explain how exploitation activities will ensure optimal use of the results within the project's lifetime and afterwards. Explain how the impact of the project will be sustained beyond its lifetime. Please list the outcomes that you consider sustainable and describe the strategy to ensure their long lasting use beyond the project's lifetime. Also explain how the results will be mainstreamed and multiplied at national/regional level. Describe the strategy foreseen to attract co-funding and other forms of non-EU support for the project.

☐

| Sustainable Outcomes | Strategy to ensure their sustainability | Resources necessary to achieve this | Where will these resources be obtained? |
| --- | --- | --- | --- |

Please insert rows as necessary

PART H - Other EU grants

Please list the projects for which the organisations involved in this application have received financial support from EU programmes.

☒

| Programme or initiative | Reference number | Beneficiary Organisation | Title of the Project |
| --- | --- | --- | --- |

Please insert rows as necessary.

Please list other EU grant proposalssubmitted by your organisation, or by any partner organisation in this project proposal. For each grant application, please mention the EU Programme concerned and the amount requested.

☐

| Programme concerned | Beneficiary Organisation | Amount requested |
| --- | --- | --- |

Please insert rows as necessary.

PART I- Check List

Please make sure that you fully completed each part of this application form, as follows:

☒

☐	PART D - RELEVANCE OF THE PROJECT

☐	PART E - QUALITY OF THE PROJECT DESIGN AND IMPLEMENTATION

☐	E.4 Logical Framework Matrix

☐	E.5 Workplan

☐	E.6 Work packages

☐	PART F - Quality of the Project Team and Cooperation Arrangements

☐	PART G - Impact and Sustainability

☐	PART H - Other EU grants

☐	PART I - CHECK LIST

Please see Programme Guide, Part B for your action, Table A – Project Implementation (amounts in Euro per day) Programme Countries and Table B - Project Implementation (amounts in Euro per day) Partner Countries.