3+3. LOGICAL FRAMEWORK MATRIX – LFM

| Wider Objective: What is the overall broader objective, to which the project will contribute? | ### Indicators of progress: What are the key indicators related to the wider objective? | #### How indicators will be measured: What are the sources of information on these indicators? |  |
| --- | --- | --- | --- |
| Specific Project Objective/s: What are the specific objectives, which the project shall achieve? Enhancement and implementation of state-of-the-art IT technologies in Serbian universities. Enhancement and implementation of state-of-the-art student practices. Enhancement and implementation of the curriculum for Software Engineering and Business Informatics. Implementation of modern laboratories and university state-of-the-art technological centers. | ## Indicators of progress: What are the quantitative and qualitative indicators showing whether and to what extent the project’s specific objectives are achieved? | How indicators will be measured: What are the sources of information that exist and can be collected? What are the methods required to get this information? | Assumptions & risks: What are the factors and conditions not under the direct control of the project, which are necessary to achieve these objectives? What risks have to be considered? |
| Outputs (tangible) and Outcomes (intangible): - Please provide the list of concrete DELIVERABLES - outputs/outcomes (grouped in Workpackages), leading to the specific objective/s.: 1. Analiza trenutnog stanja, potreba i dobrih praksi 1.1 Procena potreba i studija izvodljivosti e-menadžment Sistema 1.1.1 Analiza potreba za razvoj novog IT sistema. 1.1.2 Razvijen izveštaj o potrebama za razvoj IT sistema. 1.2 Dizajn i arhitektura rešenja 1.2.1 Odabrana odgovarajuća blockchain tehnologiju 1.2.2 Razvijen dizajn sistemske arhitekture i interfejsa. 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima 1.3.1 Analiza broja i vrsti praksi koje se trenutno nude. 1.3.2 Analiza zadovoljstva studenata I firmi postojećim ssistemom praksi 1.3.3 Analiza postojećih partnerstva sa kompanijama i procena njihove efikasnosti. 1.3.4 Sveukupna analiza stanja stručne prakse na univerzitetu 1.4 Analiza potreba privrede 1.4.1 Identifikacija mogućih partnera u industriji 1.4.2 Izveštaj o mogućnostima novih partnera 1.4.3 Analiza stručnih praksi koje nude mala I srednja preduzeća 1.5 Primeri dobre prakse u implementaciji laboratorija I centara 1.5.1 Detaljni okvir koji određuje kriterijume I metrike analize 1.5.2 Kompilacija skupljenih izveštaja, publikacija I studija slučajeva iz izabranih univerziteta 1.5.3 Skupljeni podaci iz intervjua I anketa sa partnerima u izabranim EU univerzitetima 1.5.4 Snimci I transkripti iz virtuelnih poseta I sesija observacije 1.5.5 Sveobuhvatni izveštaj koji detaljno opisuje najbolje prakse, inovativne pristupe I preporuke 2. Razvoj modernih IT tehnologija na srpskim univerzitetima 2.1 Razvoj prototipa 2.1.1 Funkcionalan MVP; Dokumentacija o funkcionalnostima MVP-a. 2.1.2 Izveštaj o rezultatima početnog testiranja korisnika; Zbirka povratnih informacija korisnika. 2.2 Strategija implementacije 2.2.1 Dokumentacija o razvijenom kompletnom sistemu; Izveštaj o završetku razvoja. 2.2.2 Izveštaj o integraciji sa postojećim univerzitetskim sistemima; Dokumentacija o interfejsima i protokolima integracije. 2.3 Ispitivanje i osiguranje kvaliteta 2.3.1 Izveštaj o rezultatima sveobuhvatnog testiranja; Dokumentacija o sigurnosnim, performansnim i UAT testovima. 2.3.2 Izveštaj o rešenim i ispravljenim problemima; Lista identifikovanih i rešenih problema. 2.4 Implementacija i uvođenje 2.4.1 Sprovedeni pilot programi; Povratne informacije od korisnika tokom pilot faze. 2.4.2 Izveštaj o implementaciji sistema u svim relevantnim institutima; Dokumentacija o uvođenju. 2.5 Evaluacija i kontinuirano poboljšanje 2.5.1 Izveštaji o performansama sistema; Analitički podaci o korišćenju i učinkovitosti. 2.5.2 Dokumentacija o ažuriranjima i poboljšanjima; Povratne informacije od korisnika o poboljšanjima. 2.6 Usklađenost i sigurnost 2.6.1 Izveštaji o usklađenosti i sigurnosne revizije; Lista identifikovanih problema sa usklađenošću i sigurnošću. 2.6.2 Ažurirani sigurnosni protokoli; Dokumentacija o usklađenosti. 2.7 Održivost i skalabilnost 2.7.1 Raspored održavanja i ažuriranja; Planovi za redovno održavanje. 2.7.2 Dokumentacija o dizajnu karakteristika za buduću potražnju; Izveštaji o sprovedenim skalabilnim rešenjima. 3. Osavremenjivanje stručnih praksi 3.1 Studijske posete ucid u dobre prakse 3.1.1 Studijske posete poslovnim simulacijam 3.1.1.1 Itinerar posete 3.1.1.2 Aranžmani za putovanje i smeštaj 3.1.1.3 Priprema materijala za posete 3.1.1.4 Informacione brošure i vodiči 3.1.1.5 Detaljna agenda posete 3.1.1.6 Dokument za pozadinske informacije 3.1.1.7 Obrazovne prezentacije 3.1.1.8 Raspored i vodič posete 3.1.1.9 Prezentacioni materijal i rasporedi govornika 3.1.1.10 Interaktivni plan sesije 3.1.1.11 Raspored događaja za umrežavanje 3.1.1.12 Beleške sa sastanka i observacioni izveštaji 3.1.1.13 Rezimei sa konferencija i radionica 3.1.1.14 Rezimei vrituelnih poseta i demonstracija 3.1.2 Studijske posete panel diskusijama 3.1.2.1 Itinerar posete 3.1.2.2 Aranžmani za putovanje i smeštaj 3.1.2.3 Priprema materijala za posete 3.1.2.4 Informacione brošure i vodiči 3.1.2.5 Detaljna agenda posete 3.1.2.6 Dokument za pozadinske informacije 3.1.2.7 Obrazovne prezentacije 3.1.2.8 Raspored i vodič posete 3.1.2.9 Prezentacioni materijal i rasporedi govornika 3.1.2.10 Interaktivni plan sesije 3.1.2.11 Raspored događaja za umrežavanje 3.1.2.12 Beleške sa sastanka i observacioni izveštaji 3.1.2.13 Rezimei sa konferencija i radionica 3.1.2.14 Rezimei vrituelnih poseta i demonstracija 3.2 Organizacija bisnis simulacija 3.2.1 Document outlining specific learning outcomes for the simulation. 3.2.2 Simulation scope document detailing duration, components, and participation levels. 3.2.3 Detailed business scenario document. 3.2.4 Comprehensive storyline with integrated business elements. 3.2.5 List of recruited facilitators, mentors, and support staff. 3.2.6 Scripts, role descriptions, and instruction manuals for participants. 3.2.7 Compilation of background materials and documents. 3.2.8 Developed digital tools or platforms. 3.2.9 Set of printed and physical materials. 3.2.10 Promotion plan and materials. 3.2.11 Registration system and informational materials. 3.2.12 Orientation session agenda and materials. 3.2.13 Preparatory materials and task assignments. 3.2.14 Setup and readiness checklist. 3.2.15 Technical system test reports. 3.2.16 Introductory session materials. 3.2.17 Facilitator's guide and session logs. 3.2.18 Monitoring logs and adjustment records. 3.2.19 Debriefing session summary and feedback reports. 3.3 Panel Diskusije AI i Machine learning 3.3.1 Venue setup checklist and test report. 3.3.2 Promotional materials and distribution records. 3.3.3 Welcome script and introduction plan. 3.3.4 Panel discussion guide and facilitation notes. 3.3.5 Q&A session plan and summary of audience questions. 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju 3.4.1 Venue setup checklist and test report. 3.4.2 Promotional materials and distribution records. 3.4.3 Welcome script and introduction plan. 3.4.4 Panel discussion guide and facilitation notes. 3.4.5 Q&A session plan and summary of audience questions. 4. Formiranje laboratorije za digitalnu transformaciju 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps 4.1.1 List of recruited stakeholders; stakeholder recruitment report. 4.1.2 Committee roles and responsibilities document; organizational chart. 4.2 Conduct a Needs Assessment 4.2.1 Needs assessment report; survey and interview summaries. 4.2.2 Assessment report on current facilities and resources. 4.3 Develop a Detailed Plan 4.3.1 Detailed project plan document. 4.3.2 Technical specifications document. 4.4 Procure Equipment and Software 4.4.1 Vendor selection report; list of selected vendors. 4.4.2 Purchase orders; delivery receipts; equipment and software inventory. 4.5 Prepare the Physical Space 4.5.1 Location approval document; space allocation report. 4.5.2 Renovation completion report; setup checklist. 4.6 Install Equipment and Software 4.6.1 Installation report; setup verification checklist. 4.6.2 Software installation and configuration report. 4.7 Establish Cloud Infrastructure 4.7.1 Cloud infrastructure setup report; configuration documents. 4.7.2 Security protocols document; access control list. 4.8 Conduct a Soft Launch 4.8.1 Soft launch event plan; test results; feedback forms. 4.8.2 Feedback summary; adjustment action plan. 4.9 Organize an Official Launch Event 4.9.1 Launch event plan; attendee list; event agenda. 4.9.2 Demonstration scripts; promotional materials; event feedback report. | Indicators of progress: What are the indicators to measure whether and to what extent the project achieves the envisaged results and effects? 1.1.1 Odrađeno 5 intervjua, organizovano 5 fokus grupa i 1 analiza potreba je izvršena 1.2.1 Definisani zahtevi, 1 kriterijum evaluacije, 1 tehnička analiza I 6 pilot projekata 1.3.1 1 analiza kroz 5 intervjua 1.3.2 Odrađeno 5 intervjua I 1 analiza dobijenih podataka 1.3.3 1 izveštaj o efikasnosti postojećih stažiranja sa kompanijama, 1 izveštaj o broju I tipu stažiranja dostupno studentima I 1 analiza trenutnog procesa povezivanja studenata 1.3.4 1 zapis o trenutnim partnerstvima, 1 izveštaj o dostupnosti stažiranja i 1 zapis preporuka za poboljšanje veza između studenata I stažiranja 1.3.1 1 analiza kroz 5 intervjua 1.3.2 Sprovedeno 600 intervjua sa studentima, 20 kompanija 1.3.3 5 intervjua sa univerzitetima i 20 sa kompanijama 1.3.4 1 analiza sveobuhvatnog stanja 1.4.1 20 sastanaka sa stručnjacima iz privrede 1.4.2 20 intervjua o potrebama privrede 1.4.3 20 istraživanja trenutnih tipova stažiranja sa 20 intervjua sa kompanijama 1.5.1 Razvoj I odobrenje razvojnog okvira 1.5.2 6 izveštaja, publikacije, studija slučajeva, 60 transkripta sa intervjua I anketa 1.5.3 6 virtuelnih poseta I sesija observacije 1.5.4 3 najboljih praksi I inovativnih pristupa identifikovano u analizi 1.5.5 Završetak I podnošenje sveobuhvatnoh izveštaja 2.1.1 Završetak razvoja MVP-a. 2.1.1 10 funkcionalnosti uključenih u MVP. 2.1.1 Kvalitet i stabilnost MVP-a tokom inicijalnog testiranja. 2.1.2 40 korisnika uključenih u testiranje. 2.1.2 Identifikovani problemi i predlozi za poboljšanje. 2.1.2 85% korisnika koji su zadovoljni MVP-om. 2.2.1 Završetak razvoja kompletnog sistema. 2.2.1 25 funkcionalnosti implementiranih u sistem. 2.2.2 5 uspešnih integracija sa postojećim sistemima. 2.2.2 10 problema tokom integracije i način njihovog rešavanja. 2.3.1 10 sprovedenih testova (sigurnost, performanse, UAT). 2.3.1 8 identifikovanih problema tokom testiranja. 2.3.2 8 rešenih problema. 2.3.2 15 dana potrebno za rešavanje problema. 2.4.1 3 uspešnih pilot instalacija. 2.4.1 Povratne informacije od korisnika tokom pilot faze. 2.4.2 5 institucija u kojima je sistem implementiran. 2.4.2 2 meseca potrebno za implementaciju u svim institutima. 2.5.1 Redovnost i učestalost evaluacije performansi sistema. 2.5.1 5 programskih problema identifikovo. 2.5.2 1 sprovedeno ažuriranje i poboljšanje. 2.5.2 Kvalitet povratnih informacija i zadovoljstvo korisnika. 2.6.1 4 sprovedenih provera usklađenosti i revizija. 2.6.1 2 identifikovana problema sa usklađenošću i sigurnošću. 2.6.2 1 ažuriranja sigurnosnih protokola. 2.6.2 Poboljšanje nivoa usklađenosti i sigurnosti. 2.7.1 15 planiranih i sprovedenih aktivnosti održavanja. 2.7.1 Učestalost ažuriranja sistema na svake 2 godine. 2.7.2 15 implementiranih skalabilnih karakteristika. 2.7.2 Povećanje kapaciteta sistema i njegovo zadovoljavanje buduće potražnje. 3.1.1.1 Potvrda poseta 3.1.1.2 6 logističkih aranžmana završeno 3.1.1.3 Upotpunjeni i relevantnost materijala 3.1.1.4 Kvalitet I jasnoća materijala 3.1.1.5 Pridržavanje agende posete tokom posete 3.1.1.6 Tačnost I sveobuhvatnost informacija 3.1.1.7 Korisnost I angažman materijala 3.1.1.8 6 poseta, povratne informacije od strane posetilaca 3.1.1.9 12 prezentacija, zadovoljstvo učesnika 3.1.1.10 Uključenje i povratne informacije učesnika 3.1.1.11 6 događaja za umrežavanje, interakcija učesnika 3.1.1.12 6 prikazanih praksi, dobijen uvid 3.1.1.13 6 radionica, identifikovane najbolje prakse 3.1.1.14 6 virtuelnih poseta, dobijen uvid 3.1.2 3.2.1 6 learning outcomes identified; alignment of outcomes with course objectives. 3.2.2 Scope approval by stakeholders; completeness of scope details. 3.2.3 Relevance of the scenario to the field of study; complexity level of challenges included. 3.2.4 6 storylines with 10 business elements included; feedback on storyline realism. 3.2.5 180 participants recruited; diversity of roles filled. 3.2.6 Completeness and clarity of documents; participant feedback on usability. 3.2.7 Relevance of materials; feedback on usefulness. 3.2.8 Functionality and usability of tools; 3 issues reported during testing. 3.2.9 Completeness of materials; participant feedback on adequacy. 3.2.10 Reach and engagement rates of promotional efforts; 60 registered participants. 3.2.11 60 registered participants; completeness of information provided. 3.2.12 Attendance rates; participant feedback on preparedness. 3.2.13 Completeness of preparation; participant feedback on readiness. 3.2.14 Availability and functionality of equipment and space; 2 issues encountered. 3.2.15 2 issues identified and resolved; system readiness. 3.2.16 Student understanding of scenario and rules; feedback on clarity. 3.2.17 Student engagement levels; facilitator feedback on progress. 3.2.18 Student engagement metrics; 6 of adjustments made. 3.2.19 Student reflection quality; learning outcomes achieved. 3.3.1 Functionality of AV equipment; readiness of the venue. 3.3.2 1 set of materials distributed; attendee feedback on materials. 3.3.3 Audience engagement during introductions; feedback on session start 3.3.4 Relevance of discussion content; adherence to agenda. 3.3.5 10 audience questions; level of audience interaction. 3.4.1 Functionality of AV equipment; readiness of the venue. 3.4.2 1 set of materials distributed; attendee feedback on materials. 3.4.3 Audience engagement during introductions; feedback on session start 3.4.4 Relevance of discussion content; adherence to agenda. 3.4.5 10 audience questions; level of audience interaction. 4.1.1 18 stakeholders recruited; diversity of roles represented; stakeholder engagement levels. 4.1.2 Clarity of assigned roles; committee meeting attendance and participation rates. 4.2.1 36 respondents; key features and capabilities identified; satisfaction with the consultation process. 4.2.2 6 facilities assessed; identified gaps and needs; accuracy and thoroughness of the assessment. 4.3.1 Completeness of the plan; stakeholder approval of the plan; alignment with project objectives. 4.3.2 6 specifications detailed; stakeholder feedback on the specifications; alignment with needs assessment findings. 4.4.1 5 vendors evaluated; compliance with selection criteria; approval of selected vendors. 4.4.2 Timeliness of procurement; compliance with specifications; 6 sets of items acquired. 4.5.1 Suitability of location; approval from relevant authorities; readiness of the space. 4.5.2 Completion of renovations on schedule; functionality of infrastructure; feedback on space setup. 4.6.1 12 devices installed; functionality testing results; installation completion timeline. 4.6.2 5 software applications installed; configuration accuracy; feedback from initial users. 4.7.1 6 cloud resources configured; functionality tests; security and compliance checks. 4.7.2 18 security measures implemented; compliance with security standards; incident reports. 4.8.1 120 attendees; functionality testing results; feedback on facilities and processes. 4.8.2 25 feedback responses; issues identified and resolved; readiness for official launch. 4.9.1 120 attendees; stakeholder representation; media coverage. 4.9.2 6 demonstrations conducted; audience engagement levels; feedback on showcased technologies. Metrics for for project M20 ∙ Dissemination and Exploitation plan defined by M6 ∙ Project visual identity designed by M2 ∙Web-site launched by M3 ∙ 10 good practices ∙ 10 Info days (300 part.) ∙ Final report on 3rd mission activities ∙ Final conference proceedings ∙Manual for Contractual and Financial Management by M2 ∙ 1 kick off and 6 SC meetings ∙ 51 Partners' Reports ∙ 2 report to EACEA | How indicators will be measured: What are the sources of information on these indicators? 1.1.1 Zapisnici i transkripti intervjua 1.1.1 Zapisnici I transkripti fokus grupa 1.1.1 Povratne informacije učesnika. 1.1.1 Dokumentacija o analizi podataka. 1.2.1 Evaluacioni izveštaji. 1.2.1 Tehnička dokumentacija blockchain tehnologija. 1.2.1 Izveštaji tehničkih i finansijskih stručnjaka 1.2.2 Tehnička dokumentacija. 1.2.2 Povratne informacije zainteresovanih strana. 1.2.2 Revizije i iteracije dizajna. 1.3.1 Zapisnici i transkripti intervjua 1.3.2 Zapisnici i transkripti intervjua 1.3.3 Zapisnici i transkripti intervjua 1.3.4 Postojeći odgovori o stažiranju 1.4.1 Zapisnici sa sastanaka 1.4.2 Zapisnici I transkripti intrevjua 1.4.3 Postojeći ugovori o stažiranju 1.5.1 Prihvaćen okvirni dokument 1.5.2 Sažetak I kompilacija skupljenih izveštaja I publikacija 1.5.3 Transkripti, snimci I rezultati anketa od partnera 1.5.4 Snimci I transkripti iz virtuelnih poseta I observacija 1.5.5 Završeni izveštaj I pronalasci I preporuke, podeljene sa partnerima 2.1.1 Razvojna dokumentacija. 2.1.1 Tehnički izveštaji i zapisi o testiranju. 2.1.1 Povratne informacije od timova za razvoj i testiranje. 2.1.2 Testni scenariji i zapisi. 2.1.2 Anketni rezultati i povratne informacije korisnika. 2.1.2 Dokumentacija o iteracijama i poboljšanjima na osnovu testiranja. 2.2.1 Razvojna dokumentacija. 2.2.1 Izveštaji razvojnih timova. 2.2.2 Dokumentacija o integraciji. 2.2.2 Tehnički zapisi o interfejsima i protokolima. 2.3.1 Testni izveštaji. 2.3.1 Zapisi o sigurnosnim, performansnim i UAT testovima. 2.3.2 Dokumentacija o problemima i njihovom rešavanju. 2.3.2 Povratne informacije timova za testiranje. 2.4.1 Izveštaji o pilot raspoređivanju. 2.4.1 Povratne informacije korisnika tokom pilot faze. 2.4.2 Dokumentacija o implementaciji. 2.4.2 Izveštaji timova za uvođenje. 2.5.1 Izveštaji o performansama sistema. 2.5.1 Analitički alati i softver za praćenje. 2.5.2 Dokumentacija o ažuriranjima. 2.5.2 Povratne informacije korisnika i ankete. 2.6.1 Izveštaji o usklađenosti i sigurnosne revizije. 2.6.1 Dokumentacija o identifikovanim problemima. 2.6.2 Ažurirana dokumentacija o sigurnosnim protokolima. 2.6.2 Konsultacije sa stručnjacima za usklađenost i sigurnost. 2.7.1 Dokumentacija o rasporedu održavanja. 2.7.1 Izveštaji o sprovedenim održavanjima i ažuriranjima. 2.7.2 Planovi za skalabilnost. 2.7.2 Izveštaji o implementaciji skalabilnih rešenja. QC and monitoring manual ∙Metrics for project ∙ External monitoring reports ∙ Dissemination and exploitation plan ∙ Project promotional materials ∙ Project web site ∙ Review of policies for promoting third mission ∙ Good practices ∙ Final report on implementation of third mission ∙ Final Conference proceedings ∙Manual for contractual and financial management ∙ Steering Committee meetings’ minutes ∙ Partners’ reports ∙ Interim and Final reports to EACEA 3.1.1.1 Visit itinerary Confirmed itinerary document; correspondence with host institutions. 3.1.1.2 Travel and accommodation arrangements Travel booking confirmations; accommodation receipts. 3.1.1.3 Preparation of materials for visits Copies of prepared materials; distribution logs. 3.1.1.4 Information brochures and guides Printed brochures and guides; distribution records. 3.1.1.5 Detailed visit agenda Finalized visit agenda; meeting minutes from planning sessions. 3.1.1.6 Background Information Document Background information document; review logs. 3.1.1.7 Educational presentations Copies of presentation slides; feedback forms from attendees. 3.1.1.8 Schedule and visit guide Approved visit schedule; guidebook copies. 3.1.1.9 Presentation material and speaker schedules Presentation slides; speaker schedules; attendance records. 3.1.1.10 Interactive Session Plan Session plans; participant feedback forms. 3.1.1.11 Networking Event Schedule Networking event agenda; attendee lists. 3.1.1.12 Meeting notes and observation reports Meeting notes; observation reports; summary documents. 3.1.1.13 Summaries from conferences and workshops Conference and workshop summaries; attendance certificates. 3.1.1.14 Summaries of virtual visits and demonstrations Virtual visit summaries; demonstration reports; screen recordings. 3.1.2 Study Visits to Panel Discussions 3.1.2.1 Visit itinerary Confirmed itinerary document; correspondence with host institutions. 3.1.2.2 Travel and accommodation arrangements Travel booking confirmations; accommodation receipts. 3.1.2.3 Preparation of materials for visits Copies of prepared materials; distribution logs. 3.1.2.4 Information brochures and guides Printed brochures and guides; distribution records. 3.1.2.5 Detailed visit agenda Finalized visit agenda; meeting minutes from planning sessions. 3.1.2.6 Background Information Document Background information document; review logs. 3.1.2.7 Educational presentations Copies of presentation slides; feedback forms from attendees. 3.1.2.8 Visit schedule and guide Approved visit schedule; guidebook copies. 3.1.2.9 Presentation material and speaker schedules Presentation slides; speaker schedules; attendance records. 3.1.2.10 Interactive Session Plan Session plans; participant feedback forms. 3.1.2.11 Networking Event Schedule Networking event agenda; attendee lists. 3.1.2.12 Meeting notes and observation reports Meeting notes; observation reports; summary documents. 3.1.2.13 Summaries from conferences and workshops Conference and workshop summaries; attendance certificates. 3.1.2.14 Summaries of Virtual Visits and Demonstrations Virtual visit summaries; demonstration reports; screen recordings 3.2 Organization of Business Simulations 3.2.1 Document outlining specific learning outcomes for the simulation. Learning outcomes document; approval signatures from academic staff. 3.2.2 Simulation scope document detailing duration, components, and participation levels Simulation scope document; stakeholder meeting minutes. 3.2.3 Detailed business scenario document. Scenario document; feedback from academic and industry reviewers. 3.2.4 Comprehensive storyline with integrated business elements. Storyline document; participant feedback surveys. 3.2.5 List of recruited facilitators, mentors, and support staff. Recruitment records; signed agreements; training logs. 3.2.6 Scripts, role descriptions, and instruction manuals for participants. Copies of scripts and manuals; distribution records. 3.2.7 Compilation of background materials and documents. Background materials packet; participant feedback forms. 3.2.8 Developed digital tools or platforms. Tool/software development reports; testing logs; user manuals. 3.2.9 Set of printed and physical materials. Physical copies of materials; inventory logs. 3.2.10 Promotion plan and materials. Promotion plan document; copies of promotional materials; outreach metrics. 3.2.11 Registration system and informational materials. Registration system logs; informational materials packet. 3.2.12 Orientation session agenda and materials. Orientation session agenda; attendance sheets; feedback forms. 3.2.13 Preparatory materials and task assignments. Copies of preparatory materials; task assignment logs. 3.2.14 Setup and readiness checklist. Completed checklists; setup photos. 3.2.15 Technical system test reports. System test logs; issue resolution records. 3.2.16 Introductory session materials. Copies of introductory session slides and handouts. 3.2.17 Facilitator's guide and session logs. Facilitator's guide; session logs and feedback forms. 3.2.18 Monitoring logs and adjustment records. Monitoring logs; adjustment notes; participant feedback. 3.2.19 Debriefing session summary and feedback reports. Debriefing session notes; feedback summary reports. 3.3 Panel Discussions of AI and Machine Learning 3.3.1 Venue setup checklist and test report. Completed venue setup checklist; AV equipment test report. 3.3.2 Promotional materials and distribution records. Copies of promotional materials; distribution logs. 3.3.3 Welcome script and introduction plan. Copies of the welcome script; event program. 3.3.4 Panel discussion guide and facilitation notes. Panel discussion guide; facilitator notes; session recordings. 3.3.5 Q&A session plan and summary of audience questions. Q&A session plan; summary of audience questions; session transcripts. 3.4 Panel Discussion of Blockchain Technology and Application in Business 3.4.1 Venue setup checklist and test report. Completed venue setup checklist; AV equipment test report. 3.4.2 Promotional materials and distribution records. Copies of promotional materials; distribution logs. 3.4.3 Welcome script and introduction plan. Copies of the welcome script; event program. 3.4.4 Panel discussion guide and facilitation notes. Panel discussion guide; facilitator notes; session recordings. | Assumptions & risks: What external factors and conditions must be realised to obtain the expected outcomes and results on schedule? 4.1.1 Difficulty in recruiting a diverse group of stakeholders. Low engagement or commitment from recruited members. Conflicting interests among stakeholders, leading to delays. 4.1.2 Misalignment of roles and responsibilities leading to confusion. Overlapping duties causing inefficiencies. Resistance to assigned roles from committee members. 4.2.1 Limited participation or response from key groups. Biased or incomplete feedback affecting the accuracy of needs assessment. Misinterpretation of stakeholder input leading to incorrect requirements. 4.2.2 Inaccurate assessment due to outdated or incomplete data. Overlooking critical facility or equipment deficiencies. Underestimating the cost or time required to upgrade facilities. 4.3.1 Inaccurate estimation of costs and timelines. Scope creep due to unclear or evolving objectives. Inadequate resource allocation impacting project execution. 4.3.2 Misalignment between specifications and actual needs. Rapid technological changes rendering specifications outdated. Difficulty in sourcing equipment that meets specified requirements. 4.4.1 Selection of unreliable or unqualified vendors. Vendor delays affecting project timelines. Budget overruns due to unexpected costs or price changes. 4.4.2 Equipment or software not meeting quality standards or specifications. Delivery delays impacting project schedule. Issues with software licensing or compliance. 4.5.1 Difficulty in securing a suitable location. Space not meeting the needs of the planned setup. Delays in obtaining necessary approvals for space use. 4.5.2 Construction or renovation delays. Unforeseen costs related to infrastructure upgrades. Safety or compliance issues during renovation. 4.6.1 Installation delays due to technical issues. Incompatibility between new and existing hardware. Damage to equipment during installation. 4.6.2 Software configuration errors leading to operational issues. Cybersecurity vulnerabilities introduced during setup. Inadequate staff training on new software. 4.7.1 Misconfigurations leading to security breaches or performance issues. Over-provisioning or under-provisioning cloud resources. Unforeseen costs associated with cloud services. 4.7.2 Inadequate security measures leading to data breaches. Complex access controls causing usability issues. Compliance failures with data protection regulations. 4.8.1 Equipment or systems not functioning as expected during the soft launch. Low participation from initial users affecting feedback quality. Insufficient time to address issues before the official launch. 4.8.2 Delayed feedback from users hindering timely adjustments. Identified issues requiring major changes impacting the timeline. Resistance to changes from stakeholders. 4.9.1 Logistical challenges affecting the quality of the event. Low attendance or engagement from key stakeholders. Negative feedback or technical issues during the event. 4.9.2 Technical issues during demonstrations. Failure to effectively communicate the benefits, leading to low interest. Misalignment of expectations among different stakeholder groups. |
| Activities: What are the key activities to be carried out (grouped in Workpackages) and in what sequence in order to produce the expected results? 1. Analiza trenutnog stanja, potreba i dobrih praksi 1.1 Procena potreba i studija izvodljivosti e-menadžment Sistema 1.1.1 Sprovođenje intervjua, formiranje fokus grupa I analiza podataka sa zainteresovanim stranama 1.1.2 Odrađena je tehnološka i finansijska studija izvodljivosti 1.2 Dizajn i arhitektura rešenja 1.2.1 Definicija zahteva, kriterijuma evaluacije, tehnička analiza predloženih tehnologija i pilot projekti 1.2.2 Priprema izveštaja o evaluaciji I izveštaja o odabiru tehnologije 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima 1.3.1 Sprovođenje intervjua o broju i vrstama praksi koje se trenutno nude. 1.3.2 Sprovođenje intervjua i analiza dobijenih podataka 1.3.3 Intervjui o efikasnosti postojećih partnerstva sa kompanijama, broju i tipu stažiranja dostupnih studentima i analiza trenutnog procesa povezivanja studenata sa mogućim stažiranjima. 1.3.4 Uvezivanje svih rezultata u jedan zajednički izveštaj 1.4 Analiza potreba privrede 1.4.1 Sprovođenje intervjua I virtuelnih sastanaka sa mogućim partnerima u industriji 1.4.2 Formiranje izveštaja o mogućnostima novih partnera 1.4.3 Sastanci i intervjui sa malim i srednjim preduzećima 1.5 Primeri dobre prakse u implementaciji laboratorija I centara 1.5.1 Formiranje okvira za analizu dobrih praksi, ukljućuljući kriterijume i metrike 1.5.2 Prikupljanje postojećih izveštaja, publikacija I slučajeva korišćenja o laboratorijama i centrima iz ovih univerziteta 1.5.3 Sprovođenje intervjua I anketa sa fakultetima, administratorima I menadžerima laboratorija u izabranim EU univerzitetima 1.5.4 Organizovanje virtuelnih poseta I sesija observacije za razumevanje operacije laboratorija I centara 1.5.5 Analiza skupljenih podataka radi identifikacije najboljih praksi, inovativnih pristupa I uspešnih strategija 1.5.6 Spremljen sveobuhvatni izveštaj koji sažeto opisuje pronalaske I daje preporuke za implementiranje sličnih praksi u srpskim univerzitetima. 2. Razvoj modernih IT tehnologija na srpskim univerzitetima 2.1 Razvoj prototipa 2.1.1 Razvijanje minimalno održivog proizvoda (MVP). 2.1.2 Provođenje početnog testiranja korisnika i prikupljanje povratne informacije. 2.2 Strategija implementacije 2.2.1 Razvijanje kompletnog sistema. 2.2.2 Integracija sa postojećim univerzitetskim sistemima. 2.3 Ispitivanje i osiguranje kvaliteta 2.3.1 Izvršavanje sveobuhvatnog testiranja (sigurnost, performanse, UAT). 2.3.2 Rešavanje i ispravka identifikovanih problema. 2.4 Implementacija i uvođenje 2.4.1 Instalacija pilot sistema. 2.4.2 Instalacija sistema u svim relevantnim institucijama. 2.5 Evaluacija i kontinuirano poboljšanje 2.5.1 Praćenje i procena performanse sistema. 2.5.2 Implementacija poboljšanja na osnovu povratnih informacija. 2.6 Usklađenost i sigurnost 2.6.1 Provera usklađenosti i sigurnosne revizije. 2.6.2 Ažuriranje sigurnosnih protokola i dokumentacije o usklađenosti po potrebi. 2.7 Održivost i skalabilnost 2.7.1 Definisanje rasporeda održavanja i ažuriranja. 2.7.2 Priprema budućih iteracija proizvoda 3. Osavremenjivanje stručnih praksi 3.1 Studijske posete 3.1.1 Posete univerzitetima i institucijama radi provere njihovih praksi u poslovnoj simulaciji 3.1.1.1 Zakazivanje posete 3.1.1.2 Organizovanje logistike 3.1.1.3 Razvoj potrebnog materijala 3.1.1.4 Kreiranje informacionog materijala 3.1.1.5 Razvoj agende za posetu, uključujući detaljni raspored aktivnosti 3.1.1.6 Priprema pozadinske informacije o domaćoj organizaciji, ukljućujući njenu misiju i ključne ličnosti 3.1.1.7 Priprema obrazovnog materijala 3.1.1.8 Sprovođenje obilaska objekta, istaćući klučne oblasti interesa i operacija 3.1.1.9 Priprema prezentacija od strane ključnih ličnosti, fokusirajući se na teme relevantne za studentske studije i interese vezane za karijeru 3.1.1.10 Organizacija interaktivnih aktivnosti, kao što su Q&A sesije, demonstracije ili praktične radionice, radi angažovanja studenata i poboljšanja razumevanja 3.1.1.11 Prprema za neformalne sesije 3.1.1.12 Posete univerziteta i institucija radi observacije njihovih praksi u diskusijama za Poslovnu Informatiku 3.1.1.13 Učestvovanje u radionicama i konferencijama koje se fokusiraju na najbolje prakse u visokom obrazovanju i poslovnoj informatici 3.1.1.14 Sprovođenje virtuelnih poseta i prisustvo onlajn demonstracijama naprednih e-menadžment sistema i IT infrastrukture 3.2 Organizacija bisnis simulacija 3.2.1 Identify the specific learning outcomes 3.2.2. Determine the scope of the simulation 3.2.3 Develop a detailed business scenario 3.2.4 Create a storyline 3.2.5 Recruit facilitators and mentors 3.2.6 Develop the scripts 3.2.7 Create background materials 3.2.8 Design and create any digital platforms 3.2.9 Prepare physical materials 3.2.10 Promote the simulation event 3.2.11 Set up a registration process 3.2.12 Organize orientation sessions 3.2.13 Distribute preparatory materials 3.2.14 Arrange the physical and virtual space 3.2.15 Test all technical systems and tools 3.2.16 Conduct an introductory session 3.2.17 Facilitate the simulation 3.2.18 Monitor student interactions and progress 3.2.19 Conduct debriefing sessions 3.3 Panel Diskusije AI i Machine learning 3.3.1 Set up the venue 3.3.2 Develop promotional materials 3.3.3 Welcome attendees and introduce the panelists and moderator. 3.3.4 Facilitate the panel discussion, ensuring it stays on track and covers the key themes. 3.3.5 Allow time for audience questions and interaction with the panelists. 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju 3.4.1 Set up the venue 3.4.2 Develop promotional materials 3.4.3 Welcome attendees and introduce the panelists and moderator. 3.4.4 Facilitate the panel discussion, ensuring it stays on track and covers the key themes. 3.4.5 Allow time for audience questions and interaction with the panelists. 4. Formiranje laboratorije za digitalnu transformaciju 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps 4.1.1 Identify and recruit key stakeholders 4.1.2 Assign roles and responsibilities within the committee 4.2 Conduct a Needs Assessment 4.2.1 Gather input from faculty, students, and industry partners on the desired features of the laboratory and center. 4.2.2 Assess the current state of facilities, equipment, and resources available at the university. 4.3 Develop a Detailed Plan 4.3.1 Create a comprehensive plan outlining the objectives, scope, timeline, budget, and resources required for the establishment of the laboratory and center. 4.3.2 Ensure the plan includes detailed specifications 4.4 Procure Equipment and Software 4.4.1 Identify and select vendors 4.4.2 Purchase and acquire the necessary equipment and software licenses 4.5 Prepare the Physical Space 4.5.1 Identify and secure a suitable location on campus 4.5.2 Renovate and set up the physical space 4.6 Install Equipment and Software 4.6.1 Set up servers, workstations, networking devices, and other hardware 4.6.2 Install and configure necessary software, including cloud platforms, DevOps tools, and other relevant applications. 4.7 Establish Cloud Infrastructure 4.7.1 Set up cloud accounts and configure cloud resources 4.7.2 Implement security measures and access controls to protect the cloud infrastructure. 4.8 Conduct a Soft Launch 4.8.1 Organize a soft launch event to test the laboratory and center's facilities 4.8.2 Gather feedback from initial users and make any necessary adjustments before the official launch. 4.9 Organize an Official Launch Event 4.9.1 Plan and host an official launch event 4.9.2 Showcase the facilities, demonstrate key technologies, and highlight the benefits for students, faculty, and industry partners. 3. Osavremenjivanje stručnih praksi Act5.1 Developing QCM manual ∙ Act6.2 Defining third mission metrics ∙ Act6.3 Internal monitoring ∙ Act6.4 Monitoring of defined metrics ∙ Act7.1 Elaboration of Diss. and Exploitation Plan ∙ Act7.2 Design of project visual identity ∙ Act7.3 Design/upgrade of web-site ∙ Act7.4 Defining institutional policies to promote third mission ∙ Act7.5 Good practices on Tech. transfer and Innovation Act7.6 10 Info days and other events ∙ Act7.7 Final Conference on university third mission ∙ Act8.1 Elaboration of Manual for contractual and financial mngt. ∙ Act8.2 Overall project mngt ∙ Act8.3 Local management ∙ Act8.4 SC meetings | ### Inputs: What inputs are required to implement these activities, e.g. staff time, equipment, mobilities, publications etc.? - Staff costs: - Travel costs: - Costs of stay: - Equipment: - Subcontracting: - Co-financing: |  | Assumptions, risks and pre-conditions: What pre-conditions are required before the project starts? What conditions outside the project’s direct control have to be present for the implementation of the planned activities? |