|  |  |  | Application Form Selection: 2020 KA2 – Cooperation for innovation and the exchange of good practices – Capacity Building in the field of Higher Education |
| --- | --- | --- | --- |

Call for Proposals 2020 - EAC/A02/2019

Title of the Project / Acronym

DETAILEDDESCRIPTION OF THE PROJECT

JOINT PROJECTS

(To be attached to the e-Form)

Please note that, in accordance with Article 193 of the “Financial Regulation Applicable to the General Budget of the Union”, grants cannot be awarded retroactively. This means that activities covered by the grant can only be implemented as from the date on which the last party has signed the grant agreement.

As it might not in all cases be possible to sign the grant agreement for a selected proposal before the start date indicated in the application, the project planning should ideally cater for this possibility.

If your work plan does not allow for the necessary flexibility to adapt to such an event and/or if you have scheduled activities that must start on a particular date in the very early phase of the proposed action, you should provide a justification. The justification should explain the reasons why the activities in question cannot be postponed if the contract is not signed by 15 November 2020 or 15 January 2021) and need to take place on the foreseen date.

If this is the case for your project, you should specify below the following (max 3000 characters):

- the date on which the consortium would need to start its project activities covered by the grant. Only from this date on costs covered by the EU grant can be incurred;

- a detailed justification.The justification should explain why the activities foreseen (and their corresponding costs) cannot be delayed and why such a delay would jeopardise the project’s implementation.

The project activities are carefully designed to address the key objectives of modernizing and enhancing the educational, technological, and administrative capacities of Serbian universities. Each activity contributes to achieving the overall goals of the project by focusing on critical areas such as needs assessment, technological development, curriculum enhancement, practical student experiences, and sustainability. 1. Analysis of current state, needs, and best practices: The first set of activities focuses on understanding the existing conditions at universities, conducting feasibility studies, and benchmarking best practices in other institutions. These are essential steps to ensure that the project builds on a clear understanding of the current landscape and the specific needs of each university. This phase also ensures that the proposed solutions are viable and based on successful models from leading institutions. 2. Development of modern IT technologies: The development of modern IT technologies is a core component of the project, aimed at transforming the digital infrastructure of Serbian universities. Prototyping and testing are critical for ensuring that the chosen solutions meet the needs of the institutions and can be integrated seamlessly with existing systems. By focusing on security, scalability, and performance, these activities ensure that the technologies implemented will be sustainable and support future growth. 3. Modernization of internships and practical experience: The focus on improving student internships and practical experiences is essential for aligning academic programs with industry needs. Study visits, business simulations, and panel discussions with industry leaders will help students gain hands-on experience and better prepare them for the job market. These activities also foster partnerships with industry, which is crucial for long-term collaboration and the continuous improvement of curricula. 4. Establishment of digital transformation laboratories: Creating laboratories for AI, machine learning, digital transformation, and DevOps is key to providing students and faculty with access to cutting-edge technology. These labs will serve as innovation hubs, allowing students to engage in research, experimentation, and real-world problem-solving. The activities involved in setting up these labs, from needs assessment to equipment procurement, ensure that the facilities meet the specific requirements of the institutions and are designed for long-term use. 5. Development of QCM manual: Developing a Quality Control and Monitoring (QCM) manual is critical for establishing standardized metrics and ensuring that the third mission of universities — community engagement and societal impact — is properly monitored and evaluated. This ensures that the project’s objectives are being met and that the universities are held accountable for their societal contributions. 6. Dissemination and exploitation plan: The dissemination and exploitation plan is vital for ensuring that the results and impacts of the project are communicated effectively to all stakeholders. By designing a visual identity, upgrading the website, and organizing events such as info days and a final conference, the project will reach a wide audience and promo

# PART D – Relevance of the Project

# D.1 Why does the consortium undertake this project?

- Which problem(s) will the project address in theparticipating Partner Countries? Why are these problems pressing?

- Please explain the result of the need analysis carried out for each Partner Country and for each Partner institution and provide qualitative and quantitative evidence for your results.Please refer also to studies carried out and feasibility analyses undertaken. In particular explain for each institution,why the support from the CBHEactionis required.(limit 10.000 characters)

The consortium members undertake this project for several key reasons, all aligned with their institutional missions and long-term strategic goals. This project is a response to pressing needs in the higher education sector, particularly regarding the modernization of teaching, learning, and research practices, as well as the implementation of cutting-edge technologies. Below is a detailed explanation of the motivations and rationale behind the consortium's commitment to this project: 1. Alignment with Institutional and National Priorities The consortium consists of leading universities and organizations from both Serbia and the EU, each of which has a vested interest in advancing their educational, research, and social missions. For Serbian universities, this project provides an opportunity to enhance their technological capabilities, modernize curricula, and align with international standards. These universities are looking to bridge gaps in digital transformation, student engagement, and research infrastructure. In particular, institutions such as the University of Belgrade, University of Niš, and University of Novi Sad recognize that this project aligns with Serbia's national strategy for higher education modernization, which emphasizes innovation, collaboration with industry, and internationalization. For EU partners, such as the Technical University of Berlin, IT University of Copenhagen, and AVT Business School, this project offers the opportunity to extend their expertise and best practices in education technology and innovation to institutions in Serbia. These EU universities have already developed strong competencies in areas such as AI, machine learning, digital transformation, and DevOps, and are committed to sharing their knowledge with emerging universities. Through this collaboration, EU partners can further strengthen their research networks, promote cross-border collaboration, and contribute to the growth of higher education in the European region. 2. Need for Technological Advancement and Digital Transformation The consortium members recognize that higher education institutions globally are undergoing rapid changes due to technological advancements, especially in areas such as digital learning platforms, AI-driven research, and blockchain technology for e-management systems. For Serbian universities, the current IT infrastructure is not sufficient to support cutting-edge research and innovative student practices. This project, therefore, focuses on the development and implementation of state-of-the-art IT systems, including cloud-based learning environments and AI-driven laboratories. For the Serbian universities, participation in this project means upgrading their technological infrastructure to support advanced research in fields like AI, machine learning, and DevOps. The introduction of blockchain technologies for e-management and administrative systems will also enable greater transparency and efficiency in university operations. This aligns with the global trend toward digital transformation in higher education and prepares Serbian universities to compete on an international level. 3. Curriculum Modernization and Internationalization One of the main goals of the project is the modernization of curricula in Software Engineering and Business Informatics. Serbian universities face the challenge of outdated curricula that do not fully reflect the current demands of the global job market, particularly in high-demand fields such as AI, data science, and digital transformation. By working with EU partners, Serbian institutions will benefit from expertise in curriculum development that incorporates the latest technological advancements and industry needs. This collaboration ensures that Serbian universities not only modernize their curricula but also align them with international standards. This is crucial for fostering student mobility, international collaboration, and the ability of graduates to compete in the global marketplace. The EU partners bring extensive experience in developing dynamic, interdisciplinary curricula that are adaptable to rapidly changing technologies and market demands. 4. Enhancing Student Learning and Employability A core motivation for the consortium is the enhancement of student learning experiences and employability outcomes. By developing advanced laboratories in AI, machine learning, and cloud computing, Serbian universities will offer students hands-on experience with state-of-the-art technologies. These laboratories will serve as innovation hubs where students can engage in real-world problem solving, collaborate on interdisciplinary projects, and gain skills that are highly sought after by employers. For EU partners, this focus on student engagement aligns with their commitment to innovative teaching practices and enhancing the practical skills of graduates. The development of business simulations and internships integrated into the curriculum will also strengthen the employability of graduates, ensuring that they are prepared for the demands of modern industries, particularly in tech-driven fields. 5. Promoting Research and Innovation through Technology Transfer Another key motivation for the consortium is the promotion of research and innovation, particularly through the establishment of technology transfer centers and innovation hubs within the Serbian universities. These centers will foster collaboration between academia and industry, driving research that addresses real-world problems and promotes economic growth. For the EU partners, technology transfer is already a well-established part of their institutional missions, and this project allows them to extend their expertise in this area to Serbian universities. The development of these centers will not only enhance the research capacity of Serbian institutions but also strengthen the ties between universities and local industries, promoting innovation and entrepreneurship. 6. Strategic International Partnerships and Knowledge Sharing The project provides a unique platform for fostering strategic international partnerships and facilitating knowledge sharing between EU and Serbian universities. By participating in this consortium, all members will benefit from an exchange of best practices in educational technology, curriculum development, and research innovation. For Serbian universities, this collaboration offers a pathway to internationalization, enabling them to develop partnerships that extend beyond the EU and position them as key players in global higher education networks. EU partners, in turn, gain access to new research opportunities and cultural exchanges, expanding their academic influence in Southeast Europe. This partnership also reinforces the importance of cooperation between developed and developing institutions in achieving common educational and research goals, ultimately contributing to the European Higher Education Area (EHEA). 7. Addressing Societal Challenges through the Third Mission Universities globally are increasingly recognizing their "third mission" — the societal impact they have beyond teaching and research. This project aligns with that mission by promoting societal engagement through technology transfer, innovation centers, and partnerships with local businesses. Serbian universities, through this project, aim to address regional challenges such as brain drain, youth unemployment, and underutilization of technological resources. By collaborating with industry and engaging with the local community, universities can drive economic growth and foster a more technologically advanced society. For EU universities, the third mission has long been part of their strategic objectives, and this project provides an opportunity to share their experiences in integrating societal impact into the core activities of higher education institutions. This will encourage both EU and Serbian universities to take a more active role in addressing societal challenges through education and research. 8. Long-term Sustainability and Capacity Building The project also focuses on building long-term capacity within Serbian universities to ensure that the improvements made through the project are sustainable. This includes the establishment of management frameworks, the development of financial and contractual manuals, and the provision of training for staff and faculty. These measures will ensure that Serbian universities are equipped to maintain and further develop the project’s outcomes long after the consortium has ended. For EU partners, this capacity-building aspect aligns with their goals of promoting sustainable development and ensuring that the knowledge and expertise shared during the project lead to lasting improvements. The creation of sustainable systems within Serbian universities will also strengthen the partnership between EU and Serbian institutions, fostering future collaborations. Conclusion In summary, the consortium members undertake this project because it aligns with their institutional missions, addresses urgent needs for technological advancement, promotes curriculum modernization, enhances student learning, fosters research and innovation, and builds long-term capacity. For Serbian universities, this project is a transformative opportunity to modernize their infrastructure and align with international standards. For EU partners, it provides a platform to share their expertise, promote cross-border collaboration, and extend their impact on the global higher education landscape.

(Please add Partner Countries/partners as appropriate)

Please identify the target groups and their needs in each Partner Country and in each Partner Country institution.(limit 8.000 characters)

The project targets a diverse range of groups across partner institutions in Serbia, the EU, and Turkey. Each partner has specific beneficiaries, including students, faculty, administrative staff, and industry partners, all of whom will gain from the project’s initiatives. The main goal is to modernize curricula, improve practical skills, enhance research, and foster collaboration between universities and industries. 1. Serbia Partner Institution: Državni Univerzitet u Novom Pazaru Students (Undergraduate and Graduate): Students require practical training in modern technologies like AI, blockchain, and machine learning, along with internships to improve employability. Faculty: Faculty need training in advanced technologies, curriculum development, and collaboration with EU partners for research and teaching. Administrative Staff: Staff need tools like blockchain-based e-management systems to improve efficiency. Industry Partners (Local SMEs): Businesses require graduates with practical skills and seek university support for technology transfer and research collaboration. Partner Institution: Univerzitet u Nišu (Faculty of Electronic Engineering) Students: Students need access to modern labs and practical training in AI, DevOps, and cloud computing. Faculty and Researchers: Faculty require opportunities for collaboration with EU institutions to update curricula and advance research. Industry Partners (Tech Companies and Startups): Industry needs skilled graduates and joint R&D opportunities with the university. Partner Institution: Elektrotehnički Fakultet u Beogradu (University of Belgrade - Faculty of Electrical Engineering) Students: Students require hands-on experience with AI, machine learning, and blockchain to meet industry demands. Faculty: Faculty need to adopt new teaching methods and engage in international research collaborations. Industry Partners (Large Tech Firms): Tech firms need graduates skilled in digital technologies and stronger university-industry partnerships for internships and research projects. Partner Institution: Univerzitet u Kragujevcu (Faculty of Mechanical Engineering) Students: Engineering students need access to labs and internships focused on automation, AI, and digital transformation. Faculty and Researchers: Faculty need access to advanced technologies and collaboration with international partners to enhance teaching and research. Industry Partners (Manufacturing Firms): Industry needs graduates with expertise in digital transformation and collaboration for R&D initiatives. Partner Institution: Ekonomski Fakultet u Beogradu (University of Belgrade - Faculty of Economics) Students (Business and Economics): Students require exposure to blockchain, AI, and digital economy applications, along with better internship opportunities. Faculty: Faculty need training in digital business transformation and the integration of new technologies like AI and big data into courses. Industry Partners (Finance and Tech Sectors): Businesses need graduates with knowledge of fintech, blockchain, and digital finance, as well as stronger collaboration with the university for research and internship programs. 2. European Union Partner Institution: Technical University of Berlin (Germany) Students and Researchers: Students seek international collaboration on digital transformation and innovation. Faculty and Staff: Faculty need opportunities to share expertise in technology-driven education and curriculum modernization with Serbian universities. Partner Institution: IT University of Copenhagen (Denmark) Students and Faculty: Both groups are focused on collaboration with Serbian universities in IT and digital transformation projects. Industry Partners (Tech Firms): Danish tech firms seek collaborative research projects with Serbian institutions for innovation. Partner Institution: AVT Business School (Denmark) Students (Business and Innovation): Students need exposure to international business innovation practices through collaboration with Serbian institutions. Faculty: Faculty need collaboration on curriculum development and research in business technology with Serbian universities. 3. Turkey Partner Institution: Istanbul Technical University Students (Engineering and IT): Students require international collaboration to enhance their practical skills in AI, blockchain, and machine learning. Faculty: Faculty need collaborative research and teaching exchanges with Serbian and EU institutions to update their curricula and stay aligned with global trends. 4. Ireland Partner Institution: Dublin Business School (Ireland) Students (Business and IT): Students need global exposure and collaboration with Serbian universities on real-world business and IT projects. Faculty: Faculty seek opportunities to engage in international research and curriculum development in business informatics and software engineering. Summary of Common Needs Across All Partner Institutions • Students: Need modernized curricula, practical experience in emerging technologies, and international exposure to enhance their employability. • Faculty: Require professional development opportunities, collaboration for curriculum modernization, and research partnerships. • Administrative Staff: Need training in the use of new digital tools to streamline university operations. • Industry Partners: Need access to skilled graduates and R&D collaboration with universities to drive innovation and growth. This project addresses these needs by fostering international collaboration, modernizing curricula, improving practical training opportunities, and enhancing the digital infrastructure at partner institutions. These initiatives aim to bridge the gap between education and industry, ensuring that graduates are prepared for the demands of the global job market while supporting research and innovation across the consortium.

(Please add partner countries/partners as appropriate)

How will the project address the relevant thematic national/regional priorities (see https://eacea.ec.europa.eu/erasmus-plus/funding/capacity-building-higher-education-2019_en) set by the Programme for its target country (ies)/region(s)? (limit 8.000 characters)

This project aligns directly with the national and regional priorities set by the Erasmus+ Programme for higher education modernization, technological innovation, and capacity building in the Western Balkans, particularly Serbia. The initiatives within the project are designed to address these priorities through comprehensive actions in curriculum development, digital transformation, fostering university-industry collaboration, and promoting internationalization. Below is a detailed explanation of how the project addresses these relevant thematic priorities. 1. Digital Transformation in Higher Education National/Regional Priority: Serbia and the Western Balkans region prioritize the digital transformation of educational institutions to align with global technological advancements. The country’s education strategy includes goals for integrating modern IT infrastructure and enhancing the digital skills of students, faculty, and administrative staff. How the Project Addresses This Priority: The project includes extensive activities focused on implementing state-of-the-art digital technologies at Serbian universities, such as AI, blockchain, cloud computing, and DevOps. By establishing advanced laboratories for digital transformation, AI, and machine learning, the project ensures that students and faculty have access to cutting-edge tools and learning environments. Moreover, the project supports the development of e-management systems through blockchain, improving university administration efficiency. These technological upgrades align with Serbia’s national goals of digitalization, providing a robust framework for modernizing higher education in the region. 2. Curriculum Modernization and Alignment with Industry Needs National/Regional Priority: A key priority in the Western Balkans is the modernization of university curricula to align with the needs of modern industries, particularly in high-demand fields such as software engineering, business informatics, and digital technologies. The region emphasizes the integration of practical skills and industry-driven learning into higher education programs. How the Project Addresses This Priority: The project specifically focuses on updating and improving curricula in Software Engineering and Business Informatics. By collaborating with leading EU institutions such as the Technical University of Berlin and IT University of Copenhagen, the project will integrate best practices from the EU to revamp the educational programs. It includes activities such as developing new courses that emphasize practical skills, modern IT tools, and technologies. Furthermore, the project enhances student internships and practical experiences, ensuring that graduates meet the current needs of the industry. This practical orientation directly responds to the regional priority of improving employability and industry relevance in higher education. 3. Strengthening University-Industry Collaboration National/Regional Priority: Promoting collaboration between universities and industries is a critical regional priority. The Serbian government and regional bodies stress the importance of partnerships that drive research and innovation, as well as improve student employability through internships and real-world learning experiences. How the Project Addresses This Priority: The project fosters strong collaboration between universities and industries by enhancing internship programs, conducting study visits to business and tech environments, and involving industry partners in curriculum development. Through activities like panel discussions, business simulations, and internship placements, students will gain exposure to real-world business challenges. Additionally, industry partners will collaborate with universities in Serbia to develop joint R&D projects in emerging fields such as AI, blockchain, and cloud computing. This ensures that universities become innovation hubs that contribute directly to economic development, in line with regional priorities for education and industry cooperation. 4. Capacity Building and Internationalization National/Regional Priority: Increasing the capacity of universities to operate at an international level and promote knowledge exchange is a key regional priority. Serbia and the broader Western Balkans are focused on improving the quality of higher education by fostering collaboration with EU and international institutions to enhance academic standards, research capabilities, and student mobility. How the Project Addresses This Priority: The project emphasizes building the capacity of Serbian universities through collaboration with top-tier EU institutions, including the Technical University of Berlin, IT University of Copenhagen, and Dublin Business School. These partnerships provide Serbian faculty and students with access to international expertise, resources, and research opportunities. The project also includes training for faculty and administrative staff in the latest digital tools and management systems, enhancing the institutional capacity to operate efficiently in a global educational landscape. Furthermore, the project supports student and staff mobility by organizing study visits, virtual exchanges, and international conferences, aligning with the priority of fostering internationalization. 5. Improving Research and Innovation Capacity National/Regional Priority: The Western Balkans region prioritizes enhancing the research and innovation capacities of its universities, particularly in areas such as digital technologies, engineering, and business innovation. Developing the research infrastructure and promoting technology transfer between universities and industry are key objectives. How the Project Addresses This Priority: The project addresses this priority by establishing advanced laboratories for AI, machine learning, and digital transformation. These labs will serve as research hubs where students and faculty can engage in cutting-edge projects that drive technological innovation. Additionally, the project’s focus on building partnerships with industry ensures that research conducted at Serbian universities has practical applications in the real world, promoting technology transfer. By enhancing research infrastructure and fostering collaboration with EU institutions, the project contributes to creating a more innovative higher education system in Serbia. 6. Quality Assurance and Institutional Development National/Regional Priority: A priority for Serbia and the Western Balkans is improving the quality of education through the implementation of robust quality assurance frameworks and institutional development strategies. There is a strong focus on enhancing governance, transparency, and accountability within educational institutions. How the Project Addresses This Priority: The project integrates quality assurance mechanisms into every aspect of its activities, ensuring that the initiatives are sustainable and meet international standards. The development of the Quality Control and Monitoring (QCM) manual will provide Serbian universities with tools to assess their progress in achieving educational and research goals, especially in the context of the "third mission" (social responsibility and community engagement). By implementing e-management systems using blockchain technology, the project will also enhance transparency and accountability in university operations. These efforts align with the priority of institutional development and improving governance in higher education. 7. Lifelong Learning and Skills Development National/Regional Priority: Serbia and the Western Balkans prioritize lifelong learning and the continuous development of skills for students, graduates, and professionals. This includes fostering environments where students can continuously upgrade their skills to adapt to changes in technology and the labor market. How the Project Addresses This Priority: The project promotes lifelong learning by integrating flexible learning pathways into its curriculum development. Through business simulations, panel discussions, and interactive learning modules, the project offers students and faculty opportunities to continuously update their skills in emerging fields such as AI, blockchain, and digital transformation. Additionally, the project's collaboration with industry ensures that skills training remains relevant to the evolving needs of the job market, directly addressing the regional priority of fostering lifelong learning and skills development.

(Please add Partner Countries/regions as appropriate)

# D.2 Aims and objectives

- What does the proposal aim at in general? What are the project’s specific objectives?

- Explain how the specific objectives of the project address theproblems mentioned in Part D1 and the needs of each target group in each Partner Country. Demonstrate also that the set objectives are realistic and feasible in the national and institutional context(s).

(limit 8.000 characters)

The primary aim of the project is to enhance the quality and relevance of higher education at Serbian universities by modernizing IT infrastructure, updating curricula, improving practical experiences for students, and fostering stronger university-industry collaboration. It focuses on creating a digitally-driven academic environment that aligns with global trends in technology, ensuring that students, faculty, and the economy benefit from the implementation of cutting-edge tools and methodologies. This project seeks to address gaps in Serbian universities by providing modern educational platforms, expanding research capacity, and integrating industry-relevant practices into academic programs. The goal is to equip students with skills needed for the digital economy and foster a culture of innovation within Serbian higher education institutions. General Aim of the Proposal The project’s overall aim is to: • Modernize IT infrastructure at Serbian universities. • Develop and implement advanced curricula in Software Engineering and Business Informatics. • Improve the quality and relevance of student internships and practical experiences. • Establish laboratories for AI, machine learning, and digital transformation to support research and teaching. These initiatives aim to transform Serbian universities into centers of technological innovation, bridging the gap between education and industry while aligning with international standards. Specific Objectives of the Project 1. Analiza trenutnog stanja, potreba i dobrih praksi (Analysis of Current State, Needs, and Best Practices): This objective involves analyzing the current conditions at Serbian universities, identifying gaps in infrastructure, curricula, and partnerships. The analysis will reveal the specific needs of each institution and benchmark best practices from leading EU institutions. o Addresses Problems: Serbian universities face challenges in maintaining updated curricula and infrastructure. This analysis will identify areas needing improvement, laying the foundation for targeted interventions. o Addresses Needs: The analysis ensures solutions are data-driven and tailored to the needs of students, faculty, and administrative staff. o Realism and Feasibility: By leveraging existing resources and partnerships, the project will gather accurate data through interviews, focus groups, and benchmarking. 2. Razvoj modernih IT tehnologija na srpskim univerzitetima (Development of Modern IT Technologies): This objective focuses on implementing cutting-edge IT systems like blockchain-based e-management, cloud computing, and DevOps across Serbian universities to enhance both administrative and educational processes. o Addresses Problems: The outdated IT infrastructure in Serbian universities limits efficiency and the ability to offer modern education. o Addresses Needs: Students require hands-on experience with the latest technologies, while faculty need tools for teaching and research. This objective ensures the availability of training in AI, machine learning, and blockchain. o Realism and Feasibility: With support from international partners, the gradual integration of prototypes and systems into university operations is achievable, making this objective sustainable and scalable. 3. Osavremenjivanje stručnih praksi (Modernization of Internships and Practical Experiences): This objective aims to improve student internships by strengthening the link between universities and industry partners. The goal is to ensure that students gain relevant, hands-on experience to prepare them for the job market. o Addresses Problems: The disconnect between university curricula and industry needs leads to graduates lacking practical experience. o Addresses Needs: Students need practical exposure, while industry partners require graduates with real-world skills. This objective fosters stronger university-industry connections. o Realism and Feasibility: By building on existing university-industry relationships, this objective expands internship opportunities and integrates them into academic frameworks, creating sustainable improvements in employability. 4. Formiranje laboratorije za digitalnu transformaciju (Establishment of Laboratories for Digital Transformation): The project will establish labs for AI, machine learning, and digital transformation, creating hubs for research, innovation, and practical training. o Addresses Problems: Serbian universities lack the infrastructure for advanced research and training in digital technologies. This objective addresses this by establishing dedicated innovation spaces. o Addresses Needs: Students and researchers need access to modern tools and resources for practical learning and advanced research. Industry partners will benefit from university-led innovation driving economic growth. o Realism and Feasibility: With experienced international partners, establishing these laboratories is feasible, ensuring they are well-integrated into research and teaching. How the Specific Objectives Address Problems and Target Group Needs Each specific objective is designed to address the challenges and needs of target groups at Serbian universities, including students, faculty, administrative staff, and industry partners. 1. Students: o Problems Addressed: Lack of modern curricula, practical training, and access to emerging technologies limits students' employability. o How Objectives Meet Their Needs: By introducing modern IT systems, enhancing internships, and establishing advanced labs, students gain practical, industry-relevant skills, improving their competitiveness in the job market. 2. Faculty and Researchers: o Problems Addressed: Faculty members lack the tools and resources to teach and conduct research in advanced fields like AI and blockchain. o How Objectives Meet Their Needs: The development of modern IT technologies and establishment of laboratories provide faculty with the tools they need to improve teaching and research. Training programs will help them stay updated with the latest technological trends. 3. Administrative Staff: o Problems Addressed: Administrative processes at Serbian universities are inefficient due to outdated systems. o How Objectives Meet Their Needs: The implementation of blockchain-based e-management systems streamlines operations, improving transparency, data security, and efficiency. 4. Industry Partners: o Problems Addressed: Industry partners struggle to find graduates with practical skills needed to contribute to innovation in sectors like technology, finance, and manufacturing. o How Objectives Meet Their Needs: By modernizing internships and fostering collaboration with universities, the project ensures that students graduate with the skills needed by industry, creating a pipeline of talent and supporting joint R&D projects. Realism and Feasibility of the Objectives The project's objectives are realistic and feasible within Serbia's national and institutional contexts. Several factors ensure their success: 1. Support from International Partners: The involvement of experienced institutions like the Technical University of Berlin and IT University of Copenhagen provides access to expertise, resources, and best practices. This collaboration ensures that the project’s objectives are achievable within the Serbian context. 2. Alignment with National Priorities: The project aligns with Serbia’s education and innovation strategies, which emphasize digital transformation, higher education modernization, and stronger university-industry collaboration. This alignment ensures that the project is backed by institutional and governmental policies. 3. Existing Institutional Capacity: Serbian universities are committed to modernizing their curricula and adopting new technologies. The project builds on this momentum, making the objectives realistic and well-suited to the current environment. 4. Scalability and Sustainability: The project’s phased approach—starting with pilot systems and prototypes—ensures that technologies and practices can be tested and refined before being fully implemented. This approach guarantees scalability and adaptability to various institutional capacities. Conclusion The project’s specific objectives are carefully crafted to address the identified problems and meet the needs of students, faculty, administrative staff, and industry partners at Serbian universities. Through international collaboration and a strategic approach, the project aims to create a sustainable, forward-looking higher education system that aligns with global technological trends and supports economic growth in Serbia.

(Please add Partner Countries/regions as appropriate)

Please explain how the planned activities and the expected results meet the needs of the identified target groupsin the Partner Countries(limit 6.000 characters)

The project’s activities are designed to meet the needs of the target groups at Serbian universities and partner institutions. These groups include students, faculty, administrative staff, and industry partners. Each activity addresses current gaps in higher education, ensuring that outcomes align with the evolving digital economy, delivering impactful and sustainable results. 1. Students Identified Needs: Students require modern curricula, practical experience with advanced technologies like AI, blockchain, and cloud computing, and stronger connections to the job market. Planned Activities: • Curriculum Modernization: Updating curricula in Software Engineering and Business Informatics with cutting-edge technologies. • Internship Programs: Strengthening internship opportunities to provide real-world industry experience. • Laboratories: Creating AI, machine learning, and digital transformation labs to enhance hands-on learning. Expected Results: • Improved Employability: Graduates will have skills that match industry demands. • Access to Emerging Technologies: Students will gain exposure to AI, machine learning, and blockchain. • Increased Practical Experience: Internship programs will bridge the gap between academic learning and the job market. 2. Faculty and Researchers Identified Needs: Faculty need access to advanced teaching tools and training, and opportunities to collaborate with international institutions to stay updated on global trends in technology and research. Planned Activities: • Faculty Training: Providing training on advanced technologies and methodologies. • International Collaboration: Facilitating research partnerships and knowledge-sharing with EU institutions. • Research Labs: Establishing labs for digital transformation and AI to support research and teaching. Expected Results: • Enhanced Teaching: Faculty will integrate new pedagogical tools and technologies into their courses. • Strengthened Research Capacity: Access to advanced research tools will allow faculty to engage in innovative research. • Knowledge Exchange: Collaboration with EU partners will lead to long-term research and curriculum development projects. 3. Administrative Staff Identified Needs: Administrative staff require modern digital tools to streamline operations, improve data security, and manage university processes more efficiently. Planned Activities: • E-Management Systems: Implementing blockchain-based e-management systems to improve operational efficiency. • Training Programs: Providing training on the use of new digital tools. Expected Results: • Increased Efficiency: Administrative processes will be more efficient and transparent. • Improved Data Security: Blockchain systems will enhance data integrity and security. • Streamlined Operations: Staff will manage academic and student records more effectively. 4. Industry Partners Identified Needs: Industry partners need graduates with practical skills in emerging technologies, and stronger collaboration with universities for joint research and development initiatives. Planned Activities: • University-Industry Collaboration: Strengthening partnerships between universities and industries for internships and R&D projects. • Modernizing Internships: Ensuring that internships align with industry needs. • Panel Discussions and Workshops: Engaging industry leaders in discussions and workshops to align educational outcomes with workforce needs. Expected Results: • Highly Skilled Graduates: Industry partners will have access to graduates with relevant, practical skills in AI, blockchain, and other emerging technologies. • Collaborative R&D: Universities and industry partners will collaborate on innovative R&D projects. • Strengthened Ties: Industry-university partnerships will ensure that educational programs stay aligned with market needs. Addressing Needs in Partner Institutions Državni Univerzitet u Novom Pazaru: • Activity Focus: Modernizing IT infrastructure and improving training in Computer Technologies and Economics. • Expected Results: Enhanced employability for students through hands-on learning and improved digital literacy for faculty. Univerzitet u Nišu (Faculty of Electronic Engineering): • Activity Focus: Establishing AI and digital transformation labs and modernizing engineering and IT curricula. • Expected Results: Increased research capacity and the production of graduates with technical skills in AI and digital transformation. Elektrotehnički Fakultet u Beogradu: • Activity Focus: Implementing advanced IT systems, updating curricula, and fostering industry partnerships. • Expected Results: Better preparation for careers in digital technologies and stronger ties with the tech sector. Univerzitet u Kragujevcu (Faculty of Mechanical Engineering): • Activity Focus: Developing practical engineering curricula and creating digital transformation labs. • Expected Results: Graduates with practical skills in automation and AI, supporting Serbia’s manufacturing and tech industries. Ekonomski Fakultet u Beogradu: • Activity Focus: Modernizing Business Informatics curricula and building partnerships with the finance and tech sectors. • Expected Results: Graduates equipped with knowledge in fintech and digital business, ready for leadership roles in these industries. Conclusion The project’s activities directly address the needs of students, faculty, administrative staff, and industry partners in each partner country and institution. By providing modernized curricula, advanced IT infrastructure, practical experience, and closer links with industry, the project ensures that Serbian universities produce graduates ready for the digital economy. These initiatives enhance the teaching and research capacities of faculty, streamline administrative processes, and foster collaboration that drives innovation and growth. This comprehensive approach ensures that all stakeholders benefit from sustainable improvements in higher education.

(Please add Partner Countries as appropriate)

How will the project and its results contribute effectively to the objectives of the action Capacity-Building in the Field of Higher Educationin eachtargetedPartner Country? (limit 6.000 characters)

The project contributes directly to the objectives of Capacity-Building in the Field of Higher Education by addressing key challenges in Serbian higher education institutions. Its activities and results focus on enhancing the quality, accessibility, and relevance of higher education, aligned with the broader goals of Capacity-Building initiatives. The following explains how the project contributes effectively to the core objectives across Serbia. 1. Improving the Quality of Higher Education The project modernizes curricula, upgrades IT infrastructure, and introduces innovative teaching and learning methods across Serbian universities. By aligning educational programs with global technology trends like AI, blockchain, and cloud computing, the project improves the quality of education. How It Achieves This: • Curriculum Development: Introducing state-of-the-art curricula in Software Engineering and Business Informatics, meeting industry needs and technological advancements. • Faculty Training: Providing faculty with training on cutting-edge technologies, improving their teaching methods to align with international standards. • Research and Laboratories: Establishing research labs for AI, machine learning, and digital transformation to equip students and faculty with tools for high-level research. Results: • Graduates will gain skills aligned with modern job market demands, especially in IT-related fields. • Faculty will be equipped with the latest methodologies and technologies, improving student learning outcomes. 2. Strengthening University-Industry Linkages The project strengthens the relationship between Serbian universities and industry by modernizing internships and creating opportunities for collaboration. This addresses a major gap in Serbian higher education, where practical skills among graduates are often lacking. How It Achieves This: • Internships and Practical Training: The project enhances internships by collaborating with industry partners, ensuring students gain relevant experience. • Collaborative R&D: Universities will work with industry partners on joint R&D projects, driving technological innovation. • Panel Discussions and Workshops: Regular interactions between industry leaders and universities will ensure that education aligns with industry needs. Results: • Graduates will possess practical skills, making them more employable. • University-industry partnerships will foster joint innovation projects, leading to long-term collaboration. 3. Modernizing Infrastructure for Higher Education The project addresses the need for modern IT infrastructure in Serbian universities by implementing advanced e-management systems, cloud platforms, and blockchain-based systems. These improvements enhance the efficiency of university operations and enable cutting-edge education in line with international standards. How It Achieves This: • Digital Infrastructure: Cloud computing and blockchain-based e-management systems modernize both academic and administrative operations, enhancing transparency, security, and efficiency. • Laboratories for Digital Transformation: Establishing labs for AI and digital transformation provides the infrastructure needed for students and researchers to engage with modern technologies. Results: • Universities will operate more efficiently with updated IT systems, improving the experiences of students and faculty. • The modern infrastructure will help Serbian universities compete globally and attract more students. 4. Enhancing Research Capacities The project directly contributes to improving research capacity in Serbian universities by creating labs focused on cutting-edge technologies. This allows Serbian institutions to become centers for advanced research and innovation. How It Achieves This: • Research Labs: Creating AI and digital transformation labs supports high-level research, enabling faculty and students to engage with advanced technologies. • International Collaboration: Facilitating research partnerships between Serbian and EU institutions fosters knowledge exchange and joint research projects. Results: • Serbian universities will increase their research output, particularly in digital transformation and IT. • Collaboration with international partners will position Serbian institutions as key players in global research networks. 5. Fostering International Cooperation The project enhances international cooperation by establishing strong partnerships between Serbian universities and institutions from the EU and Turkey. This aligns with the broader Capacity-Building objective of promoting international cooperation and best practice exchange in higher education. How It Achieves This: • Collaboration with EU and Turkish Institutions: Partner universities from Serbia, Germany, Denmark, and Turkey will collaborate on curriculum development, research, and knowledge sharing. • Exchange of Best Practices: Serbian institutions will benefit from EU expertise in digital technologies and higher education management. • Study Visits and Knowledge Exchange: Study visits to EU institutions will enable Serbian universities to adopt best practices from their counterparts. Results: • Serbian universities will gain insights into international best practices and apply them in local contexts. • Long-term international collaboration will continuously improve education quality and research capacity. 6. Aligning with National and Institutional Priorities The project is aligned with Serbia's national priorities, which emphasize digital transformation, modernized curricula, and strengthened university-industry collaboration. It also supports the long-term goals of individual universities by enhancing their competitiveness in the global higher education landscape. How It Achieves This: • Alignment with National Education Strategies: The project supports national efforts to modernize higher education, particularly in IT, engineering, and business. • Institutional Goals: The project addresses the needs of each participating institution, contributing to their specific development plans and goals. Results: • The project will contribute to the overall modernization of Serbia’s higher education system, aligning it with international standards. • Each partner institution will see significant improvements in infrastructure, curricula, and research capacity, positioning them as leaders in digital education.

(Please add Partner Countries as appropriate)

How do the project's objectives fit in with the modernisation and internationalisation agenda of the targeted higher education institutions in the Partner Countries and with the development strategy for higher education in each Partner Country involved in the project? (limit 6.000 characters)

The project's objectives align closely with the modernization and internationalization agendas of targeted higher education institutions in Serbia and partnered countries, as well as national development strategies for higher education. By integrating advanced IT systems, modernizing curricula, building research capacity, and fostering university-industry collaboration, the project supports the enhancement of quality, relevance, and international engagement in higher education across all partner countries. 1. Alignment with Institutional Modernization Agendas Serbian Higher Education Institutions Objective 1: Modernizing IT Infrastructure Serbian universities such as Državni Univerzitet u Novom Pazaru, Univerzitet u Nišu, and Elektrotehnički Fakultet u Beogradu prioritize modernizing IT infrastructure to improve both academic and administrative efficiency. The project’s integration of cloud computing, blockchain-based e-management systems, and AI-driven platforms directly supports their digital transformation goals. Fit with Modernization Agenda: By upgrading digital infrastructure and integrating cutting-edge technologies into daily operations, the project enhances these universities' ability to deliver high-quality education and streamline administrative processes. This objective aligns with their vision of creating tech-driven academic environments that foster innovation and collaboration. Objective 2: Curriculum Modernization and Research Development Universities like the Faculty of Electronic Engineering at Niš and the Faculty of Mechanical Engineering at Kragujevac aim to update curricula to meet the demands of the evolving tech industry. The project focuses on modernizing curricula in Software Engineering and Business Informatics, alongside establishing AI, machine learning, and digital transformation labs. Fit with Modernization Agenda: Introducing advanced curricula and research labs equips students and faculty with the skills and tools for cutting-edge research and practical applications. This supports the modernization goals of these institutions, ensuring graduates are prepared for the digital economy and contribute to technological innovation. 2. Alignment with National Development Strategies for Higher Education in Serbia Digital Transformation and Infrastructure Development Serbia’s national education strategy emphasizes the need for modern IT infrastructure to support digital learning, research, and administration. The project addresses this by implementing blockchain-based management systems and cloud platforms across Serbian universities, supporting the goal of making Serbia a digital innovation hub. Fit with National Strategy: The project contributes to Serbia’s digital transformation by providing the necessary tools and infrastructure to modernize higher education, positioning the country as a leader in digital education and research. University-Industry Collaboration The Serbian government prioritizes strengthening ties between universities and industry to produce graduates with practical, industry-relevant skills. The project enhances internship programs, facilitates joint R&D initiatives, and organizes panel discussions with industry leaders to address this need. Fit with National Strategy: By bridging the gap between academia and industry, the project ensures universities contribute to innovation and economic development, supporting national strategies for workforce readiness and industrial collaboration. Internationalization of Higher Education Serbia’s higher education strategy emphasizes international collaboration to enhance education and research quality. The project partners with EU institutions such as the Technical University of Berlin, IT University of Copenhagen, and Dublin Business School, as well as Istanbul Technical University, to support Serbia’s internationalization goals. Fit with National Strategy: The project fosters international collaboration, aligning Serbia’s higher education system with global standards, enhancing academic networks, and improving education quality. 3. Fit with Institutional Internationalization Agendas Internationalization at Serbian Institutions Serbian universities, including the University of Belgrade and the University of Novi Pazar, aim to expand international collaborations. The project’s partnerships with EU and Turkish institutions advance their internationalization agenda through knowledge exchange, research collaboration, and adoption of international best practices. Fit with Internationalization Agenda: Incorporating international expertise into curriculum development and research raises the global status of Serbian universities, opening opportunities for student and faculty exchange, joint research, and global partnerships. Collaboration with EU Partners EU institutions like the Technical University of Berlin and IT University of Copenhagen are leaders in digital transformation and education. By collaborating with these institutions, Serbian universities gain access to the latest advancements in educational technologies, teaching methods, and research networks. Fit with Internationalization Agenda: The collaboration enhances the global competitiveness of Serbian universities by aligning their programs with European standards and increasing visibility in international research networks. This supports both national and institutional goals, positioning Serbian universities as global academic players. 4. Support for Regional Cooperation and Integration Regional Cooperation In addition to fostering international partnerships, the project promotes regional cooperation through collaboration with Istanbul Technical University in Turkey. Involving a regional partner encourages integration and the exchange of best practices within the Balkan and Mediterranean regions. Fit with Regional Cooperation: This partnership enhances Serbia’s regional influence in higher education and supports broader geopolitical goals of fostering cooperation. It ensures Serbian universities are well-positioned for cross-border academic initiatives.

(Please add Partner Countries/partners as appropriate)

Please explain how the proposal will pay attention tothe issues of inclusion, diversity and socio-economically disadvantaged participantsand/or organisations in the Partner Countries. (limit 2.000 characters)

The proposal places strong emphasis on inclusion, diversity, and support for socio-economically disadvantaged participants and organizations in the Partner Countries. By modernizing IT infrastructure, enhancing curricula, and fostering university-industry collaboration, the project aims to create an accessible and equitable educational environment that accommodates students and staff from diverse backgrounds, including those facing socio-economic challenges. Inclusion: The project ensures that all students, regardless of background, have access to the same high-quality education and resources. By introducing advanced technologies such as AI, cloud computing, and digital transformation labs, the project enables students from remote or underserved regions to participate in cutting-edge learning experiences. The digital tools and e-learning platforms reduce geographic barriers and provide flexible, affordable access to education. Diversity: The project promotes cultural and academic diversity by encouraging collaboration between universities in Serbia, EU countries, and Turkey. By integrating international best practices and fostering cross-cultural exchanges, the project enhances the educational experience for participants from diverse ethnic, social, and cultural backgrounds. Faculty and student exchange programs will create opportunities for participants to interact with peers and experts from various countries, promoting a global perspective. Support for Socio-Economically Disadvantaged Participants: The project targets socio-economically disadvantaged students by providing access to internships, scholarships, and practical training, helping them gain valuable work experience and enhance their employability. The emphasis on internships with local businesses and SMEs will offer participants from disadvantaged backgrounds the chance to build professional networks and gain skills relevant to the labor market. By addressing these issues, the project ensures equitable participation and benefits for all stakeholders.

# D.3 Innovative character

Demonstrate why the proposal is innovative.

If it is complementary to previous/existing funded projects nationally or internationallyplease explain how the new proposal build on it/them and demonstrate its added value and why it is not a simple continuation thereof. (limit 2.000 characters)

The proposal is innovative because it addresses the evolving needs of higher education in a digital era by integrating cutting-edge technologies and modern educational approaches into the academic systems of Serbian universities. It leverages advanced IT systems such as blockchain-based e-management, cloud computing, and AI-driven platforms, which are not yet widely implemented in the region’s higher education institutions. This modernization of infrastructure provides a foundation for digital transformation across academic, administrative, and research functions, setting a new standard for university operations in Serbia. The project introduces modern curricula in Software Engineering and Business Informatics that are aligned with the latest global trends, including AI, machine learning, and digital transformation. By incorporating these emerging technologies into the educational experience, the proposal ensures that students are equipped with the practical, industry-relevant skills needed in today’s and tomorrow’s job markets. In addition to the technological advancements, the project focuses on strengthening university-industry collaboration in innovative ways. It connects students to real-world applications through updated internship programs, joint R&D initiatives, and industry-driven panels and workshops. This direct link between academia and industry not only bridges the skills gap but also drives innovation and economic growth through collaborative research and development projects. The creation of specialized labs for AI, machine learning, and digital transformation is another innovative aspect of the project. These labs will serve as hubs for cutting-edge research and practical training, enabling both faculty and students to engage in innovative projects and contributing to the development of future-forward skills and technologies in the region. By integrating advanced technology, modern educational methodologies, and strengthened industry links, this proposal sets a benchmark for innovation in higher education.

If the proposal builds on any previous or existing EU-funded/non-EU funded national or international activities/projects in this field, please fill the following table for each of these projects.

☐

| Reference number |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) |  |  | Programme or initiative |  |
| Funded by |  |  |  |  |
| Title of the project |  |  |  |  |
| Coordinating organisation |  |  |  |  |
| Partner Countries /institutions targeted by this project |  |  |  |  |
| Website | http:// |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000characters). |  |  |  |  |

Please copy and paste tables as necessary

# D.4European added value

Why is there a need for cooperation with the Programme Countries in this area of activity and a funding via the Erasmus+ Programme?Why can the intended results not be achieved through national, regional or local funding in the Partner Countries? (limit 2.000 characters)

There is a clear need for cooperation with Programme Countries and funding via the Erasmus+ Programme for this project due to the advanced expertise, resources, and global experience that Programme Country institutions bring to the table. Serbian universities are currently facing challenges in modernizing their infrastructure, curricula, and research capacities, which require access to cutting-edge technologies, international collaboration, and best practices that are well-established in Programme Countries like Germany, Denmark, and Ireland. Expertise and Knowledge Transfer: Universities in Programme Countries, such as the Technical University of Berlin and IT University of Copenhagen, are recognized leaders in digital transformation, AI, blockchain, and innovative educational practices. Their involvement will facilitate the transfer of knowledge and best practices that are not currently available in Serbian universities. The project leverages their expertise in modernizing curricula, implementing cutting-edge IT infrastructure, and developing research labs, which are essential for elevating Serbian higher education to international standards. Global Collaboration and Networking: Cooperation with Programme Countries creates opportunities for cross-border collaboration, joint research projects, and student/faculty exchanges, all of which are critical for fostering innovation and enhancing the global competitiveness of Serbian universities. Erasmus+ funding allows Serbian universities to build long-term partnerships that will sustain beyond the project’s life cycle, creating a solid foundation for continuous growth and development. Funding Gap: National, regional, or local funding in the Partner Countries is often limited and unable to cover the costs associated with implementing large-scale modernization projects involving advanced technologies and international collaboration. The Erasmus+ Programme provides essential financial resources to facilitate this transformation, enabling the Serbian universities to access expertise, technologies, and networks that are otherwise out of reach.

# D.5 Cross-regional cooperation

If your proposal is cross-regional, demonstrate the need for this cooperation between institutions from different regions.Please also explain the added value of this cross-regional cooperation for the targeted Partner Country institutions. (limit 2.000 characters)

Cross-regional cooperation between institutions from different regions is essential for addressing the shared challenges faced by Serbian universities, particularly in the areas of digital transformation, curriculum modernization, and university-industry collaboration. Institutions from Programme Countries such as Germany, Denmark, and Ireland have already established best practices in these areas, which Serbian universities can benefit from by engaging in this cooperative effort. Need for Cross-Regional Cooperation: Serbian higher education institutions are in the early stages of adopting advanced technologies like AI, blockchain, and cloud computing. However, the lack of access to cutting-edge knowledge, infrastructure, and expertise hinders their ability to make this transition independently. Institutions in Programme Countries, such as the Technical University of Berlin and IT University of Copenhagen, are leaders in implementing these technologies and can transfer their knowledge and resources. This cooperation accelerates the modernization of Serbian universities and bridges the technological and educational gaps they face. Added Value of Cross-Regional Cooperation: Cross-regional collaboration offers immense added value by facilitating the transfer of innovative ideas, modern teaching methodologies, and cutting-edge research practices. Through partnerships with institutions in Programme Countries, Serbian universities can gain access to international networks, joint research opportunities, and capacity-building initiatives that they would not achieve locally. This cooperation also fosters intercultural exchange, enhancing the global outlook of Serbian students and faculty by integrating them into global academic and professional communities. Long-term Benefits: The knowledge exchange and capacity-building elements of this cross-regional cooperation help Serbian universities establish sustainable and scalable solutions in curriculum development, research, and university-industry relations. These collaborations create an international framework for continuous growth, innovation, and competitiveness in the global education landscape.

# PART E – Quality of the Project Design and Implementation

# E.1 Project activities and methodology

Please provide a detailed description of the activities and the working methodology to be used for achieving the objectives (including major milestones, measurable indicators, etc.). (limit 6.000 characters)

To achieve the project's objectives, a clear methodology and set of structured activities have been developed. The project’s activities are divided into four key areas: analysis of the current state, development of modern IT technologies, modernization of professional practices, and the establishment of digital transformation laboratories. The following outlines the core activities, working methodology, and milestones designed to meet these objectives. 1. Analysis of Current State, Needs, and Best Practices This phase lays the foundation for the entire project, ensuring that all interventions are data-driven and aligned with the needs of each partner institution. Activities: 1.1 Needs Assessment and Feasibility Study: Conduct interviews and focus groups with stakeholders at Serbian universities, industry partners, and students to evaluate the current status of IT infrastructure, curricula, and professional practices. 1.2 Benchmarking with EU Institutions: Analyze best practices from partner universities in Programme Countries through virtual study visits, workshops, and case studies to understand the successful implementation of modern IT systems, internships, and industry collaborations. Working Methodology: Data will be collected through surveys, interviews, and focus groups. Best practices from EU partners will be benchmarked using qualitative analysis to identify gaps and opportunities for Serbian institutions. Milestones: • Completion of interviews and focus groups (Month 2). • Delivery of a comprehensive analysis report detailing gaps and opportunities (Month 3). Measurable Indicators: • Number of stakeholders engaged (minimum 100). • Completion of a benchmarking report on best practices. 2. Development of Modern IT Technologies at Serbian Universities The modernization of IT infrastructure and digital systems at Serbian universities is crucial for aligning with global technological trends. Activities: 2.1 Prototyping and Testing IT Solutions: Develop a minimal viable product (MVP) for an e-management system based on blockchain and cloud computing technologies. 2.2 System Integration: Integrate these IT solutions into the existing administrative and academic processes across universities, focusing on scalability and security. Working Methodology: Cross-institutional teams will design and test the MVP, with input from both Serbian and Programme Country partners. The system will be iteratively tested for performance, user acceptance, and security compliance. Milestones: • Delivery of MVP (Month 6). • Successful integration of the system in at least three Serbian universities (Month 12). Measurable Indicators: • Number of universities implementing the new IT systems (minimum 3). • User satisfaction score from pilot testing (target: >80%). 3. Modernization of Professional Practices (Internships and Practical Experiences) This phase addresses the gap between academic training and industry requirements by enhancing internship programs and creating strong university-industry linkages. Activities: 3.1 Study Visits for Good Practice Exchange: Organize study visits to EU partner universities to observe their approach to business simulations, internships, and student-industry engagement. 3.2 Redesign of Internship Programs: Work with industry partners to co-develop new internship models and integrate them into curricula. 3.3 Workshops and Panel Discussions with Industry: Facilitate workshops with industry leaders in Serbia to align academic outputs with labor market needs. Working Methodology: Each Serbian university will engage industry partners through consultations and workshops to co-design internship programs that are relevant and scalable. Study visits will provide insights into successful EU models. Milestones: • Completion of study visits and virtual workshops (Month 8). • Launch of redesigned internship programs (Month 10). Measurable Indicators: • Number of internships established with local businesses (target: 50). • Participation of students in new internships (target: 200 students). 4. Establishment of Laboratories for Digital Transformation This activity focuses on creating dedicated spaces for research, innovation, and training in AI, machine learning, and cloud computing. Activities: 4.1 Laboratory Design and Setup: Establish digital transformation labs at each partner Serbian university, fully equipped with modern tools and resources for research in AI, machine learning, and blockchain technologies. 4.2 Faculty and Student Training: Provide training for faculty and students on the use of these labs, ensuring their integration into research and curriculum development. 4.3 Launch of Research Projects: Collaborate with EU partners to initiate joint research projects in the new labs, focusing on cutting-edge technologies. Working Methodology: The labs will be designed based on input from faculty, industry, and EU partners. Training programs will be co-developed with experts from Programme Country institutions. Milestones: • Completion of lab setup at all universities (Month 12). • Launch of joint research projects with EU partners (Month 14). Measurable Indicators: • Number of labs established (minimum 5). • Number of students and faculty trained (minimum 100). • Number of joint research projects initiated (minimum 5). Cross-Cutting Activities Monitoring and Evaluation The project will implement a continuous monitoring and evaluation process to ensure that all activities are progressing according to plan and achieving the desired impact. Regular progress reports will be shared among partners, and feedback from stakeholders will be collected at key milestones. Measurable Indicators: • Number of progress reports submitted (quarterly). • Feedback score from stakeholders (target: >85% satisfaction). Dissemination and Exploitation To ensure that the project's outcomes are sustainable and scalable, a dissemination strategy will be put in place. This includes hosting info days, creating project websites, and conducting a final conference to share results with a broader audience. Measurable Indicators: • Number of dissemination events hosted (minimum 10). • Number of participants attending dissemination activities (minimum 300).

Please demonstrate that the activities and the methodology mentioned are the most appropriate to achieve the envisaged results and that they are feasible. (limit 3.000 characters)

The activities and methodology outlined in the project are carefully designed to meet the specific needs of Serbian universities, making them both appropriate and feasible for achieving the desired results. By following a structured, phased approach that includes analysis, development, implementation, and evaluation, the project builds on data-driven insights and international best practices, ensuring practical impact within local and institutional contexts. Appropriateness of Activities and Methodology The initial data-driven needs assessment and benchmarking ensure that interventions are tailored to address specific challenges at Serbian universities. By analyzing the current infrastructure and practices, the project identifies gaps and develops targeted solutions. Benchmarking against best practices from Programme Country partners aligns Serbian institutions with global standards, making modernization efforts both relevant and impactful. The development and implementation of IT solutions focuses on introducing modern IT systems like blockchain-based e-management and cloud computing to enhance administrative efficiency and digital learning environments. These technologies, proven successful in Programme Countries, will be gradually integrated into Serbian universities, starting with MVP prototypes, followed by full-scale implementation. This phased rollout reduces risks and ensures adaptability to the institutions' specific needs. To address the gap between academic knowledge and labor market demands, the project emphasizes modernizing internships and university-industry collaboration. Working with industry partners to co-design internship programs ensures that students gain practical skills aligned with industry needs, while also strengthening ties between universities and key economic sectors. The establishment of digital transformation laboratories for AI, machine learning, and digital transformation is crucial for equipping students and faculty with the tools needed for cutting-edge research and practical learning. Input from local stakeholders and international partners ensures that these labs are fully integrated into the academic system, and training programs ensure their optimal use. Feasibility of the Methodology The project leverages existing institutional resources and partnerships, ensuring that the proposed activities can be effectively implemented. The involvement of Programme Country institutions, with their expertise in modern IT and education systems, provides Serbian universities with the necessary support to overcome challenges. A phased implementation strategy—starting with analysis, followed by piloting, scaling, and evaluation—ensures that the project remains adaptable to the evolving needs of universities. This approach reduces risks and builds on lessons learned during each phase. The project includes capacity building for faculty, staff, and students, ensuring they can effectively use the new systems, labs, and methodologies. This training guarantees the sustainability of the project's outcomes, empowering universities to continue advancing after the project's completion. In summary, the project's activities and methodology are both appropriate and feasible, ensuring impactful, sustainable, and scalable results.

What concrete, tangible results are expected to be achieved at the end of the project's activities in each of the targetedPartner Countries? (limit 6.000 characters)

At the conclusion of the project's activities, several concrete and tangible results will be achieved across each partner country, particularly in Serbia, where the primary focus is on modernizing higher education institutions. These results will transform Serbian universities into modern centers of learning, research, and innovation, benefiting students, faculty, administrative staff, and industry partners alike. Serbia Državni Univerzitet u Novom Pazaru Expected Results: • Modernized IT Infrastructure: Implementation of advanced IT systems, including blockchain-based e-management platforms and cloud services, streamlining administrative operations and enhancing digital learning environments. • Updated Curricula: Modernized programs in Computer Technologies and Economics incorporating AI, blockchain, and cloud computing, equipping students with relevant skills for the digital economy. • Increased Internship Opportunities: Stronger partnerships with local industry, providing students with hands-on experience in emerging technologies. • New Laboratories: Establishment of digital transformation labs for AI and machine learning, boosting research and innovation capacity. Univerzitet u Nišu (Faculty of Electronic Engineering) Expected Results: • Enhanced Digital Labs: Creation of AI, DevOps, and cloud computing laboratories, offering students and faculty access to cutting-edge tools for practical learning and research. • Modernized Engineering Curriculum: Updated curriculum reflecting the latest industry trends, equipping graduates with in-demand skills in engineering fields. • Strengthened Industry Collaboration: Strengthened ties with tech companies and startups, offering students increased opportunities for internships and joint R&D projects. Elektrotehnički Fakultet u Beogradu (University of Belgrade - Faculty of Electrical Engineering) Expected Results: • Cutting-Edge IT Systems: Implementation of advanced IT infrastructure (AI, blockchain, cloud), enhancing academic and administrative functions, and making the faculty a leader in digital transformation. • Revised Electrical Engineering Curriculum: New courses focusing on emerging technologies, preparing students for global and local job markets in AI, blockchain, and machine learning. • Industry Collaboration: Stronger partnerships with large tech firms, providing students with real-world project experience and fostering joint research. Univerzitet u Kragujevcu (Faculty of Mechanical Engineering) Expected Results: • Modernized Engineering Curriculum: Updated courses focusing on automation, AI, and digital transformation, preparing students for modern engineering roles. • Advanced Labs: Establishment of digital transformation and AI labs for cutting-edge research and development. • Increased Industry Engagement: Expanded internship programs and R&D collaboration with manufacturing firms, providing real-world experience and contributing to local industry innovation. Ekonomski Fakultet u Beogradu (University of Belgrade - Faculty of Economics) Expected Results: • Modernized Business Informatics Curriculum: Curriculum updates reflecting fintech, digital business, and blockchain technology, preparing students for leadership roles in finance and technology. • New Internship and Industry Partnerships: New partnerships with financial institutions and tech firms, offering more practical experience for students. • Enhanced Research Capacity: Development of research labs focused on digital business transformation, boosting Serbia’s digital economy through innovative research. European Union Technical University of Berlin (Germany) Expected Results: • Knowledge Exchange: Collaboration with Serbian institutions on best practices in digital transformation and curriculum development, enriching Serbian IT and education systems. • Joint Research Projects: Initiation of collaborative research projects in AI, machine learning, and blockchain, fostering long-term regional partnerships. IT University of Copenhagen (Denmark) Expected Results: • Cross-Collaboration: Support for Serbian universities in implementing advanced IT systems and modernizing Software Engineering curricula, promoting joint research and exchanges. • Joint Projects: Launch of R&D projects in digital innovation, benefiting both Serbia and Denmark. AVT Business School (Denmark) Expected Results: • Business Curriculum Development: Serbian institutions benefit from AVT’s expertise in modernizing business curricula, particularly in fintech and digital transformation. • International Case Studies: Exposure to global business case studies, enhancing understanding of international market dynamics. Dublin Business School (Ireland) Expected Results: • Collaboration on Business Informatics: Curriculum development in Business Informatics at Serbian universities, integrating global best practices and technology. • Research and Internship Opportunities: Participation in joint research and internships, offering Serbian students international exposure. Turkey Istanbul Technical University Expected Results: • Regional Cooperation: Strengthened ties with Serbian institutions in digital transformation and engineering education, with joint research and academic exchanges established. • Technology Transfer: Collaboration on technology transfer initiatives, integrating new technologies into Serbian curricula and research. Cross-Regional Results • International Partnerships: Long-term cross-regional partnerships between EU, Turkish, and Serbian institutions established for research, curriculum development, and faculty exchange. • Standardized Curricula: Adoption of modern, standardized curricula in Software Engineering, Business Informatics, and other fields, creating high-quality educational programs across partner institutions. • Enhanced Research and Innovation Capacity: New labs and research collaborations significantly boost the research capabilities of Serbian universities, enabling contributions to global innovation in digital transformation, AI, and machine learning. In conclusion, the project will achieve substantial advancements in IT infrastructure, curricula, research capacity, and university-industry collaboration across all partner institutions. These outcomes will elevate the quality and relevance of higher education in Serbia, positioning its universities as key players in the global academic and research landscape.

(Please add Partner Countries as appropriate)

For all types of activities(curriculum development, modernisation of governance, management and functioning of HEIs; strengthening of relations between HEIs and the wider economic and social environment), for each Partner Country institution please provide information in Part F.2 Organisation and Activities.

# E.2Quality control and monitoring

Please explain what mechanisms willbe put in place for ensuring the quality of the project and how the evaluation will be carried out.If an external evaluation is foreseen, provide informationon the purpose and expected outcomes of this evaluation. Please define the specific quality measures established, as well as the benchmarks and indicators foreseen to verify the outcome of the action. Make sure that the information in this section is consistent with the project Logical Framework Matrix. (limit 3.000 characters)

To ensure the quality of the project, a comprehensive internal and external quality assurance framework will be implemented. This approach ensures continuous monitoring, evaluation, and feedback, guaranteeing that the project remains on track, meets its objectives, and delivers high-quality, impactful outcomes. Internal Quality Assurance Mechanisms Regular Monitoring and Reporting: A dedicated Quality Assurance (QA) team will oversee all activities. Partner institutions will submit regular progress reports based on predefined benchmarks and performance indicators. These reports will be reviewed during monthly virtual meetings and quarterly Steering Committee (SC) meetings, ensuring timely identification and resolution of any issues. Quality Control of Deliverables: All outputs, including curricula updates, IT infrastructure implementations, and internship programs, will undergo a peer review process. This internal quality control ensures that all deliverables meet academic and professional standards before finalization. Internal Evaluations: Periodic internal evaluations will be conducted at key project milestones (e.g., after curriculum development, IT installations, and lab establishment). These evaluations will assess if the activities are aligned with project objectives and are making the expected impact. Capacity Building and Training: Faculty and staff will participate in training programs focused on maintaining high standards in curriculum design, research, and administrative processes. Feedback from participants will be collected to ensure the training meets the project’s capacity-building goals. External Quality Assurance and Evaluation External Evaluation: Midway through the project, an external evaluator will be appointed to conduct an independent assessment. This evaluation will ensure that project activities align with the set objectives and offer recommendations for improvement. The evaluation will also assess the impact on target groups like students, faculty, and industry partners. Final External Evaluation: At the end of the project, a final external evaluation will be conducted to assess overall success, based on the pre-established performance indicators and benchmarks. This evaluation will measure the sustainability of the project outcomes, ensuring that the newly implemented systems, curricula, and partnerships continue to benefit the institutions. Specific Quality Measures, Benchmarks, and Indicators Benchmarks: • Curriculum Modernization: Updated curricula adopted across partner institutions within 18 months. • IT Systems Implementation: Blockchain-based e-management systems deployed in three universities by the end of the second year. • Research Labs: Fully operational AI and digital transformation labs established by month 24. Performance Indicators: • Number of Internships: At least 150 new internship placements by the end of the project. • Curriculum Adoption: A minimum of 500 students enrolled in updated courses across partner universities. • IT System Utilization: A 30% increase in the use of e-management systems among administrative staff, leading to improved efficiency.

# E.3 Budget and cost effectiveness

Please describe the strategy adopted to ensure that the proposed results and objectives will be achieved in the most economical way, and on time. Explain the principles of budget allocation amongst partners. Indicate the arrangements adopted for financial management. What sources of co-funding will be used?(limit 3.000 characters)

The strategy adopted to ensure that the proposed results and objectives are achieved in the most economical and timely manner is based on careful planning, efficient resource allocation, and strong financial oversight. The following key principles guide the strategy: 1. Efficient Planning and Phased Implementation: The project adopts a phased approach to implementation, ensuring that each phase builds on the outcomes of the previous one. This phased approach, combined with continuous monitoring and feedback mechanisms, ensures that activities are completed on time. Each phase will have clearly defined milestones, deadlines, and responsible parties. Regular progress reviews will allow for adjustments to be made as needed, ensuring that the project remains on track. 2. Cost-Effectiveness and Economies of Scale: The project prioritizes the most cost-effective solutions, including leveraging digital tools, sharing resources among partner institutions, and implementing joint training sessions. Bulk purchasing of IT infrastructure and software, where possible, will help achieve economies of scale and reduce costs. By using online tools for communication, training, and meetings, travel costs will be minimized, reducing the overall budget expenditure. 3. Strategic Budget Allocation: The budget is allocated based on the specific needs and roles of each partner institution, ensuring a balanced and fair distribution of funds that aligns with the contribution and responsibilities of each partner. Higher budget allocation is provided to those institutions responsible for key infrastructure developments, such as the establishment of digital labs and the implementation of IT systems. Smaller allocations are reserved for administrative costs and capacity-building activities. 4. Financial Management and Accountability: A central financial management system will be established to ensure transparency and accountability. The lead institution will oversee the financial management of the project, with each partner institution responsible for maintaining financial records and submitting regular financial reports. A dedicated financial officer will be appointed to monitor expenditures and ensure compliance with Erasmus+ guidelines. All partners will follow strict procurement policies to ensure that goods and services are purchased in the most economical way. 5. Co-Funding and In-Kind Contributions: In addition to Erasmus+ funding, partner institutions will contribute through co-funding and in-kind contributions. This includes providing staff time, facilities, and existing equipment where possible. These contributions are critical for the sustainability of the project and will help to reduce dependency on external funding. 6. Contingency Planning: A contingency budget has been allocated to address any unforeseen challenges or additional costs that may arise during the project. This ensures that the project remains resilient and can adapt to unexpected changes without compromising the achievement of its objectives. By following these strategies, the project ensures that resources are used efficiently, deadlines are met, and the results are delivered in a cost-effective and sustainable manner.

If your project involves any "exceptional costs" related to travel, pleasejustify them here. (limit 2.000 characters)

The "exceptional costs" related to travel are justified by the need to facilitate crucial cross-regional cooperation and ensure the successful implementation of project activities. Travel is essential for achieving the project’s objectives, particularly for knowledge exchange, capacity building, and collaboration between partner institutions. The following points explain why these travel-related costs are necessary and justified: 1. International Collaboration and Knowledge Transfer: The project involves multiple universities and institutions from different regions, including the European Union, Serbia, and Turkey. In-person meetings, study visits, and workshops are essential for transferring knowledge, sharing best practices, and ensuring alignment between partners. These activities enable partners to collaborate effectively on curriculum development, digital transformation, and research initiatives, which cannot be fully achieved through virtual means alone. 2. Study Visits and On-Site Assessments: On-site visits to EU partner institutions are critical for Serbian universities to observe advanced IT systems, research labs, and industry-university collaboration models. These visits will provide firsthand exposure to cutting-edge practices and technologies that Serbian partners will implement at their own institutions. The costs associated with these visits are necessary for building the capacity of faculty, administrative staff, and researchers. 3. Establishing Laboratories and Infrastructure: Setting up digital transformation laboratories and implementing modern IT infrastructure requires coordinated efforts between partners. Travel for expert teams to provide hands-on support, training, and oversight during the installation and integration of these technologies is crucial to ensure their successful deployment. 4. Building Long-Term Partnerships: Face-to-face interactions are vital for strengthening long-term partnerships between the participating institutions. These relationships form the foundation for future joint research projects, exchange programs, and continued collaboration beyond the project’s duration. Given these critical needs, the exceptional travel costs are an essential investment in the success of the project. They are justified to ensure effective cooperation, knowledge transfer, and the achievement of high-impact, sustainable outcomes.

Please justify the equipment costs for each Partner Country Institution:

- why the Partner Countryinstitutions need themfor the implementation of the project;

- their relations with the content to be developed and the specific activities to be implemented) and

- the estimated timeframe for their purchase as well asthe estimated place where they will be located (limit 3.000 characters)

The equipment costs for each Partner Country Institution are essential to ensure the successful implementation of the project’s objectives, which focus on modernizing IT infrastructure, establishing digital transformation laboratories, and enhancing teaching and research capacities. Below is a justification for these equipment costs, their relevance to the project’s content, and the estimated timeframe and location for installation: Državni Univerzitet u Novom Pazaru Justification: The university requires modern IT infrastructure and lab equipment for its Computer Technologies and Economics programs. AI, machine learning, and blockchain labs will be established to support hands-on learning and research, contributing to a digitally-driven curriculum. Relation to Activities: Servers, AI workstations, and blockchain nodes are necessary for the new curriculum and research labs, allowing students and faculty to work on advanced tech projects. Timeframe & Location: Equipment will be purchased within the first 6 months and installed in the digital transformation lab on campus. Univerzitet u Nišu (Faculty of Electronic Engineering) Justification: The university aims to enhance its engineering programs with AI, DevOps, and cloud computing labs. Equipment costs will cover servers, networking devices, and high-performance computing (HPC) systems for research and teaching. Relation to Activities: These labs are crucial for modernizing the curriculum and supporting both practical learning and research, ensuring students acquire relevant skills for the job market. Timeframe & Location: Equipment will be acquired in the first year and set up in AI and cloud computing labs at the Faculty of Electronic Engineering. Elektrotehnički Fakultet u Beogradu (University of Belgrade - Faculty of Electrical Engineering) Justification: Advanced IT infrastructure is needed to support the faculty’s focus on AI, blockchain, and machine learning. This equipment will be used to update the curriculum and support research projects. Relation to Activities: Servers, AI training machines, and blockchain platforms will enhance teaching and facilitate university-industry collaborations. Timeframe & Location: The equipment will be installed by year-end in AI and blockchain labs under development within the faculty. Univerzitet u Kragujevcu (Faculty of Mechanical Engineering) Justification: The faculty requires equipment for automation, AI, and digital transformation projects. The costs are necessary to establish research labs where students and faculty can work on cutting-edge industry-related projects. Relation to Activities: This equipment is critical for implementing advanced engineering courses and aligning internships with industry needs. Timeframe & Location: Equipment will be purchased by month 9 and installed in AI and automation labs. Ekonomski Fakultet u Beogradu (University of Belgrade - Faculty of Economics) Justification: The faculty requires IT infrastructure upgrades for courses in fintech, blockchain, and digital business transformation. Equipment such as blockchain servers, fintech software, and cloud-based platforms are essential for these tracks.

(Please add Partner Countries as appropriate)

Please complete the following Logical Framework Matrix:

☐

# E.4 Logical Framework Matrix – LFM

| Wider Objective:☒ What is the general objective, to which the project will contribute? - • Poboljšanje uslova i rada vezanog za Poslovnu Informatiku I Softversko Inženjerstvo, gde ćemo prvobitno uvesti programe vezane za poboljšani e-menadžment, savremenu stručnu praksu I nove laboratorije. | Indicators of progress: What are the key indicators related to the wider objective? 30% više se koristi onlajn prijava Sistema od proslog - 100% povećano korišćenje onlajn platformi od administracije | How indicators will be measured: What are the sources of information on these indicators? Statisticki dokumenti Državna statistika - Lokalna statistika |  |  |
| --- | --- | --- | --- | --- |
| Specific Project Objective/s: What are the specific objectives, which the project shall achieve? 1. Analiza trenutnog stanja, potreba i dobrih praksi 2. Razvoj modernih IT tehnologija na srpskim univerzitetima 3. Osavremenjivanje stručnih praksi - 4. Formiranje laboratorije za digitalnu transformaciju | Indicators of progress: What are the quantitative and qualitative indicators showing whether and to what extent the project’s specific objectives are achieved? Razvijena nova platforma za e- management Instalirana na 6 institucija Razvijen novi plan i program za stručne prakse vezane za AI, Machine Learning i BlockChain tehnologije, primenjen u 6 institucija - Formirane nove laboratorije za AI i Machine Learning, digitalnu transformaciju i DevOps, formirane u 6 institucija | How indicators will be measured: What are the sources of information that exist and can be collected? What are the methods required to get this information? Odluka univerziteta o razvoju I implementaciji e-menadžment platforme Odluka univerziteta o osavremenjivanju I implementaciji nove stručne prakse - Odluka univerziteta o formiranju novih laboratorija | Assumptions & risks - What are the factors and conditions not under the direct control of the project, which are necessary to achieve these objectives? What risks have to be considered? | How the risks will be mitigated: |
| Outputs (tangible) and Outcomes (intangible): Please provide the list of concrete DELIVERABLES - outputs/outcomes (grouped in Workpackages), leading to the specific objective/s.: 1. Analiza trenutnog stanja, potreba i dobrih praksi 1.1 Procena potreba i studija izvodljivosti e-menadžment Sistema 1.1.1 Analiza potreba za razvoj novog IT sistema. 1.1.2 Razvijen izveštaj o potrebama za razvoj IT sistema. 1.2 Dizajn i arhitektura rešenja 1.2.1 Odabrana odgovarajuća blockchain tehnologiju 1.2.2 Razvijen dizajn sistemske arhitekture i interfejsa. 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima 1.3.1 Analiza broja i vrsti praksi koje se trenutno nude. 1.3.2 Analiza zadovoljstva studenata I firmi postojećim ssistemom praksi 1.3.3 Analiza postojećih partnerstva sa kompanijama i procena njihove efikasnosti. 1.3.4 Sveukupna analiza stanja stručne prakse na univerzitetu 1.4 Analiza potreba privrede 1.4.1 Identifikacija mogućih partnera u industriji 1.4.2 Izveštaj o mogućnostima novih partnera 1.4.3 Analiza stručnih praksi koje nude mala I srednja preduzeća 1.5 Primeri dobre prakse u implementaciji laboratorija I centara 1.5.1 Detaljni okvir koji određuje kriterijume I metrike analize 1.5.2 Kompilacija skupljenih izveštaja, publikacija I studija slučajeva iz izabranih univerziteta 1.5.3 Skupljeni podaci iz intervjua I anketa sa partnerima u izabranim EU univerzitetima 1.5.4 Snimci I transkripti iz virtuelnih poseta I sesija observacije 1.5.5 Sveobuhvatni izveštaj koji detaljno opisuje najbolje prakse, inovativne pristupe I preporuke 2. Razvoj modernih IT tehnologija na srpskim univerzitetima 2.1 Razvoj prototipa 2.1.1 Funkcionalan MVP; Dokumentacija o funkcionalnostima MVP-a. 2.1.2 Izveštaj o rezultatima početnog testiranja korisnika; Zbirka povratnih informacija korisnika. 2.2 Strategija implementacije 2.2.1 Dokumentacija o razvijenom kompletnom sistemu; Izveštaj o završetku razvoja. 2.2.2 Izveštaj o integraciji sa postojećim univerzitetskim sistemima; Dokumentacija o interfejsima i protokolima integracije. 2.3 Ispitivanje i osiguranje kvaliteta 2.3.1 Izveštaj o rezul | Indicators of progress: What are the indicators to measure whether and to what extent the project achieves the envisaged results and effects? 1.1.1 Odrađeno 5 intervjua, organizovano 5 fokus grupa i 1 analiza potreba je izvršena 1.2.1 Definisani zahtevi, 1 kriterijum evaluacije, 1 tehnička analiza I 6 pilot projekata 1.3.1 1 analiza kroz 5 intervjua 1.3.2 Odrađeno 5 intervjua I 1 analiza dobijenih podataka 1.3.3 1 izveštaj o efikasnosti postojećih stažiranja sa kompanijama, 1 izveštaj o broju I tipu stažiranja dostupno studentima I 1 analiza trenutnog procesa povezivanja studenata 1.3.4 1 zapis o trenutnim partnerstvima, 1 izveštaj o dostupnosti stažiranja i 1 zapis preporuka za poboljšanje veza između studenata I stažiranja 1.3.1 1 analiza kroz 5 intervjua 1.3.2 Sprovedeno 600 intervjua sa studentima, 20 kompanija 1.3.3 5 intervjua sa univerzitetima i 20 sa kompanijama 1.3.4 1 analiza sveobuhvatnog stanja 1.4.1 20 sastanaka sa stručnjacima iz privrede 1.4.2 20 intervjua o potrebama privrede 1.4.3 20 istraživanja trenutnih tipova stažiranja sa 20 intervjua sa kompanijama 1.5.1 Razvoj I odobrenje razvojnog okvira 1.5.2 6 izveštaja, publikacije, studija slučajeva, 60 transkripta sa intervjua I anketa 1.5.3 6 virtuelnih poseta I sesija observacije 1.5.4 3 najboljih praksi I inovativnih pristupa identifikovano u analizi 1.5.5 Završetak I podnošenje sveobuhvatnoh izveštaja 2.1.1 Završetak razvoja MVP-a. 2.1.1 10 funkcionalnosti uključenih u MVP. 2.1.1 Kvalitet i stabilnost MVP-a tokom inicijalnog testiranja. 2.1.2 40 korisnika uključenih u testiranje. 2.1.2 Identifikovani problemi i predlozi za poboljšanje. 2.1.2 85% korisnika koji su zadovoljni MVP-om. 2.2.1 Završetak razvoja kompletnog sistema. 2.2.1 25 funkcionalnosti implementiranih u sistem. 2.2.2 5 uspešnih integracija sa postojećim sistemima. 2.2.2 10 problema tokom integracije i način njihovog rešavanja. 2.3.1 10 sprovedenih testova (sigurnost, performanse, UAT). 2.3.1 8 identifikovanih problema tokom testiranja. 2.3.2 8 rešenih problema. 2.3.2 15 dana potrebno za rešavanje problema. 2.4.1 3 uspešnih pilot instalacija. - 2.4.1 Povr | How indicators will be measured: What are the sources of information on these indicators? 1.1.1 Zapisnici i transkripti intervjua 1.1.1 Zapisnici I transkripti fokus grupa 1.1.1 Povratne informacije učesnika. 1.1.1 Dokumentacija o analizi podataka. 1.2.1 Evaluacioni izveštaji. 1.2.1 Tehnička dokumentacija blockchain tehnologija. 1.2.1 Izveštaji tehničkih i finansijskih stručnjaka 1.2.2 Tehnička dokumentacija. 1.2.2 Povratne informacije zainteresovanih strana. 1.2.2 Revizije i iteracije dizajna. 1.3.1 Zapisnici i transkripti intervjua 1.3.2 Zapisnici i transkripti intervjua 1.3.3 Zapisnici i transkripti intervjua 1.3.4 Postojeći odgovori o stažiranju 1.4.1 Zapisnici sa sastanaka 1.4.2 Zapisnici I transkripti intrevjua 1.4.3 Postojeći ugovori o stažiranju 1.5.1 Prihvaćen okvirni dokument 1.5.2 Sažetak I kompilacija skupljenih izveštaja I publikacija 1.5.3 Transkripti, snimci I rezultati anketa od partnera 1.5.4 Snimci I transkripti iz virtuelnih poseta I observacija 1.5.5 Završeni izveštaj I pronalasci I preporuke, podeljene sa partnerima 2.1.1 Razvojna dokumentacija. 2.1.1 Tehnički izveštaji i zapisi o testiranju. 2.1.1 Povratne informacije od timova za razvoj i testiranje. 2.1.2 Testni scenariji i zapisi. 2.1.2 Anketni rezultati i povratne informacije korisnika. 2.1.2 Dokumentacija o iteracijama i poboljšanjima na osnovu testiranja. 2.2.1 Razvojna dokumentacija. 2.2.1 Izveštaji razvojnih timova. 2.2.2 Dokumentacija o integraciji. 2.2.2 Tehnički zapisi o interfejsima i protokolima. 2.3.1 Testni izveštaji. 2.3.1 Zapisi o sigurnosnim, performansnim i UAT testovima. 2.3.2 Dokumentacija o problemima i njihovom rešavanju. 2.3.2 Povratne informacije timova za testiranje. 2.4.1 Izveštaji o pilot raspoređivanju. 2.4.1 Povratne informacije korisnika tokom pilot faze. 2.4.2 Dokumentacija o implementaciji. 2.4.2 Izveštaji timova za uvođenje. 2.5.1 Izveštaji o performansama sistema. 2.5.1 Analitički alati i softver za praćenje. 2.5.2 Dokumentacija o ažuriranjima. 2.5.2 Povratne informacije korisnika i ankete. - 2.6.1 Izveštaji o usklađenosti i sigu | Assumptions & risks What external factors and conditions must be realised to obtain the expected outcomes and results on schedule? 1.1.1 Ključni učesnici možda neće biti dovoljno angažovani ili dostupni, što može uticati na kvalitet prikupljenih informacija. Moguće je pogrešno interpretirati podatke iz intervjua i fokus grupa zbog subjektivnosti ili lošeg dizajna upitnika. Niska kvaliteta podataka ako su intervjui i fokus grupe loše organizovani ili sprovedeni. 1.1.2 Tehnološka i finansijska studija može sadržavati nerealne procene troškova ili nepredviđene troškove. Tehnološki aspekti studije mogu pokazati da predloženo rešenje nije izvodljivo ili nije kompatibilno sa postojećom infrastrukturom. 1.2.1. Nedefinisani ili nepotpuni zahtevi mogu dovesti do grešaka u dizajnu i funkcionalnosti sistema. Odabrane tehnologije možda neće zadovoljiti potrebe projekta ili mogu biti zastarele. Problemi u pilot projektima mogu otkriti značajne nedostatke u dizajnu koji nisu ranije prepoznati. 1.2.2 Kriterijumi evaluacije mogu biti neadekvatni za potrebe projekta, što može rezultirati lošim odlukama. Izveštaji mogu sadržavati preporuke koje nisu realne ili izvodljive u kontekstu projekta. 1.3.1 Podaci prikupljeni iz intervjua mogu biti nepotpuni ili netačni. 1.3.2 Greške u analizi podataka mogu dovesti do pogrešnih zaključaka o trenutnom stanju. 1.3.3. Prekomerna količina informacija može otežati analizu i donošenje korisnih zaključaka. Neadekvatna evaluacija postojećih partnerstava može rezultirati lošim preporukama. 1.3.4. Izveštaj može biti nepovezan ili teško razumljiv ako podaci nisu dobro organizovani. 1.4.1 Mogući partneri možda neće biti zainteresovani za učestvovanje u intervjuima ili sastancima. Problemi sa organizovanjem virtuelnih sastanaka mogu uticati na kvalitet prikupljenih informacija. 1.4.2. Izveštaj može sadržavati preporuke koje nisu realne ili izvodljive za povezivanje sa novim partnerima. 1.4.3 Informacije dobijene od malih i srednjih preduzeća mogu biti ograničene ili neodgovarajuće. 1.5.1. Ako kriterijumi za analizu nisu sveobuhvatni, može doći do propuštanja važnih aspekata. - 1.5.2. P | How the risks will be mitigated: |
| Activities: What are the key activities to be carried out (grouped in Workpackages) and in what sequence in order to produce the expected results? 1. Analiza trenutnog stanja, potreba i dobrih praksi 1.1 Procena potreba i studija izvodljivosti e-menadžment Sistema 1.1.1 Sprovođenje intervjua, formiranje fokus grupa I analiza podataka sa zainteresovanim stranama 1.1.2 Odrađena je tehnološka i finansijska studija izvodljivosti 1.2 Dizajn i arhitektura rešenja 1.2.1 Definicija zahteva, kriterijuma evaluacije, tehnička analiza predloženih tehnologija i pilot projekti 1.2.2 Priprema izveštaja o evaluaciji I izveštaja o odabiru tehnologije 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima 1.3.1 Sprovođenje intervjua o broju i vrstama praksi koje se trenutno nude. 1.3.2 Sprovođenje intervjua i analiza dobijenih podataka 1.3.3 Intervjui o efikasnosti postojećih partnerstva sa kompanijama, broju i tipu stažiranja dostupnih studentima i analiza trenutnog procesa povezivanja studenata sa mogućim stažiranjima. 1.3.4 Uvezivanje svih rezultata u jedan zajednički izveštaj 1.4 Analiza potreba privrede 1.4.1 Sprovođenje intervjua I virtuelnih sastanaka sa mogućim partnerima u industriji 1.4.2 Formiranje izveštaja o mogućnostima novih partnera 1.4.3 Sastanci i intervjui sa malim i srednjim preduzećima 1.5 Primeri dobre prakse u implementaciji laboratorija I centara 1.5.1 Formiranje okvira za analizu dobrih praksi, ukljućuljući kriterijume i metrike 1.5.2 Prikupljanje postojećih izveštaja, publikacija I slučajeva korišćenja o laboratorijama i centrima iz ovih univerziteta 1.5.3 Sprovođenje intervjua I anketa sa fakultetima, administratorima I menadžerima laboratorija u izabranim EU univerzitetima 1.5.4 Organizovanje virtuelnih poseta I sesija observacije za razumevanje operacije laboratorija I centara 1.5.5 Analiza skupljenih podataka radi identifikacije najboljih praksi, inovativnih pristupa I uspešnih strategija - 1.5.6 Spremljen sveobuhvatni izveštaj koji sažeto opisuje pronalaske I daje preporuke za implementiranje sličnih praksi u srpskim univerz | ### Inputs: What inputs are required to implement these activities, e.g. staff time, equipment, mobilities, publications etc.? |  | Assumptions ¦& risks What pre-conditions are required before the project starts? What conditions outside the project’s direct control have to be present for the implementation of the planned activities? | How the risks will be mitigated: |

Please complete the following work plan.☒

# E.5 Work Plan

On the following pages, please provide your work plan for each year of the proposed project

- Please use the model provided below.

- Please complete a one-page work plan for each project year.

- For each year of your proposal, please complete a work plan indicating the deadlines for each outcome and the period and location in which your activities will take place.

- If needed, please insert additional rows into the work plan tables.

- The same reference and sub-reference numbers as used in the logical framework matrix must be assigned to each outcome and related activities.

Examples:

Activity carried out in the Programme Country:         = (E.g. activity in France for two weeks in the first month of the project 2= under M1)

Activity carried out in the Partner Country (ies):        X (E.g., activity in Tunisia for three weeks in the second month of the project: 3X under M2)

# WORKPLAN for project year 1☒

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1 Procena potreba i studija izvodljivosti e-menadžment sistema | 20 | X | X | X | X |  | X |  |  |  |  |  |  |
|  | 1.2 Dizajn i arhitektura rešenja | 24 | X | X | X | X | X | X |  |  |  |  |  |  |
|  | 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima | 16 | X | X | X |  |  | X |  |  |  |  |  |  |
|  | 1.4 Analiza potreba privrede | 16 | X | X | X |  |  | X |  |  |  |  |  |  |
|  | 1.5 Primeri dobre prakse u implementaciji laboratorija I centara | 12 | X | X |  |  |  | X |  |  |  |  |  |  |
|  | 2.1 Razvoj prototipa | 24 |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 3.1 Studijske posete | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 3.2 Organizacija bisnis simulacija | 24 |  |  | X | X | X | X | X | X |  |  |  |  |
|  | 3.3 Panel Diskusije AI i Machine learning | 8 |  |  |  |  |  |  |  |  | X | X |  |  |
|  | 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju | 8 |  |  |  |  |  |  |  |  | X | X |  |  |
|  | 5.1 Defining third mission metrics | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 5.2 Internal monitoring | 16 |  |  | X | X | X | X |  |  |  |  |  |  |
|  | 5.3 Monitoring of defined metrics | 24 |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 6.1 Design of project visual identity | 24 | X | X | X | X | X | X |  |  |  |  |  |  |
|  | 6.2 Design/upgrade of web-site | 24 |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 7.1 Overall project managementt | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.2 Local management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.3 SC meetings | 48 | X | X | X | X | X | X | X | X | X | X | X | X |

# WORKPLAN for project year 2☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2 Strategija implementacije |  | X | X | X | X | X | X |  |  |  |  |  |  |
|  | 2.3 Ispitivanje i osiguranje kvaliteta |  |  |  | X | X | X | X | X | X |  |  |  |  |
|  | 2.4 Implementacija i uvođenje |  |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 4.2 Conduct a Needs Assessment | 12 | X | X | X |  |  |  |  |  |  |  |  |  |
|  | 4.3 Develop a Detailed Plan | 12 |  |  | X | X | X |  |  |  |  |  |  |  |
|  | 4.4 Procure Equipment and Software | 12 |  |  |  |  | X | X | X |  |  |  |  |  |
|  | 4.5 Prepare the Physical Space | 12 |  |  |  |  |  |  | X | X | X |  |  |  |
|  | 4.6 Install Equipment and Software | 4 |  |  |  |  |  |  |  |  |  | X |  |  |
|  | 4.7 Establish Cloud Infrastructure | 8 |  |  |  |  |  |  |  |  |  |  | X | X |
|  | 5.3 Monitoring of defined metrics | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 6.3 Defining institutional policies to promote third mission | 16 | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 6.4 Good practices on Tech. transfer and Innovation | 8 |  |  |  |  | X | X |  |  |  |  |  |  |
|  | 6.5 10 Info days and other events | 12 |  |  |  |  |  |  | X | X | X |  |  |  |
|  | 6.6 Final Conference on university third mission | 4 |  |  |  |  |  |  |  |  |  | X |  |  |
|  | 7.1 Overall project management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.2 Local management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.3 SC meetings | 48 | X | X | X | X | X | X | X | X | X | X | X | X |

# WORKPLAN for project year 3☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.5 Evaluacija i kontinuirano poboljšanje | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 2.6 Usklađenost i sigurnost | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 2.7 Održivost i skalabilnost | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 4.8 Conduct a Soft Launch | 8 | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 4.9 Organize an Official Launch Event | 8 |  |  | X | X |  |  |  |  |  |  |  |  |
|  | 5.3 Monitoring of defined metrics | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.1 Overall project management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.2 Local management | 48 | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 7.3 SC meetings | 48 | X | X | X | X | X | X | X | X | X | X | X | X |

Please complete the information on each work package for your project

# E.6 Work packages

Please enter the different project activities you intend to carry out in your project. Make sure that the information in this section is consistent with the project Logical Framework Matrix.

| Work package type and ref.nr ☒ | PREPARATION |  |  | 1 |
| --- | --- | --- | --- | --- |
| Title | Analiza trenutnog stanja, potreba i dobrih praksi |  |  |  |
| Related assumptions and risks | 1.1.1 Ključni učesnici možda neće biti dovoljno angažovani ili dostupni, što može uticati na kvalitet prikupljenih informacija. Moguće je pogrešno interpretirati podatke iz intervjua i fokus grupa zbog subjektivnosti ili lošeg dizajna upitnika. Niska kvaliteta podataka ako su intervjui i fokus grupe loše organizovani ili sprovedeni. 1.1.2 Tehnološka i finansijska studija može sadržavati nerealne procene troškova ili nepredviđene troškove. Tehnološki aspekti studije mogu pokazati da predloženo rešenje nije izvodljivo ili nije kompatibilno sa postojećom infrastrukturom. 1.2.1. Nedefinisani ili nepotpuni zahtevi mogu dovesti do grešaka u dizajnu i funkcionalnosti sistema. Odabrane tehnologije možda neće zadovoljiti potrebe projekta ili mogu biti zastarele. Problemi u pilot projektima mogu otkriti značajne nedostatke u dizajnu koji nisu ranije prepoznati. 1.2.2 Kriterijumi evaluacije mogu biti neadekvatni za potrebe projekta, što može rezultirati lošim odlukama. Izveštaji mogu sadržavati preporuke koje nisu realne ili izvodljive u kontekstu projekta. 1.3.1 Podaci prikupljeni iz intervjua mogu biti nepotpuni ili netačni. 1.3.2 Greške u analizi podataka mogu dovesti do pogrešnih zaključaka o trenutnom stanju. 1.3.3. Prekomerna količina informacija može otežati analizu i donošenje korisnih zaključaka. Neadekvatna evaluacija postojećih partnerstava može rezultirati lošim preporukama. 1.3.4. Izveštaj može biti nepovezan ili teško razumljiv ako podaci nisu dobro organizovani. 1.4.1 Mogući partneri možda neće biti zainteresovani za učestvovanje u intervjuima ili sastancima. Problemi sa organizovanjem virtuelnih sastanaka mogu uticati na kvalitet prikupljenih informacija. 1.4.2. Izveštaj može sadržavati preporuke koje nisu realne ili izvodljive za povezivanje sa novim partnerima. 1.4.3 Informacije dobijene od malih i srednjih preduzeća mogu biti ograničene ili neodgovarajuće. 1.5.1. Ako kriterijumi za analizu nisu sveobuhvatni, može doći do propuštanja važnih aspekata. 1.5.2. Prikupljeni izveštaji i publikacije mogu biti zastareli ili neadekvatni za trenutne potrebe. 1.5.3. Mogući problemi u prikupljanju relevantnih podataka ili nepristupačnost ključnih informacija. 1.5.4. Problemi sa tehnologijom mogu otežati virtuelne posete i sesije observacije. 1.5.5. Moguće greške u analizi podataka mogu dovesti do pogrešnih zaključaka o najboljim praksama. 1.5.6. Izveštaj može biti nejasan ili nepregledan, što otežava implementaciju preporuka. |  |  |  |
| Description |  |  |  |  |
| Tasks | 1.1 Procena potreba i studija izvodljivosti e-menadžment sistema 1.2 Dizajn i arhitektura rešenja 1.3. Analiza postojećeg stanja stručne prakse na univerzitetima 1.4 Analiza potreba privrede 1.5 Primeri dobre prakse u implementaciji laboratorija I centara |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation | DUNP |  |  |  |
| Participating Organisation | All Partners |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Procena potreba i studija izvodljivosti e-menadžment sistema |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | X Event x Report X Service/Product |  |
|  | Description | Act. 1.1.1 first activity of the project is to establish the needs for the development of a new IT system at the partner universities. This process will be conducted through interviews and focus groups over one month. The planning phase involves identifying relevant stakeholders, defining the objectives of the discussions, and developing a structured set of questions to guide the sessions. In the recruitment phase, a diverse group of participants from each partner university will be selected to provide a comprehensive understanding of the IT needs. Sessions will be scheduled at convenient times, and formal invitations will be sent to the selected participants, detailing the purpose, time, and location of the meetings. During the execution phase, focus groups and interviews will be conducted. Facilitators will ensure all participants have the opportunity to speak, and sessions will be recorded for accurate data analysis. Transcriptions and detailed notes will be used to capture the discussions. In the data analysis phase, the recordings from the focus groups and interviews will be transcribed, and common themes, issues, and requirements will be identified. A summary report will be created to highlight the key findings and insights gathered from the sessions. Act.1.1.2. The final reporting phase will involve drafting a omprehensive report detailing the identified needs and equirements for the new IT system. The draft report will be reviewed by key stakeholders, feedback will be incorporated, and a final report will be produced. The expected deliverable is a needs assessment report that provides a clear understanding of the current IT infrastructure issues and specific needs of the partner universities. This will enable informed decision-making and enhance collaboration among the universities. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff X☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | XNational ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Dizajn i arhitektura rešenja |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act 1.2.1 The second activity of the project is to select the appropriate blockchain technology for the e-management system, to be completed over one month. The process begins with defining the specific requirements for the blockchain technology, such as security and scalability, followed by thorough research on available options. Next, a set of evaluation criteria is developed to assess the technologies, focusing on factors like security features, performance, cost, and ease of integration. From the initial research, a shortlist of the most suitable blockchain technologies is created for further evaluation. In the assessment phase, a detailed technical analysis of each shortlisted technology is conducted, including security assessments and performance benchmarks. Blockchain experts are consulted for additional insights and recommendations. Pilot projects are then set up to test the shortlisted technologies in a controlled environment, with feedback collected from technical teams and stakeholders on their performance and usability. Act. 1.2.2 Finally, the data and feedback from the pilot tests are analyzed to determine the strengths and weaknesses of each technology. A final decision is made on the most appropriate blockchain technology based on the evaluation criteria and pilot test results. The deliverables include an evaluation report and a selection report, with expected outcomes being an informed decision on the blockchain technology and clear documentation of the selection process. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Analiza postojećeg stanja stručne prakse na univerzitetima |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act. 1.3.1 The third activity involves gathering and analyzing data about the number and types of practices available in national universities, to be completed in two months. The process begins with defining objectives and creating structured questionnaires and interview guides to collect relevant data from students and partner organizations. Act. 1.3.2 Next, students from various universities and several companies are selected , ensuring a diverse and representative sample. Interviews are then scheduled and conducted, with all sessions recorded or detailed notes taken to capture the information accurately. Supplementary data from university records and internship databases is also collected to enhance the findings. Act. 1.3.3 For the analysis of partnerships and internships in the third activity, the deliverables include a detailed report on the effectiveness of existing partnerships with companies, a report on the number and types of internships available to students, and an assessment of the current processes for matching students with internships. The outputs consist of raw data collected from interviews with students and partner companies, transcriptions or detailed notes from these interviews, and a summary of key findings from the analysis of this data. Act 1.3.4 The results are a clearer understanding of the effectiveness of current partnerships, insights into the availability of internships and any gaps, and recommendations for improving the processes for connecting students with internships. This approach ensures thorough analysis and actionable insights for better partnerships and enhanced internship opportunities for students. Act. 1.3.5 In the data analysis phase, the recorded interviews are transcribed, and both qualitative and quantitative methods are used to identify common themes and insights. A summary report is created to highlight key findings on the number and types of practices available. The final reporting phase involves compiling the findings into a comprehensive report, which is reviewed by stakeholders for feedback and revisions before being finalized. The deliverables include the data collection instruments and a comprehensive report summarizing the findings. The expected results are a detailed understanding of the current state of internship and practice opportunities in national universities and the identification of gaps and opportunities for improvement. This systematic approach ensures accurate data collection and valuable insights into the available practices. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Analiza potreba privrede za stažiranjima |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act. 1.4.1 The fourth activity involves conducting virtual meetings with industry partners and exploring internships offered by small and medium businesses. This task, scheduled to last one month, begins with identifying potential industry partners and defining the objectives of the virtual meetings and interviews. Structured questions are then developed to guide these sessions. In the recruitment phase, key representatives from the identified businesses are selected to participate, and meetings are scheduled at convenient times. Formal invitations are sent out, detailing the purpose, time, and format of the meetings. During the execution phase, virtual meetings are facilitated using video conferencing tools, ensuring all participants have the opportunity to speak, and recordings are made for accurate data analysis. Individual interviews with industry representatives are also conducted, with detailed notes taken. Act. 1.4.2 The data analysis phase involves transcribing the recordings from the meetings and interviews, identifying common themes and opportunities, and summarizing the findings in a report. In the reporting phase, a comprehensive report is drafted, reviewed by stakeholders for feedback, and finalized. Act. 1.4.3 The deliverables include meeting agendas and structured questions, as well as a comprehensive report summarizing the findings. The expected outputs are recorded sessions and a summary of the findings. The results of this activity will be an enhanced understanding of current internship opportunities offered by small and medium businesses, along with identified areas for potential collaboration and improvement. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Analiza trenutnog stanja kurikuluma |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | The fifth activity involves analyzing the current state of the curriculum over three months. This begins with defining the objectives of the analysis, such as identifying strengths and weaknesses and aligning the curriculum with industry standards. Act. 1.5.1. Surveys are then developed and distributed to faculty, students, and industry partners, with responses collected and analyzed. Act.1.5.2. Next, relevant academic literature, industry reports, and case studies are gathered to identify current trends and academic standards. Act. 1.5.3. For the analysis of relevant literature, industry reports, and case studies in the fifth activity, the deliverables include a literature review report summarizing the findings, an annotated bibliography detailing key insights and trends, and a trend analysis summary highlighting best practices in Software Engineering and Business Informatics. The outputs consist of the collected documents, detailed analysis notes from the reviewed materials, and a thematic analysis identifying common themes and patterns. The results provide a thorough understanding of current trends and best practices, insights into gaps between academic practices and industry needs, and data-driven recommendations for curriculum improvements. This approach ensures comprehensive analysis and valuable insights to inform the curriculum enhancement process. Act. 1.5.4. Student performance data, including grades, graduation rates, and employment outcomes, are analyzed to pinpoint areas of strength and weakness. Act. 1.5.6. The current curriculum is then thoroughly reviewed to identify gaps and outdated materials. Act, 1,5,7 A parallel analysis compares the existing curriculum with industry standards to find misalignments and areas for improvement. Act. 1.5.8. The findings from all these phases are compiled into a comprehensive report. This draft report is reviewed by stakeholders, revised based on feedback, and finalized with actionable recommendations for curriculum improvements. The deliverables include the survey instruments and a detailed report summarizing the findings. The outputs consist of collected data, literature reviews, and analysis summaries. The results provide a thorough understanding of the curriculum’s strengths and weaknesses, alignment with industry standards, and recommendations for improvement. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Primeri dobre prakse u implementaciji laboratorija I centara |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | Act 1.6.1 Create a detailed research framework that outlines the key criteria and metrics for analyzing good practices. This includes defining the scope of the analysis, the specific areas of focus (such as AI labs, Cloud Computing labs, and digital learning centers), and the methodologies to be used for data collection and analysis. Act 1.6.2 Gather existing reports, publications, and case studies related to the laboratories and centers at the selected universities. This involves accessing academic databases, university websites, and industry publications to compile relevant documents that provide insights into the setup, operations, and achievements of these facilities. Act 1.6.3 Design structured interview questions and survey instruments aimed at gathering in-depth information from faculty, administrators, and lab managers at the selected EU universities. Conduct virtual interviews and distribute surveys to collect qualitative and quantitative data on best practices, challenges, and innovative approaches used in their laboratories and centers. Act 1.6.4 Organize and conduct virtual tours of the laboratories and centers at the partner universities. Use video conferencing tools to observe the facilities in operation, noting the layout, equipment, and processes. Record observations and gather additional insights from live demonstrations and interactions with on-site personnel. Act 1.6.5 Analyze the data collected from desk research, interviews, surveys, and virtual tours. Identify common themes, successful strategies, and innovative practices. Use qualitative analysis methods to draw meaningful conclusions and highlight best practices that can be replicated or adapted for Serbian universities. Act 1.6.6 Compile all findings into a comprehensive report. The report should summarize the best practices identified, provide detailed case studies from each partner university, and offer recommendations for implementing similar practices in Serbian universities. Review the draft report with key stakeholders, incorporate their feedback, and finalize the document for dissemination. This systematic approach ensures a thorough and detailed analysis of good practices in EU university laboratories and centers, providing actionable insights for enhancing similar facilities in Serbian universities. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☐ | DEVELOPMENT |  |  | 2 |
| --- | --- | --- | --- | --- |
| Title | Razvoj modernih IT tehnologija na srpskim univerzitetima |  |  |  |
| Related assumptions and risks | 2.1.1 Rizik od proklizavanja opsega: Nekontrolisane promjene ili kontinuirano širenje MVP funkcija izvan početnog plana. Tehnički izazovi: Problemi sa integracijom novih tehnologija ili postizanjem potrebne funkcionalnosti. Ograničenja resursa: Ograničena dostupnost kvalifikovanih programera ili finansijskih resursa koji utiču na razvoj. Prekoračenje vremena: kašnjenja u ispunjavanju razvojnih prekretnica zbog nepredviđenih tehničkih složenosti. 2.1.2. Neadekvatne povratne informacije korisnika: Korisnici možda neće dati sveobuhvatne povratne informacije, što otežava identifikaciju kritičnih problema. Pristranost uzorka: Povratne informacije možda neće biti reprezentativne za veću bazu korisnika ako testna grupa nije raznolika. Tehnički problemi tokom testiranja: Greške ili problemi sa performansama otkriveni tokom testiranja mogu uticati na zadovoljstvo korisnika. Pogrešno tumačenje povratnih informacija: Netačna analiza povratnih informacija korisnika koja dovodi do neprikladnih prilagođavanja MVP-a. 2.2.1. Problemi integracije: Problemi integracije novih komponenti sistema sa postojećom infrastrukturom. Prekoračenje budžeta: Troškovi koji premašuju budžet zbog nepredviđenih tehničkih izazova ili promjena obima. Kašnjenja u razvoju: Kašnjenja zbog tehničkih poteškoća, ograničenja resursa ili problema upravljanja projektom. Neadekvatno testiranje: Nedovoljno testiranje prije konačnog izdanja, što dovodi do potencijalnih kvarova sistema. 2.2.2. Problemi kompatibilnosti: Nekompatibilnost između novog sistema i postojećih sistema što dovodi do grešaka u integraciji. Problemi migracije podataka: Izazovi u prijenosu i usklađivanju podataka između sistema. Prekid postojećih usluga: Integracija može privremeno poremetiti postojeće usluge ili sisteme. Otpor promjenama: Zainteresovane strane ili korisnici mogu se oduprijeti integraciji novog sistema, što utiče na usvajanje. 2.3.1. Neadekvatna pokrivenost testiranjem: Određeni problemi možda neće biti otkriveni ako je opseg testiranja ograničen. Sigurnosne ranjivosti: Mogu se previdjeti potencijalne sigurnosne propuste, što može dovesti do kršenja podataka ili napada. Uska grla u performansama: Problemi sa performansama možda neće biti identifikovani sve dok sistem nije u uslovima stvarnog sveta. Problemi s prihvaćanjem korisnika: Korisnici mogu odbiti sistem zbog loše upotrebljivosti ili nezadovoljenih potreba. 2.3.2. Odgođeni popravci: Pravovremeno rješavanje identificiranih problema može biti odgođeno, što utiče na ukupni vremenski okvir projekta. Neadekvatno rješavanje problema: popravci možda neće riješiti osnovni uzrok problema, što dovodi do problema koji se ponavljaju. Ograničenja resursa: Ograničeni resursi za efikasno rješavanje svih identificiranih problema. Nepotpuno testiranje nakon popravka: Problemi možda neće biti u potpunosti riješeni ako testiranje nakon popravki nije dovoljno. 2.4.1. Tehnički kvarovi: Pilot instalacije mogu naići na tehničke probleme koji mogu uticati na evaluaciju. Prihvatanje korisnika: Korisnicima može biti da je pilot sistem izazovan za korištenje ili da ne zadovoljava njihove potrebe. Nedovoljne povratne informacije o pilot fazi: Ograničene ili nereprezentativne povratne informacije iz pilot faze mogu uticati na poboljšanja. Problemi integracije: Izazovi integracije pilot sistema sa postojećim univerzitetskim sistemima. 2.4.2. Kašnjenja u implementaciji: Kašnjenja u uvođenju sistema u sve institucije zbog tehničkih ili logističkih problema. Ograničenja resursa: Ograničeni resursi ili podrška koji utječu na proces instalacije. Izazovi obuke: Neadekvatna obuka za korisnike dovodi do lošeg usvajanja i korištenja. Tehnička podrška: Nedovoljna tehnička podrška tokom faze uvođenja. 2.5.1. Netačne metrike: metrike koje se koriste za procjenu performansi možda neće tačno odražavati efikasnost sistema ili zadovoljstvo korisnika. Pad performansi: Problemi sa performansama mogu se pojaviti tokom vremena, što utiče na korisničko iskustvo. Problemi sa prikupljanjem podataka: Problemi sa preciznim prikupljanjem i analizom podataka o učinku. Sistem koji ne reaguje: Sistem možda neće raditi kako se očekivalo pod različitim uslovima opterećenja. 2.5.2. Neusklađenost povratnih informacija: Implementirana poboljšanja možda neće biti u skladu s potrebama korisnika ili povratnim informacijama. Izazovi implementacije: Poteškoće u implementaciji poboljšanja zbog tehničkih ili resursnih ograničenja. Nepredviđeni nuspojave: Promene mogu dovesti do novih problema ili negativno uticati na druge aspekte sistema. Nezadovoljstvo korisnika: Kontinuirano nezadovoljstvo uprkos implementiranim poboljšanjima. 2.6.1. Nedostaci usklađenosti: Problemi otkriveni tokom revizija mogu ukazivati ​​na neusklađenost sa propisima. Bezbednosni rizici: Potencijalne bezbednosne ranjivosti mogu biti identifikovane tokom revizija, koje zahtevaju hitnu pažnju. Neuspjesi revizije: Neuspjeh prolaska provjera usklađenosti ili sigurnosnih revizija utiče na kredibilitet projekta. Neadekvatna sanacija: Nedovoljna ili neefikasna sanacija identifikovanih problema usklađenosti ili sigurnosti. 2.6.2 . Odgođena ažuriranja: Sigurnosni protokoli ili dokumentacija o usklađenosti možda neće biti ažurirani na vrijeme. Zastarjele prakse: Kontinuirano korištenje zastarjelih sigurnosnih praksi ili dokumentacije. Previd usklađenosti: Promjene u propisima ili standardima mogu se previdjeti, što utiče na usklađenost. Greške u dokumentaciji: Greške u ažuriranoj dokumentaciji dovode do netačne usklađenosti ili sigurnosnih praksi. 2.7.1. Kašnjenja u održavanju: Kašnjenja u planiranom održavanju koja utiču na performanse ili pouzdanost sistema. Neadekvatno planiranje: Loše definisani rasporedi održavanja dovode do zastoja sistema ili problema sa performansama. Ograničenja resursa: Nedovoljni resursi za redovno održavanje i ažuriranja. Neočekivana potreba za održavanjem: Nepredviđeni problemi koji zahtijevaju dodatne napore u održavanju. 2.7.2. Neusklađenost budućih zahtjeva: Buduće iteracije možda neće biti usklađene s potrebama korisnika ili tehnološkim napretkom. Problemi skalabilnosti: Sistem se možda neće skalirati prema očekivanjima, što dovodi do degradacije performansi pod povećanim opterećenjem. Raspodjela resursa: Izazovi u dodjeli resursa za budući razvoj i iteracije. Promjene na tržištu: Promjene na tržištu ili očekivanja korisnika mogu utjecati na relevantnost budućih iteracija. |  |  |  |
| Description |  |  |  |  |
| Tasks | 2.1 Razvoj prototipa 2.2 Strategija implementacije 2.3 Ispitivanje i osiguranje kvaliteta 2.4 Implementacija i uvođenje 2.5 Evaluacija i kontinuirano poboljšanje 2.6 Usklađenost i sigurnost 2.7 Održivost i skalabilnost |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation | DUNP |  |  |  |
| Participating Organisation | All Serbian Partners |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Razvoj prototipa |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.1.1 Razvijanje minimalno održivog proizvoda (MVP): Start by defining the core functionalities required for the MVP, focusing on essential features that address the primary needs of users. Assemble a development team to design and build the MVP, ensuring it meets the identified requirements. Conduct internal reviews and iterations to refine the MVP before moving to initial testing. 2.1.2 Provođenje početnog testiranja korisnika i prikupljanje povratne informacije: Launch the MVP for a selected group of users, including faculty, students, and IT staff, to test its functionalities. Collect feedback through surveys, interviews, and usage data to identify any issues or areas for improvement. Analyze the feedback to make necessary adjustments and enhancements to the MVP. |  |  |  |
|  | Due date | M12 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Strategija implementacije |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.2.1 Razvijanje kompletanog sistema: Expand the MVP into a complete system by integrating additional features and functionalities based on the feedback received. Ensure that the system is scalable, secure, and user-friendly. Document the development process and create user manuals and training materials to support system adoption. 2.2.2 Integracija sa postojećim univerzitetskim sistemima: Plan and execute the integration of the new system with existing university IT infrastructure. Conduct compatibility tests and resolve any integration issues. Work closely with university IT departments to ensure a smooth and seamless integration process. |  |  |  |
|  | Due date | M18 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Ispitivanje i osiguranje kvaliteta |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.2.1 Razvijanje kompletnog sistema: Expand the MVP into a complete system by integrating additional features and functionalities based on the feedback received. Ensure that the system is scalable, secure, and user-friendly. Document the development process and create user manuals and training materials to support system adoption. 2.2.2 Integracija sa postojećim univerzitetskim sistemima: Plan and execute the integration of the new system with existing university IT infrastructure. Conduct compatibility tests and resolve any integration issues. Work closely with university IT departments to ensure a smooth and seamless integration process. |  |  |  |
|  | Due date | M20 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Implementacija i uvođenje |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.4.1 Instalacija pilot sistema: Roll out the system as a pilot in select departments or faculties to monitor its performance in a real-world environment. Collect feedback from users during the pilot phase to identify any remaining issues or areas for improvement. 2.4.2 Instalacija sistema u svim relevantnim institucijama: Based on the success of the pilot deployment, scale the system implementation to all relevant institutes and departments. Provide training sessions and support to ensure smooth adoption and usage across the university. |  |  |  |
|  | Due date | M24 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Evaluacija i kontinuirano poboljšanje |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.5.1 Praćenje i procena performanse sistema: Continuously monitor the system’s performance using analytics tools and user feedback. Evaluate key performance indicators (KPIs) to assess the system’s effectiveness and identify any areas for further improvement. 2.5.2 Implementacija poboljšanja na osnovu povratnih informacija: Regularly update the system to address any issues and implement improvements based on user feedback. Ensure that updates are well-documented and communicated to all users to maintain transparency and user satisfaction. |  |  |  |
|  | Due date | M30 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Usklađenost i sigurnost |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.6.1 Provera usklađenosti i sigurnosne revizije: Perform regular compliance checks and security audits to ensure the system adheres to regulatory standards and best practices. Document the findings and take corrective actions as necessary. 2.6.2 Ažuriranje sigurnosnih protokola i dokumentacije o usklađenosti po potrebi: Update security protocols and compliance documentation to reflect any changes in regulations or security practices. Ensure that all updates are communicated to relevant stakeholders and incorporated into the system. |  |  |  |
|  | Due date | M31 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.7. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Održivost i skalabilnost |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 2.7.1 Definisanje rasporeda održavanja i ažuriranja: Develop a maintenance and update schedule to ensure the system remains functional and up-to-date. Plan for regular system checks, software updates, and hardware maintenance to prevent any downtime. 2.7.2 Priprema budućih iteracija proizvoda: Design system features and infrastructure that can accommodate future growth and increased demand. Ensure that the system is scalable and flexible to adapt to evolving technological and user requirements. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☐ | DEVELOPMENT |  |  | 3 |
| --- | --- | --- | --- | --- |
| Title | Osavremenjivanje stručnih praksi |  |  |  |
| Related assumptions and risks | 3.1.1.1 Scheduling conflicts with host institutions leading to delays. Difficulty in coordinating visit dates across multiple institutions. Unexpected cancellations or changes by host institutions. 3.1.1.2 Travel and accommodation arrangements not meeting participants' needs. Unexpected travel disruptions (e.g., flight cancellations, transportation strikes). Budget overruns due to unanticipated logistical costs. 3.1.1.3 Insufficient time to prepare high-quality materials. Materials not aligning with the objectives of the visit. Delays in the approval process for materials. 3.1.1.4 Information may become outdated if not regularly updated. Inaccuracies or omissions in the material provided to participants. Low engagement or interest from participants due to poorly designed materials. 3.1.1.5 Overly ambitious agendas that are difficult to adhere to. Last-minute changes to the agenda causing confusion. Lack of alignment between the agenda and participants' learning objectives. 3.1.1.6 Miscommunication or lack of transparency from the host organization. Incomplete or inaccurate background information. Participants not fully understanding the context of the host organization. 3.1.1.7 Educational materials not meeting the learning needs of participants. Delays in the preparation of materials due to resource constraints. Low quality of materials affecting participant engagement and learning outcomes. 3.1.1.8 Key areas of interest may not be available for observation during the visit. Overcrowded or rushed tours reducing the effectiveness of the visit. Participants may miss critical information if the tour is not well-coordinated. 3.1.1.9 Availability issues with key personnel leading to a less impactful presentation. Presentations not aligned with participants' educational and career interests. Technical issues during presentations affecting the delivery of content. 3.1.1.10 Insufficient time allocated for interactive activities, limiting their effectiveness. Low participant engagement during Q&A or hands-on sessions. Technical difficulties during demonstrations or workshops. 3.1.1.11 Lack of participant interest in informal networking sessions. Unstructured sessions leading to limited networking opportunities. Scheduling conflicts reducing attendance at networking events. 3.1.1.12 Differences in practices across institutions making it difficult to draw comparisons. Language barriers or cultural differences impacting the effectiveness of observations. Limited access to key practices due to institutional restrictions. 3.1.1.13 Overbooked or highly attended workshops leading to overcrowded sessions. Misalignment between workshop content and participants' learning needs. Logistical issues such as registration errors or last-minute cancellations. 3.1.1.14 Technical issues such as poor internet connectivity affecting virtual visits. Limited engagement and interaction during online demonstrations. Time zone differences complicating scheduling and participation. 3.2.1 Learning outcomes may be too broad or not measurable. Misalignment between learning outcomes and course objectives. Difficulty in achieving consensus among stakeholders on the outcomes. 3.2.2 Scope creep due to changing requirements or expectations. Inadequate resources to support the full scope of the simulation. Misjudgment of the complexity of the simulation leading to overextension. 3.2.3 The scenario may not be relevant or realistic for participants. Insufficient detail in the scenario leading to confusion or disengagement. Failure to incorporate key learning objectives into the scenario. 3.2.4 The storyline may not capture participant interest or engagement. Inconsistencies or logical gaps in the storyline. Delays in storyline development affecting the simulation timeline. 3.2.5 Difficulty in finding qualified facilitators or mentors. Low commitment levels from recruited facilitators or mentors. Conflicts in availability leading to scheduling issues. 3.2.6 Scripts may be too complex or too simple for the target audience. Inadequate time for script development leading to rushed or incomplete scripts. Scripts not adequately reflecting the business scenario or learning objectives. 3.2.7 Background materials may be too dense or not easily understood by participants. Inaccurate or outdated information in the materials. Delays in material creation affecting the readiness of participants. 3.2.8 Technical issues in the development of the platform leading to functionality gaps. User interface may be unintuitive or difficult to navigate for participants. Security vulnerabilities in the platform affecting data privacy. 3.2.9 Shortages or delays in the procurement of physical materials. Materials not meeting the quality standards required for the simulation. Logistics issues in distributing materials to participants. 3.2.10 Low engagement with promotional efforts leading to low registration numbers. Miscommunication of the event details in promotional materials. Over-promotion leading to an overwhelming number of participants. 3.2.11 Technical issues with the registration system causing participant frustration. Mismanagement of registration data leading to errors in participant lists. Registration system not being user-friendly, leading to drop-offs. 3.2.12 Low attendance at orientation sessions impacting participant preparedness. Inadequate time for orientation, leading to incomplete understanding of the simulation. Lack of clarity in the orientation materials. 3.2.13 Delays in distribution leading to participants not being adequately prepared. Materials not aligned with the simulation content or learning outcomes. Technical issues in distributing digital materials. 3.2.14 Inadequate space for the number of participants, leading to overcrowding. Technical difficulties in setting up virtual spaces or platforms. Delays in space preparation affecting the simulation timeline. 3.2.15 Critical technical issues not identified during testing, leading to failures during the simulation. Insufficient time allocated for thorough testing. Inadequate testing protocols leading to overlooked problems. 3.2.16 Participants not fully understanding the simulation objectives or rules. Low engagement during the introductory session. Technical difficulties during the session affecting participant experience. 3.2.17 Facilitators may lack experience, leading to ineffective guidance. Participants may struggle to engage with the simulation, reducing its effectiveness. Unexpected issues arising during the simulation that disrupt the process. 3.2.18 Insufficient monitoring leading to issues going unnoticed. Bias in monitoring affecting the accuracy of observations. Difficulty in adjusting the simulation in real-time based on observations. 3.2.19 Low participation in debriefing sessions, reducing their effectiveness. Participants not providing honest or useful feedback. Inadequate time allocated for thorough debriefing. 3.3.1 Technical issues with AV equipment affecting the quality of the event. Venue not being ready or suitable for the number of attendees. Last-minute changes in venue leading to confusion. 3.3.2 Promotional materials may not effectively reach the target audience. Errors or omissions in promotional content leading to misinformation. Inadequate time for promotional efforts, resulting in low attendance. 3.3.3 Technical issues affecting the welcome and introduction segment. Poor coordination leading to confusion or delays. Low attendee engagement during the introduction. 3.3.4 Panel discussion may deviate from the key themes, reducing its relevance. Panelists may dominate the discussion, limiting audience interaction. Time management issues leading to an incomplete discussion. 3.3.5 Insufficient time allocated for audience interaction, leading to dissatisfaction. Technical issues with microphones or other equipment affecting the Q&A. Panelists may not adequately address audience questions, leading to frustration. 3.4.1 Technical issues with AV equipment affecting the quality of the event. Venue not being ready or suitable for the number of attendees. Last-minute changes in venue leading to confusion. 3.4.2 Promotional materials may not effectively reach the target audience. Errors or omissions in promotional content leading to misinformation. Inadequate time for promotional efforts, resulting in low attendance. 3.4.3 Technical issues affecting the welcome and introduction segment. Poor coordination leading to confusion or delays. Low attendee engagement during the introduction. 3.4.4 Panel discussion may deviate from the key themes, reducing its relevance. Panelists may dominate the discussion, limiting audience interaction. Time management issues leading to an incomplete discussion. 3.4.5 Insufficient time allocated for audience interaction, leading to dissatisfaction. Technical issues with microphones or other equipment affecting the Q&A. Panelists may not adequately address audience questions, leading to frustration. |  |  |  |
| Description |  |  |  |  |
| Tasks | 3.1 Studijske posete 3.2 Organizacija bisnis simulacija 3.3 Panel Diskusije AI i Machine learning 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation | DUNP |  |  |  |
| Participating Organisation | All Serbian Partners |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.1 Studijske posete |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | #### 3.1.1 Posete univerzitetima i institucijama radi provere njihovih praksi u poslovnoj simulaciji 3.1.1.1 Zakazivanje posete: Planirajte i dogovorite termine poseta univerzitetima i institucijama. Kontaktirajte relevantne kontakte za usklađivanje rasporeda i potvrdu posete. 3.1.1.2 Organizovanje logistike: Organizujte sve potrebne logističke aspekte posete, uključujući prevoz, smeštaj i obroke za učesnike. Osigurajte da svi logistički zahtevi budu ispunjeni. 3.1.1.3 Razvoj potrebnog materijala: Pripremite sve materijale koji će biti potrebni tokom posete, kao što su vodiči, brošure i informacije o instituciji koju posećujete. 3.1.1.4 Kreiranje informacionog materijala: Razvijte informativne materijale koji će pomoći učesnicima da bolje razumeju i pripreme se za posetu. Ovi materijali trebaju sadržavati ključne informacije o instituciji i njenim praksama. 3.1.1.5 Razvoj agende za posetu, uključujući detaljni raspored aktivnosti: Kreirajte detaljnu agendu posete koja uključuje sve planirane aktivnosti, kao i raspored za svakog učesnika. Osigurajte da svi ključni aspekti budu obuhvaćeni i da vreme bude efikasno iskorišćeno. 3.1.1.6 Priprema pozadinske informacije o domaćoj organizaciji, uključujući njenu misiju i ključne ličnosti: Pripremite informacije o organizaciji koja posjećuje, uključujući njenu misiju, ciljeve i ključne osobe. Ove informacije će pomoći učesnicima da steknu bolju predstavu o kontekstu i ciljevima posete. 3.1.1.7 Priprema obrazovnog materijala: Izradite obrazovne materijale koji će biti korišćeni tokom posete, uključujući prezentacije, radne listove i druge resurse koji mogu pomoći u učenju i razumevanju praksi. 3.1.1.8 Sprovođenje obilaska objekta, ističući ključne oblasti interesa i operacija: Organizujte obilazak objekta koji će uključivati sve ključne oblasti interesovanja i operacije koje su relevantne za studije i praksu poslovne simulacije. 3.1.1.9 Priprema prezentacija od strane ključnih ličnosti, fokusirajući se na teme relevantne za studentske studije i interese vezane za karijeru: Organizujte prezentacije od strane ključnih osoba u instituciji koje će se fokusirati na teme od interesa za studente i njihove karijere. 3.1.1.10 Organizacija interaktivnih aktivnosti, kao što su Q&A sesije, demonstracije ili praktične radionice, radi angažovanja studenata i poboljšanja razumevanja: Planirajte interaktivne aktivnosti koje će omogućiti studentima da postavljaju pitanja, učestvuju u demonstracijama i radionica kako bi unapredili svoje razumevanje tema. 3.1.1.11 Priprema za neformalne sesije: Organizujte neformalne sesije, kao što su mrežne aktivnosti ili susreti u neformalnom okruženju, kako bi se podstaklo neformalno učenje i umrežavanje među studentima i predstavnicima institucije. 3.1.1.12 Posete univerzitetima i institucijama radi observacije njihovih praksi u diskusijama za Poslovnu Informatiku: Uvrstite posete univerzitetima i institucijama koje se specijalizuju za poslovnu informatiku, s ciljem posmatranja i analize njihovih praksi i metoda u oblasti diskusija i obrazovanja. 3.1.1.13 Učestvovanje u radionicama i konferencijama koje se fokusiraju na najbolje prakse u visokom obrazovanju i poslovnoj informatici: Učestvujte u relevantnim radionicama i konferencijama koje se bave najboljim praksama u visokom obrazovanju i poslovnoj informatici, kako biste dobili uvid u najnovije trendove i prakse. 3.1.1.14 Sprovođenje virtuelnih poseta i prisustvo onlajn demonstracijama naprednih e-menadžment sistema i IT infrastrukture: Organizujte i učestvujte u virtuelnim posetama i onlajn demonstracijama koje prikazuju napredne e-menadžment sisteme i IT infrastrukture, kako biste proširili razumevanje o ovim tehnologijama. #### 3.1.2 Studijske posete panel diskusijama 3.1.2.1 Zakazivanje posete: Planirajte i dogovorite termine poseta univerzitetima i institucijama. Kontaktirajte relevantne kontakte za usklađivanje rasporeda i potvrdu posete. 3.1.2.2 Organizovanje logistike: Organizujte sve potrebne logističke aspekte posete, uključujući prevoz, smeštaj i obroke za učesnike. Osigurajte da svi logistički zahtevi budu ispunjeni. 3.1.2.3 Razvoj potrebnog materijala: Pripremite sve materijale koji će biti potrebni tokom posete, kao što su vodiči, brošure i informacije o instituciji koju posećujete. 3.1.2.4 Kreiranje informacionog materijala: Razvijte informativne materijale koji će pomoći učesnicima da bolje razumeju i pripreme se za posetu. Ovi materijali trebaju sadržavati ključne informacije o instituciji i njenim praksama. 3.1.2.5 Razvoj agende za posetu, uključujući detaljni raspored aktivnosti: Kreirajte detaljnu agendu posete koja uključuje sve planirane aktivnosti, kao i raspored za svakog učesnika. Osigurajte da svi ključni aspekti budu obuhvaćeni i da vreme bude efikasno iskorišćeno. 3.1.2.6 Priprema pozadinske informacije o domaćoj organizaciji, uključujući njenu misiju i ključne ličnosti: Pripremite informacije o organizaciji koja posjećuje, uključujući njenu misiju, ciljeve i ključne osobe. Ove informacije će pomoći učesnicima da steknu bolju predstavu o kontekstu i ciljevima posete. 3.1.2.7 Priprema obrazovnog materijala: Izradite obrazovne materijale koji će biti korišćeni tokom posete, uključujući prezentacije, radne listove i druge resurse koji mogu pomoći u učenju i razumevanju praksi. 3.1.2.8 Sprovođenje obilaska objekta, ističući ključne oblasti interesa i operacija: Organizujte obilazak objekta koji će uključivati sve ključne oblasti interesovanja i operacije koje su relevantne za studije i praksu poslovne simulacije. 3.1.2.9 Priprema prezentacija od strane ključnih ličnosti, fokusirajući se na teme relevantne za studentske studije i interese vezane za karijeru: Organizujte prezentacije od strane ključnih osoba u instituciji koje će se fokusirati na teme od interesa za studente i njihove karijere. 3.1.2.10 Organizacija interaktivnih aktivnosti, kao što su Q&A sesije, demonstracije ili praktične radionice, radi angažovanja studenata i poboljšanja razumevanja: Planirajte interaktivne aktivnosti koje će omogućiti studentima da postavljaju pitanja, učestvuju u demonstracijama i radionica kako bi unapredili svoje razumevanje tema. 3.1.2.11 Priprema za neformalne sesije: Organizujte neformalne sesije, kao što su mrežne aktivnosti ili susreti u neformalnom okruženju, kako bi se podstaklo neformalno učenje i umrežavanje među studentima i predstavnicima institucije. 3.1.2.12 Posete univerzitetima i institucijama radi observacije njihovih praksi u diskusijama za Poslovnu Informatiku: Uvrstite posete univerzitetima i institucijama koje se specijalizuju za poslovnu informatiku, s ciljem posmatranja i analize njihovih praksi i metoda u oblasti diskusija i obrazovanja. 3.1.2.13 Učestvovanje u radionicama i konferencijama koje se fokusiraju na najbolje prakse u visokom obrazovanju i poslovnoj informatici: Učestvujte u relevantnim radionicama i konferencijama koje se bave najboljim praksama u visokom obrazovanju i poslovnoj informatici, kako biste dobili uvid u najnovije trendove i prakse. 3.1.2.14 Sprovođenje virtuelnih poseta i prisustvo onlajn demonstracijama naprednih e-menadžment sistema i IT infrastrukture: Organizujte i učestvujte u virtuelnim posetama i onlajn demonstracijama koje prikazuju napredne e-menadžment sisteme i IT infrastrukture, kako biste proširili razumevanje o ovim tehnologijama. |  |  |  |
|  | Due date | M2 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.2 Organizacija bisnis simulacija |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.2.1 Identifikacija specifičnih obrazovnih ciljeva: Definišite obrazovne ciljeve koje želite postići kroz poslovnu simulaciju. Ovi ciljevi treba da budu jasni, merljivi i relevantni za učesnike. 3.2.2 Određivanje opsega simulacije: Odredite opseg simulacije, uključujući sve ključne aspekte i aktivnosti koje će biti deo simulacije, kako bi se postigli zadati obrazovni ciljevi. 3.2.3 Razvoj detaljnog poslovnog scenarija: Kreirajte detaljan poslovni scenario koji će biti korišćen tokom simulacije, uključujući sve relevantne informacije, izazove i situacije koje će učesnici morati da reše. 3.2.4 Kreiranje priče: Razvijte priču koja će voditi simulaciju, uključujući sve glavne događaje i prelome u scenariju koji će omogućiti učesnicima da se uključe i reaguju na situacije. 3.2.5 Angažovanje facilitator-a i mentora: Regrutujte i angažujte facilitatora i mentora koji će voditi simulaciju i pružati podršku učesnicima tokom procesa. 3.2.6 Razvoj skripti: Izradite skripte koje će biti korišćene tokom simulacije, uključujući uputstva za facilitatora i učesnike, kao i scenarije za različite situacije. 3.2.7 Kreiranje pozadinskih materijala: Pripremite sve pozadinske materijale koji će biti potrebni za simulaciju, kao što su izvodi iz izveštaja, poslovni dokumenti i drugi resursi koji pomažu u razumevanju scenarija. 3.2.8 Dizajniranje i kreiranje digitalnih platformi: Razvijte i dizajnirajte sve digitalne platforme koje će biti korišćene tokom simulacije, uključujući softverske alate i interfejse za učesnike. 3.2.9 Priprema fizičkih materijala: Organizujte sve fizičke materijale koji će biti korišćeni tokom simulacije, kao što su radni listovi, brošure i drugi materijali koji pomažu u realizaciji simulacije. 3.2.10 Promocija događaja simulacije: Promovišite događaj simulacije kroz različite kanale, kako biste privukli učesnike i osigurali visoku prijavu. 3.2.11 Postavljanje procesa registracije: Organizujte i postavite proces registracije za učesnike, uključujući online prijave i potvrde. 3.2.12 Organizovanje orijentacionih sesija: Pripremite i organizujte orijentacione sesije za učesnike kako bi se upoznali sa svim aspektima simulacije i pripremili se za ulogu koju će igrati. 3.2.13 Distribucija pripremnih materijala: Podelite pripremne materijale učesnicima pre početka simulacije kako bi se mogli pripremiti i upoznati sa sadržajem. 3.2.14 Organizovanje fizičkog i virtuelnog prostora: Pripremite i organizujte fizički i virtuelni prostor u kojem će se simulacija odvijati, uključujući sve tehničke i logističke aspekte. 3.2.15 Testiranje svih tehničkih sistema i alata: Testirajte sve tehničke sisteme i alate koji će biti korišćeni tokom simulacije, kako biste osigurali da sve funkcioniše besprekorno. 3.2.16 Održavanje uvodne sesije: Organizujte uvodnu sesiju za sve učesnike kako biste ih uputili u ciljeve i tok simulacije, kao i pružili sve potrebne informacije. 3.2.17 Facilitation of the simulation: Facilitirajte simulaciju, osiguravajući da svi učesnici imaju priliku da učestvuju i da se simulacija odvija prema planu. 3.2.18 Praćenje interakcija i napretka studenata: Pratite interakcije i napredak studenata tokom simulacije, pružajući povratne informacije i podršku kada je potrebno. 3.2.19 Održavanje sesija za refleksiju: Organizujte sesije za refleksiju nakon simulacije, kako bi učesnici mogli da analiziraju i diskutuju o svojim iskustvima i naučenim lekcijama. |  |  |  |
|  | Due date | M8 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.3 Panel Diskusije AI i Machine learning |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.3.1 Postavljanje prostora: Pripremite prostor za panel diskusiju, uključujući sve tehničke i logističke aspekte, kao što su sedišta, audio-vizuelna oprema i osvjetljenje. 3.3.2 Razvoj promotivnih materijala: Izradite promotivne materijale za panel diskusiju, kao što su plakati, brošure i objave na društvenim mrežama, kako biste privukli učesnike i publiku. 3.3.3 Dobrodošlica učesnicima i predstavljanje panelista i moderatora: Pripremite dobrodošlicu za učesnike i predstavite paneliste i moderatora, obezbeđujući da svi prisutni imaju sve potrebne informacije. 3.3.4 Facilitacija panel diskusije, osiguravajući da ostane na pravom putu i pokriva ključne teme: Vodite diskusiju, pazeći da se fokusira na ključne teme i da se svi panelisti uključe u razgovor na konstruktivan način. 3.3.5 Omogućavanje vremena za pitanja publike i interakciju sa panelistima: Obezbedite vreme za pitanja publike i interakciju sa panelistima, kako bi se omogućila dublja razmena mišljenja i informacija. |  |  |  |
|  | Due date | M10 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 3.4 Panel Diskusije BlockChain tehnologije i primena u poslovanju |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 3.4.1 Postavljanje prostora: Organizujte i pripremite prostor za panel diskusiju o blockchain tehnologiji, uključujući tehničke i logističke aspekte. 3.4.2 Razvoj promotivnih materijala: Kreirajte promotivne materijale za panel diskusiju, kako biste informisali i privukli publiku i potencijalne učesnike. 3.4.3 Dobrodošlica učesnicima i predstavljanje panelista i moderatora: Pripremite dobrodošlicu i predstavite paneliste i moderatora, pružajući sve relevantne informacije o njihovim iskustvima i stručnosti. 3.4.4 Facilitacija panel diskusije, osiguravajući da ostane na pravom putu i pokriva ključne teme: Vodeći diskusiju, osigurajte da se pokrivaju ključne teme o blockchain tehnologiji i njenim primenama u poslovanju. 3.4.5 Omogućavanje vremena za pitanja publike i interakciju sa panelistima: Planirajte vreme za pitanja publike i omogućite interakciju između publike i panelista, kako bi se omogućila dublja rasprava i razmena mišljenja. |  |  |  |
|  | Due date | M10 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Work package type and ref.nr ☐ | DEVELOPMENT |  |  | 4 |
| --- | --- | --- | --- | --- |
| Title | 4. Formiranje laboratorije za digitalnu transformaciju |  |  |  |
| Related assumptions and risks | 4.1.1 Difficulty in recruiting a diverse group of stakeholders. Low engagement or commitment from recruited members. Conflicting interests among stakeholders, leading to delays. 4.1.2 Misalignment of roles and responsibilities leading to confusion. Overlapping duties causing inefficiencies. Resistance to assigned roles from committee members. 4.2.1 Limited participation or response from key groups. Biased or incomplete feedback affecting the accuracy of needs assessment. Misinterpretation of stakeholder input leading to incorrect requirements. 4.2.2 Inaccurate assessment due to outdated or incomplete data. Overlooking critical facility or equipment deficiencies. Underestimating the cost or time required to upgrade facilities. 4.3.1 Inaccurate estimation of costs and timelines. Scope creep due to unclear or evolving objectives. Inadequate resource allocation impacting project execution. 4.3.2 Misalignment between specifications and actual needs. Rapid technological changes rendering specifications outdated. Difficulty in sourcing equipment that meets specified requirements. 4.4.1 Selection of unreliable or unqualified vendors. Vendor delays affecting project timelines. Budget overruns due to unexpected costs or price changes. 4.4.2 Equipment or software not meeting quality standards or specifications. Delivery delays impacting project schedule. Issues with software licensing or compliance. 4.5.1 Difficulty in securing a suitable location. Space not meeting the needs of the planned setup. Delays in obtaining necessary approvals for space use. 4.5.2 Construction or renovation delays. Unforeseen costs related to infrastructure upgrades. Safety or compliance issues during renovation. 4.6.1 Installation delays due to technical issues. Incompatibility between new and existing hardware. Damage to equipment during installation. 4.6.2 Software configuration errors leading to operational issues. Cybersecurity vulnerabilities introduced during setup. Inadequate staff training on new software. 4.7.1 Misconfigurations leading to security breaches or performance issues. Over-provisioning or under-provisioning cloud resources. Unforeseen costs associated with cloud services. 4.7.2 Inadequate security measures leading to data breaches. Complex access controls causing usability issues. Compliance failures with data protection regulations. 4.8.1 Equipment or systems not functioning as expected during the soft launch. Low participation from initial users affecting feedback quality. Insufficient time to address issues before the official launch. 4.8.2 Delayed feedback from users hindering timely adjustments. Identified issues requiring major changes impacting the timeline. Resistance to changes from stakeholders. 4.9.1 Logistical challenges affecting the quality of the event. Low attendance or engagement from key stakeholders. Negative feedback or technical issues during the event. 4.9.2 Technical issues during demonstrations. Failure to effectively communicate the benefits, leading to low interest. Misalignment of expectations among different stakeholder groups. |  |  |  |
| Description |  |  |  |  |
| Tasks | 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps 4.2 Conduct a Needs Assessment 4.3 Develop a Detailed Plan 4.4 Procure Equipment and Software 4.5 Prepare the Physical Space 4.6 Install Equipment and Software 4.7 Establish Cloud Infrastructure 4.8 Conduct a Soft Launch 4.9 Organize an Official Launch Event |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation | DUNP |  |  |  |
| Participating Organisation | All Serbian Partners |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.1 Formiranje projektnog tima za laboratorije AI i mašinsko učenje, digitalnu transformaciju i DevOps |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.1.1 Identifikacija i regrutovanje ključnih aktera - Počnite sa identifikacijom ključnih aktera, uključujući univerzitetske profesore, industrijske stručnjake, IT profesionalce i studente sa relevantnim interesovanjima i stručnostima. - Zakažite inicijalne sastanke kako biste razgovarali o ciljevima projekta i potencijalnim ulogama aktera. - Zvanično ih angažujte za projekat pružanjem detaljnog pregleda odgovornosti i očekivanih doprinosa. 4.1.2 Dodela uloga i odgovornosti unutar tima - Definišite specifične uloge kao što su projektni menadžer, tehnički vođa, softverski vođa i koordinator operacija. - Jasno dokumentujte i komunicirajte ove uloge svakom članu tima. - Organizujte redovne timske sastanke kako bi svaki član razumeo svoje zadatke i rokove, i kako bi se koordinisale aktivnosti između odeljenja (IT, nabavka, administracija). |  |  |  |
|  | Due date | M14 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.2 Conduct a Needs Assessment |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.2.1 Prikupljanje inputa od fakulteta, studenata i industrijskih partnera o željenim funkcijama laboratorije i centra - Sprovođenje anketa ili fokus grupa kako biste prikupili uvide od fakulteta, studenata i industrijskih partnera o njihovim potrebama i očekivanjima od laboratorije (npr. pristup AI alatima, cloud servisima ili radionicama). - Dokumentujte ključne željene funkcije i analizirajte kako se one uklapaju sa aktuelnim trendovima u AI, mašinskom učenju i DevOps-u. 4.2.2 Procena trenutnog stanja objekata, opreme i resursa dostupnih na univerzitetu - Pregledajte postojeće objekte i infrastrukturu univerziteta. - Sprovedite analizu nedostataka kako biste utvrdili koja oprema, softver i alati su već dostupni, a šta je potrebno dodatno nabaviti. - Pripremite izveštaj koji opisuje trenutno stanje resursa i potrebne nadogradnje za laboratoriju. |  |  |  |
|  | Due date | M15 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.3 Develop a Detailed Plan |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.3.1 Kreiranje sveobuhvatnog plana koji obuhvata ciljeve, opseg, vremenski okvir, budžet i resurse potrebne za osnivanje laboratorije i centra - Nacrtajte detaljan projektni plan koji obuhvata opseg laboratorije (AI, DevOps, mašinsko učenje itd.), ciljeve projekta (obuka studenata, podrška istraživanju) i razradu ključnih faza. - Uspostavite vremenski okvir sa specifičnim prekretnicama kao što su nabavka, postavljanje, testiranje i lansiranje. - Razvijte detaljan budžet, uzimajući u obzir opremu, softverske licence, osoblje, treninge i događaje. 4.3.2 Osigurajte da plan uključuje detaljne specifikacije - Uključite tehničke specifikacije za potrebnu opremu (servere, radne stanice, mrežne uređaje), softver (AI alati, cloud platforme) i sigurnosnu infrastrukturu. - Konsultujte se sa IT stručnjacima i dobavljačima kako biste finalizirali te specifikacije i osigurali da odgovaraju potrebama projekta i budu skalabilne za buduću ekspanziju. |  |  |  |
|  | Due date | M17 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.4 Procure Equipment and Software |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.4.1 Identifikacija i odabir dobavljača - Istražite potencijalne dobavljače opreme i softvera. Razmotrite faktore kao što su cena, tehnička podrška, kompatibilnost sa postojećom infrastrukturom i skalabilnost. - Zatražite ponude i pregovarajte o ugovorima sa preferiranim dobavljačima, osiguravajući da ispunjavaju univerzitetske smernice za nabavku. 4.4.2 Kupovina i nabavka potrebne opreme i softverskih licenci - Nakon što odaberete dobavljače, pošaljite narudžbenice za potrebni hardver i softver. - Koordinirajte se sa finansijskim i nabavnim odeljenjima univerziteta kako biste osigurali pravovremenu nabavku resursa. - Pratite vremenski okvir isporuke i instalacije sve opreme i softvera. |  |  |  |
|  | Due date | M19 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.5 Prepare the Physical Space |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.5.1 Identifikacija i osiguranje odgovarajuće lokacije na kampusu* - Identifikujte odgovarajući prostor na kampusu koji ima adekvatan prostor, napajanje, mrežnu povezanost i sigurnost za laboratoriju. - Osigurajte odobrenje od univerzitetske uprave za korišćenje ovog prostora. 4.5.2 Renoviranje i postavljanje fizičkog prostora - Ako je potrebno, renovirajte prostor kako bi ispunio tehničke zahteve (npr. instaliranje dodatnih električnih utičnica, poboljšanje ventilacije za servere). - Postavite prostor sa odgovarajućim nameštajem, tablama, projektorima i mrežnom infrastrukturom. |  |  |  |
|  | Due date | M21 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.6 Install Equipment and Software |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.6.1 Postavljanje servera, radnih stanica, mrežnih uređaja i druge hardverske opreme - Saradnja sa IT odeljenjem na instalaciji i konfigurisanju servera, radnih stanica i mrežnih uređaja. - Osigurajte pravilnu konfiguraciju mrežne sigurnosti, uključujući firewalle, VPN-ove i ograničen pristup osetljivim podacima i sistemima. 4.6.2 Instalacija i konfiguracija potrebnog softvera, uključujući cloud platforme, DevOps alate i druge relevantne aplikacije - Instalirajte i konfigurišite softvere za AI i mašinsko učenje, cloud servise (AWS, Azure) i DevOps alate (Jenkins, Docker). - Testirajte svaki softver kako biste osigurali njegovu besprekornu integraciju sa hardverskom i mrežnom postavkom. |  |  |  |
|  | Due date | M22 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.7. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.7 Establish Cloud Infrastructure |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.7.1 Postavljanje cloud naloga i konfiguracija cloud resursa - Kreirajte naloge kod cloud provajdera kao što su AWS, Azure ili Google Cloud. - Konfigurišite cloud infrastrukturu, uključujući postavljanje virtuelnih mašina, skladištenja i mrežnih resursa potrebnih za AI i DevOps projekte. 4.7.2 Implementacija sigurnosnih mera i kontrole pristupa radi zaštite cloud infrastrukture - Uspostavite stroge sigurnosne protokole, uključujući višefaktornu autentifikaciju, enkripciju podataka u tranzitu i mirovanju i kontrole pristupa za korisnike. - Postavite redovne backup-ove i nadzor cloud sistema kako biste sprečili neovlašćen pristup i osigurali bezbednost podataka. |  |  |  |
|  | Due date | M24 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.8. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.8 Conduct a Soft Launch |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.8.1 Organizovanje probnog lansiranja laboratorije i centra - Planirajte probno lansiranje pozivom male grupe korisnika (fakultet, studenti i industrijski partneri) kako bi koristili laboratorijske kapacitete. - Sprovedite uživo testiranje opreme i softvera kako biste identifikovali sve potencijalne probleme ili uska grla u sistemu. 4.8.2 Prikupljanje povratnih informacija od inicijalnih korisnika i prilagođavanje pre zvaničnog lansiranja - Prikupite povratne informacije od korisnika tokom probnog lansiranja o njihovom iskustvu sa alatima i infrastrukturom. - Koristite ove povratne informacije za prilagođavanja, kao što su fino podešavanje postavki pristupa, rešavanje problema sa performansama ili unapređenje korisničkog iskustva. |  |  |  |
|  | Due date | M26 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.9. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 4.9 Organize an Official Launch Event |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 4.9.1 Planiranje i organizacija zvaničnog događaja lansiranja - Isplanirajte veliki događaj koji uključuje univerzitetsku zajednicu, industrijske partnere i medije kako bi se zvanično otvorila laboratorija. - Pripremite agendu koja uključuje govore ključnih aktera, obilazak laboratorije i demonstracije tehnologija. 4.9.2 Predstavljanje laboratorijskih kapaciteta, demonstracija ključnih tehnologija i isticanje benefita za studente, fakultet i industrijske partnere |  |  |  |
|  | Due date | M28 |  |  |  |
|  | Languages | Serbian |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr☐ | QUALITY PLAN |  |  | 5 |
| --- | --- | --- | --- | --- |
| Title | 5 Developing QCM manual |  |  |  |
| Related assumptions and risks | 5.1 Lack of consensus on which metrics best represent the third mission (community engagement, social responsibility, etc.). 5.2 Inconsistent monitoring across different departments and institutions due to varying levels of understanding and commitment. 5.3 Inadequate tools or methods for effectively measuring the defined metrics, leading to inaccurate reporting. |  |  |  |
| Description |  |  |  |  |
| Tasks | 5.1 Defining third mission metrics 5.2 Internal monitoring 5.3 Monitoring of defined metrics |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation | DUNP |  |  |  |
| Participating Organisation | All Serbian Partners |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 5.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 5.1 Defining third mission metrics |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 5.1 Defining third mission metrics: Start by gathering a team of experts from within the institution, including representatives from administration, faculty, and any relevant departments, to define the third mission metrics. These metrics should capture the institution's broader impact on society, such as community engagement, technology transfer, and public outreach. Facilitate workshops and discussions to identify the most relevant metrics that align with the institution's mission and strategic goals. Once identified, document these metrics clearly, ensuring they are specific, measurable, achievable, relevant, and time-bound (SMART). This will form the foundation of the QCM (Quality Control and Monitoring) manual. |  |  |  |
|  | Due date | M2 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 5.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 5.2 Internal monitoring |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 5.2 Internal monitoring: Establish a system for internal monitoring of the defined third mission metrics. Develop processes and tools, such as templates and software, to regularly collect data related to each metric. Assign responsibilities to specific departments or individuals for data collection, analysis, and reporting. Conduct training sessions to ensure that all involved parties understand how to use the monitoring tools and follow the established procedures. Schedule regular internal audits or reviews to assess the effectiveness of the monitoring system and make adjustments as needed to improve accuracy and efficiency. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 5.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 5.3 Monitoring of defined metrics |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 5.3 Monitoring of defined metrics: Implement the monitoring system by starting the regular collection and analysis of data based on the third mission metrics. Set up a timeline for monitoring activities, including monthly or quarterly reporting, to track progress against the defined metrics. Create a feedback loop where the results are reviewed by relevant stakeholders, such as the management team, and used to inform decision-making and strategic planning. Adjust the metrics or monitoring approach if necessary, based on the findings and feedback, to ensure that they continue to reflect the institution's goals and societal impact effectively. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☒ | DISSEMINATION & EXPLOITATION |  |  | 6 |
| --- | --- | --- | --- | --- |
| Title | 6 Elaboration of Dissemination and Exploitation Plan |  |  |  |
| Related assumptions and risks | 6.1 Delay in agreeing on a visual identity that represents all partner institutions, potentially delaying other dissemination efforts. 6.2 Delays in website development or technical issues could hinder communication and dissemination of project results. 6.3 Resistance from institutions or a lack of institutional support for new policies related to the third mission. 6.4 Difficulty in identifying relevant good practices or reluctance from industry partners to share sensitive information on innovation practices. 6.5 Low participation from target audiences at info days and events, limiting the project’s dissemination reach. 6.6 Logistical challenges or scheduling conflicts could reduce attendance and engagement at the final conference. |  |  |  |
| Description |  |  |  |  |
| Tasks | 6.1 Design of project visual identity 6.2 Design/upgrade of web-site 6.3 Defining institutional policies to promote third mission 6.4 Good practices on Tech. transfer and Innovation 6.5 10 Info days and other events 6.6 Final Conference on university third mission |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation | DUNP |  |  |  |
| Participating Organisation | All Serbian Partners |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.1 Design of project visual identity |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.1 Design of project visual identity: Begin by assembling a creative team that includes graphic designers, communication experts, and key project stakeholders to develop the project's visual identity. This identity should include a logo, color scheme, typography, and design elements that reflect the project's goals and values. Conduct brainstorming sessions to gather ideas and draft multiple design concepts. Once a few concepts are developed, present them to the broader project team for feedback. Refine the chosen design based on this feedback, and ensure that the final visual identity is versatile and suitable for various platforms, including print, digital, and merchandise. Document the visual identity guidelines in a style guide to ensure consistency across all project materials. |  |  |  |
|  | Due date | M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.2 Design/upgrade of web-site |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.2 Design/upgrade of website: With the visual identity established, work with web designers and developers to create or upgrade the project website. The website should be user-friendly, accessible, and aligned with the visual identity. Begin by defining the website's structure, including key sections such as project overview, news, events, resources, and contact information. Ensure that the website is optimized for search engines (SEO) and mobile devices. Collaborate with content creators to develop engaging and informative content for each section. Launch the website after thorough testing for functionality, speed, and usability. Regularly update the site with new content and features as the project progresses. |  |  |  |
|  | Due date | M12 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.3 Defining institutional policies to promote third mission |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.3 Defining institutional policies to promote third mission: Work with institutional leaders, policy experts, and legal advisors to define policies that promote the third mission of the university, which includes activities such as community engagement, technology transfer, and societal impact. Start by reviewing existing policies to identify gaps or areas for improvement. Conduct consultations with key stakeholders, including faculty, students, and industry partners, to gather input on policy priorities. Draft the new or revised policies, ensuring they align with the institution’s mission and strategic goals. Once the policies are finalized, they should be approved by the relevant governance bodies and communicated effectively to the entire university community. |  |  |  |
|  | Due date | M16 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.4 Good practices on Tech. transfer and Innovation |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.4 Good practices on Tech transfer and Innovation: Research and document good practices in technology transfer and innovation both within the institution and from other leading universities or organizations. Begin by conducting a literature review and case studies on successful tech transfer initiatives. Engage with industry partners and experts to gather insights on effective practices and potential pitfalls. Compile this information into a comprehensive report that includes recommendations for how these practices can be adapted and implemented within the institution. Share the report with relevant departments, such as research, innovation, and tech transfer offices, and use it as a basis for training and capacity-building workshops. |  |  |  |
|  | Due date | M18 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.5 10 Info days and other events |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.5 10 Info days and other events: Plan and organize a series of 10 information days and other events to promote the project’s objectives and engage the university community and external stakeholders. Start by developing a detailed event plan that includes the target audience, key messages, speakers, and activities for each event. Secure venues and arrange for logistical support, including audiovisual equipment, catering, and promotional materials. Use the project’s visual identity to brand these events consistently. Promote the events through the project website, social media, and email campaigns. During the events, gather feedback from participants to improve subsequent info days. Document the outcomes of each event and share them with stakeholders. |  |  |  |
|  | Due date | M21 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 6.6. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 6.6 Final Conference on university third mission |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 6.6 Final Conference on university third mission: Conclude the project with a high-profile final conference focused on the university's third mission. Begin by forming a conference planning committee that includes representatives from key stakeholder groups. Develop a comprehensive plan that outlines the conference theme, agenda, speakers, workshops, and networking opportunities. Identify and invite keynote speakers who are leaders in the field of university third mission activities. Promote the conference widely to ensure strong attendance from both the university community and external partners. During the conference, facilitate discussions on best practices, challenges, and future directions for third mission activities. Collect feedback and publish a conference report that highlights the key outcomes and recommendations. |  |  |  |
|  | Due date | M22 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

| Work package type and ref.nr ☒ | MANAGEMENT |  |  | 7 |
| --- | --- | --- | --- | --- |
| Title | 7. Elaboration of Manual for contractual and financial management. |  |  |  |
| Related assumptions and risks | 7.1 Coordination challenges between multiple institutions and partners, potentially causing delays in deliverables. 7.2 Local management teams may lack the resources or expertise to handle complex financial and contractual tasks. 7.3 Scheduling conflicts and low attendance at Steering Committee meetings could slow down decision-making processes. |  |  |  |
| Description |  |  |  |  |
| Tasks | 7.1 Overall project managementt 7.2 Local management 7.3 SC meetings |  |  |  |
| Estimated Start Date (dd-mm-yyyy) |  | Estimated End Date (dd-mm-yyyy) |  |  |
| Lead Organisation | DUNP |  |  |  |
| Participating Organisation | All Serbian Partners |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. |  |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes☒ | Work Package and Outcome ref.nr | 7.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 7.1 Overall project managementt |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 7.1 Overall project management: Start by establishing a framework for overall project management that will guide the project from inception to completion. This includes defining the project’s goals, deliverables, timelines, and key milestones. Develop a comprehensive project management plan that outlines roles and responsibilities, communication protocols, risk management strategies, and quality control measures. Utilize project management tools such as Gantt charts, project dashboards, and task management software to monitor progress and ensure that all aspects of the project are on track. Regularly review and update the project management plan to reflect any changes or developments, ensuring that all stakeholders are informed and aligned with the project’s objectives. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes☒ | Work Package and Outcome ref.nr | 7.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 7.2 Local management |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 7.2 Local management: For local management, create guidelines tailored to the specific needs and contexts of the local teams involved in the project. Begin by identifying local project coordinators who will oversee the day-to-day management of activities at each location. Provide these coordinators with a clear understanding of their roles, including managing local budgets, coordinating with the central project management team, and ensuring compliance with the project’s overall goals and standards. Develop a local management manual that includes procedures for reporting, communication, and decision-making at the local level. Schedule regular check-ins between local teams and the central management team to address any challenges and ensure consistency across all locations. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

| Expected Deliverable/Results/ Outcomes☒ | Work Package and Outcome ref.nr | 7.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | 7.3 SC meetings |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☐ Service/Product |  |
|  | Description | 7.3 SC meetings: To ensure effective governance and decision-making, plan and organize Steering Committee (SC) meetings at regular intervals throughout the project. Begin by establishing the SC’s composition, including key stakeholders such as project leaders, financial managers, and representatives from each partner institution. Develop a schedule for SC meetings, typically quarterly, and circulate it to all members in advance. For each meeting, prepare an agenda that covers project progress, financial management, risk assessment, and any key decisions that need to be made. Distribute relevant documents and reports to SC members ahead of time to facilitate informed discussions. During the meetings, ensure that minutes are taken to document decisions and action items, and follow up on these actions in subsequent meetings to ensure accountability and progress. |  |  |  |
|  | Due date | M36 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐Teaching staff ☐Students ☐Trainees ☐Administrative staff ☐Technical staff ☐Librarians ☐Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☐Department / Faculty ☐Institution |  | ☐Local ☐Regional |  | ☐National ☐International |

Please copy and paste tables as necessary.

# E.7 Consortium partners involved and human resources required to complete the work packages

Indicative input of consortium staff - The total number of days per staff category should correspond with the information provided in the budget tables.☐

| Work Package Ref.nr | Partner nr | Partner acronym | Country | Number of staff days☒ |  |  |  |  | Exact Role and tasks of each person in the work package |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Category 1 | Category 2 | Category 3 | Category 4 | Total |  |
| PREPARATION | P1 | DUNP | Serbia |  |  |  |  |  | ### Activity 1.1.1 (Needs Assessment for IT System) - Administration: 10 days - Technical: 15 days - Research: 10 days ### Activity 1.1.2 (Final Reporting) - Administration: 5 days - Technical: 10 days - Research: 5 days ### Activity 1.2.1 (Blockchain Technology Selection) - Administration: 10 days - Technical: 15 days - Research: 10 days ### Activity 1.2.2 (Pilot Testing and Evaluation) - Administration: 5 days - Technical: 15 days - Research: 5 days ### Activity 1.3.1 to 1.3.5 (Data on Practices in Universities) - Administration: 15 days - Technical: 20 days - Research: 20 days ### Activity 1.4.1 to 1.4.3 (Industry Partner Meetings) - Administration: 10 days - Technical: 10 days - Research: 10 days ### Activity 1.5.1 to 1.5.8 (Curriculum Analysis) - Administration: 15 days - Technical: 20 days - Research: 25 days ### Activity 1.6.1 to 1.6.6 (Good Practices Analysis) - Administration: 15 days - Technical: 20 days - Research: 20 days |
|  | P2 |  |  |  |  |  |  |  | ### Act. 1.1.1 - Administracija: 10 dana - Tehnička podrška: 5 dana ### Act. 1.1.2 - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 1.2.1 - Administracija: 8 dana - Tehnička podrška: 6 dana ### Act. 1.2.2 - Administracija: 4 dana - Tehnička podrška: 3 dana ### Act. 1.3.1 - Administracija: 6 dana - Tehnička podrška: 4 dana ### Act. 1.3.2 - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 1.3.3 - Administracija: 7 dana - Tehnička podrška: 4 dana ### Act. 1.3.4 - Administracija: 4 dana - Tehnička podrška: 2 dana ### Act. 1.4.1 - Administracija: 5 dana - Tehnička podrška: 4 dana ### Act. 1.4.2 - Administracija: 4 dana - Tehnička podrška: 2 dana ### Act. 1.4.3 - Administracija: 3 dana - Tehnička podrška: 2 dana ### Act. 1.5.1 - Administracija: 5 dana - Tehnička podrška: 4 dana ### Act. 1.5.2 - Administracija: 4 dana - Tehnička podrška: 3 dana ### Act. 1.5.3 - Administracija: 6 dana - Tehnička podrška: 5 dana ### Act. 1.5.4 - Administracija: 3 dana - Tehnička podrška: 2 dana ### Act. 1.5.5 - Administracija: 4 dana - Tehnička podrška: 3 dana ### Act. 1.6.1 - Administracija: 6 dana - Tehnička podrška: 4 dana ### Act. 1.6.2 - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 1.6.3 - Administracija: 6 dana - Tehnička podrška: 5 dana ### Act. 1.6.4 - Administracija: 5 dana - Tehnička podrška: 4 dana ### Act. 1.6.5 - Administracija: 6 dana - Tehnička podrška: 4 dana ### Act. 1.6.6 - Administracija: 6 dana - Tehnička podrška: 5 dana |
|  | P3 |  |  |  |  |  |  |  | ### Act 1.1.1 - Administracija: 20 dana - Organizacija intervjua, definisanje ciljeva, razvoj pitanja, planiranje i zakazivanje sesija. - Tehnička podrška: 5 dana - Pomoć u postavljanju tehničkih sredstava za snimanje i analizu. ### Act 1.1.2 - Administracija: 10 dana - Pisanje, pregled i finalizacija izveštaja o potrebama. - Tehnička podrška: 3 dana - Asistencija u analizi podataka i formatiranju izveštaja. ### Act 1.2.1 - Administracija: 15 dana - Definisanje zahteva, istraživanje i razvoj kriterijuma evaluacije. - Tehnička podrška: 4 dana - Pomoć u analizi i testiranju blockchain tehnologija. ### Act 1.2.2 - Administracija: 10 dana - Pisanje i pregled evaluacionih i izbornih izveštaja. - Tehnička podrška: 3 dana - Pomoć u analizi povratnih informacija i tehničkoj evaluaciji. ### Act 1.3.1 - Administracija: 15 dana - Definisanje ciljeva, razvoj upitnika i planiranje intervjua. - Tehnička podrška: 4 dana - Pomoć u sakupljanju i analizi podataka. ### Act 1.3.2 - Administracija: 15 dana - Organizacija i vođenje intervjua, uključujući analizu podataka. - Tehnička podrška: 4 dana - Pomoć u transkripciji i analizi prikupljenih informacija. ### Act 1.3.3 - Administracija: 12 dana - Pisanje i pregled izveštaja o efektivnosti partnerstava i praksama. - Tehnička podrška: 3 dana - Asistencija u analizi i prezentaciji rezultata. ### Act 1.4.1 - Administracija: 15 dana - Identifikacija partnera, organizacija virtuelnih sastanaka, razvoj pitanja. - Tehnička podrška: 4 dana - Tehnička podrška tokom sastanaka i analiza snimaka. ### Act 1.4.2 - Administracija: 10 dana - Pisanje i pregled izveštaja sa sastanaka. - Tehnička podrška: 3 dana - Pomoć u analizi podataka iz sastanaka. ### Act 1.5.1 do Act 1.5.8 - Administracija: 30 dana - Istraživanje, analiza i pisanje izveštaja o trenutnim praksama i potrebama. - Tehnička podrška: 8 dana - Pomoć u analizi i korišćenju podataka. ### Act 1.6.1 do Act 1.6.6 - Administracija: 25 dana - Razvoj okvira istraživanja, organizacija intervjua, analiza praksi i pisanje izveštaja. - Tehnička podrška: 6 dana - Pomoć u vođenju virtualnih tura i analizi prikupljenih podataka. |
|  | P4 |  |  |  |  |  |  |  | ### Act. 1.1.1 - Utvrđivanje potreba za razvojem novog IT sistema - Administracija: 10 dana - Tehnička podrška: 5 dana ### Act. 1.1.2 - Izveštaj o potrebama - Administracija: 8 dana - Tehnička podrška: 4 dana ### Act. 1.2.1 - Selekcija odgovarajuće blockchain tehnologije - Administracija: 10 dana - Tehnička podrška: 6 dana ### Act. 1.2.2 - Izveštaj o evaluaciji blockchain tehnologije - Administracija: 6 dana - Tehnička podrška: 3 dana ### Act. 1.3.1 - Prikupljanje i analiza podataka o praksama - Administracija: 12 dana - Tehnička podrška: 7 dana ### Act. 1.3.2 - Odabir studenata za intervjue - Administracija: 8 dana - Tehnička podrška: 4 dana ### Act. 1.3.3 - Analiza partnerstava i praksi - Administracija: 10 dana - Tehnička podrška: 5 dana ### Act. 1.4.1 - Virtuelni sastanci sa industrijskim partnerima - Administracija: 8 dana - Tehnička podrška: 4 dana ### Act. 1.4.2 - Izveštaj o nalazima iz virtuelnih sastanaka - Administracija: 6 dana - Tehnička podrška: 3 dana ### Act. 1.5.2 - Analiza relevantne literature - Administracija: 8 dana - Tehnička podrška: 5 dana ### Act. 1.5.4 - Analiza podataka o performansama studenata - Administracija: 7 dana - Tehnička podrška: 4 dana ### Act. 1.6.1 - Kreiranje istraživačkog okvira - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 1.6.5 - Analiza prikupljenih podataka - Administracija: 8 dana - Tehnička podrška: 5 dana |
|  | P5 |  |  |  |  |  |  |  | ### Act. 1.1: Needs Assessment for New IT System - Administration: 10 days - Planning and scheduling interviews/focus groups, sending invitations, and managing logistics. - Technical: 8 days - Conducting interviews/focus groups, recording sessions, and analyzing data. ### Act. 1.2: Selecting Blockchain Technology - Administration: 8 days - Defining requirements, scheduling meetings with stakeholders, and managing logistics. - Technical: 12 days - Researching blockchain options, conducting assessments, and executing pilot projects. ### Act. 1.3: Data on Practices in National Universities - Administration: 12 days - Creating questionnaires, recruiting participants, scheduling interviews, and managing logistics. - Technical: 15 days - Conducting interviews, analyzing data, and compiling reports. ### Act. 1.4: Virtual Meetings with Industry Partners - Administration: 8 days - Identifying partners, scheduling meetings, and sending invitations. - Technical: 7 days - Conducting meetings, recording sessions, and analyzing data. ### Act. 1.5: Curriculum Analysis and Improvement - Administration: 15 days - Gathering literature, coordinating with stakeholders, and managing review processes. - Technical: 20 days - Analyzing performance data, reviewing the curriculum, and compiling findings. ### Act. 1.6: Analyzing Good Practices in Laboratories and Centers - Administration: 10 days - Developing the research framework, scheduling interviews, and managing logistics. - Technical: 15 days - Conducting desk research, virtual tours, and analyzing collected data. |
|  | P6 |  |  |  |  |  |  |  | ### Act 1.1: Needs Assessment for New IT System Needs Identification (1 month) - Administrative: 10 days - Technical: 5 days Data Analysis and Reporting - Administrative: 7 days - Technical: 3 days ### Total for Act 1.1: - Administrative: 17 days - Technical: 8 days ### Act 1.2: Selection of Blockchain Technology Technology Selection (1 month) - Administrative: 10 days - Technical: 5 days Pilot Testing and Evaluation - Administrative: 8 days - Technical: 4 days ### Total for Act 1.2: - Administrative: 18 days - Technical: 9 days ### Act 1.3: Internship and Practice Analysis Data Gathering (2 months) - Administrative: 15 days - Technical: 10 days Data Analysis and Reporting - Administrative: 10 days - Technical: 5 days ### Total for Act 1.3: - Administrative: 25 days - Technical: 15 days ### Act 1.4: Virtual Meetings with Industry Partners Meeting Planning and Execution (1 month) - Administrative: 10 days - Technical: 5 days Data Analysis and Reporting - Administrative: 7 days - Technical: 3 days ### Total for Act 1.4: - Administrative: 17 days - Technical: 8 days ### Act 1.5: Curriculum Analysis Literature and Data Review - Administrative: 10 days - Technical: 5 days Report Compilation - Administrative: 8 days - Technical: 4 days ### Total for Act 1.5: - Administrative: 18 days - Technical: 9 days ### Act 1.6: Good Practices in University Laboratories Research Framework and Data Collection - Administrative: 10 days - Technical: 5 days Analysis and Reporting - Administrative: 10 days - Technical: 5 days ### Total for Act 1.6: - Administrative: 20 days - Technical: 10 days |
|  | P7 |  |  |  |  |  |  |  | ### Act 1.1: Needs Assessment for New IT System Description: - Conduct interviews and focus groups to establish IT system needs. Activities: - Needs Identification (1 month) - Administrative: 10 days - Technical: 5 days - Data Analysis and Reporting - Administrative: 7 days - Technical: 3 days ### Act 1.2: Selection of Blockchain Technology Description: - Select appropriate blockchain technology for the e-management system. Activities: - Technology Selection (1 month) - Administrative: 10 days - Technical: 5 days - Pilot Testing and Evaluation - Administrative: 8 days - Technical: 4 days ### Act 1.3: Internship and Practice Analysis Description: - Gather and analyze data on available practices in national universities. Activities: - Data Gathering (2 months) - Administrative: 15 days - Technical: 10 days - Data Analysis and Reporting - Administrative: 10 days - Technical: 5 days ### Act 1.4: Virtual Meetings with Industry Partners Description: - Conduct virtual meetings to explore internships offered by small and medium businesses. Activities: - Meeting Planning and Execution (1 month) - Administrative: 10 days - Technical: 5 days - Data Analysis and Reporting - Administrative: 7 days - Technical: 3 days ### Act 1.5: Curriculum Analysis Description: - Analyze curriculum against industry standards and academic needs. Activities: - Literature and Data Review - Administrative: 10 days - Technical: 5 days - Report Compilation - Administrative: 8 days - Technical: 4 days ### Act 1.6: Good Practices in University Laboratories Description: - Analyze and document good practices in university labs. Activities: - Research Framework and Data Collection - Administrative: 10 days - Technical: 5 days - Analysis and Reporting - Administrative: 10 days - Technical: 5 days |
|  | P8 |  |  |  |  |  |  |  | ### Act 1.1: Needs Assessment for New IT System Description: - Establish the needs for a new IT system at partner universities through interviews and focus groups. Activities: - Needs Identification (1 month) - Administrative: 10 days - Technical: 5 days - Data Analysis and Reporting - Administrative: 7 days - Technical: 3 days ### Act 1.2: Selection of Blockchain Technology Description: - Select appropriate blockchain technology for the e-management system. Activities: - Technology Selection (1 month) - Administrative: 10 days - Technical: 5 days - Pilot Testing and Evaluation - Administrative: 8 days - Technical: 4 days ### Act 1.3: Internship and Practice Analysis Description: - Gather and analyze data on available practices in national universities. Activities: - Data Gathering (2 months) - Administrative: 15 days - Technical: 10 days - Data Analysis and Reporting - Administrative: 10 days - Technical: 5 days ### Act 1.4: Virtual Meetings with Industry Partners Description: - Conduct virtual meetings to explore internships offered by small and medium businesses. Activities: - Meeting Planning and Execution (1 month) - Administrative: 10 days - Technical: 5 days - Data Analysis and Reporting - Administrative: 7 days - Technical: 3 days ### Act 1.5: Curriculum Analysis Description: - Analyze curriculum against industry standards and academic needs. Activities: - Literature and Data Review - Administrative: 10 days - Technical: 5 days - Report Compilation - Administrative: 8 days - Technical: 4 days ### Act 1.6: Good Practices in University Laboratories Description: - Analyze and document good practices in university labs. Activities: - Research Framework and Data Collection - Administrative: 10 days - Technical: 5 days - Analysis and Reporting - Administrative: 10 days - Technical: 5 days |
|  | P9 |  |  |  |  |  |  |  | ### ct 1.1: Needs Assessment for New IT System - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.2: Selection of Blockchain Technology - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.3: Internship and Practice Analysis - Administracija: 60 dana - Tehnički deo: 15-20 dana ### Act 1.4: Virtual Meetings with Industry Partners - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.5: Curriculum Analysis - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.6: Good Practices in University Laboratories - Administracija: 30 dana - Tehnički deo: 15-20 dana |
|  | P10 |  |  |  |  |  |  |  | ### Act 1.1: Needs Assessment for New IT System - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.2: Selection of Blockchain Technology - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.3: Internship and Practice Analysis - Administracija: 60 dana - Tehnički deo: 15-20 dana ### Act 1.4: Virtual Meetings with Industry Partners - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.5: Curriculum Analysis - Administracija: 30 dana - Tehnički deo: 15-20 dana ### Act 1.6: Good Practices in University Laboratories - Administracija: 30 dana - Tehnički deo: 15-20 dana |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| DEVELOPMENT | P1 |  |  |  |  |  |  |  | ### Activity 2.1.1 (Developing the MVP) - Administration: 5 days - Technical: 15 days - Research: 5 days ### Activity 2.1.2 (Initial User Testing and Feedback) - Administration: 5 days - Technical: 10 days - Research: 10 days ### Activity 2.2.1 (Developing the Complete System) - Administration: 10 days - Technical: 25 days - Research: 10 days ### Activity 2.2.2 (Integration with Existing Systems) - Administration: 5 days - Technical: 15 days - Research: 5 days ### Activity 2.4.1 (Pilot System Installation) - Administration: 5 days - Technical: 10 days - Research: 5 days ### Activity 2.4.2 (Full System Installation) - Administration: 10 days - Technical: 15 days - Research: 5 days ### Activity 2.5.1 (Performance Monitoring and Evaluation) - Administration: 5 days - Technical: 10 days - Research: 5 days ### Activity 2.5.2 (Implementing Improvements) - Administration: 5 days - Technical: 10 days - Research: 5 days ### Activity 2.6.1 (Compliance and Security Audits) - Administration: 5 days - Technical: 10 days - Research: 5 days ### Activity 2.6.2 (Updating Security Protocols) - Administration: 5 days - Technical: 5 days - Research: 5 days ### Activity 2.7.1 (Maintenance and Update Schedule) - Administration: 5 days - Technical: 5 days - Research: 5 days ### Activity 2.7.2 (Preparing for Future Iterations) - Administration: 5 days - Technical: 10 days - Research: 5 days 3.1.1.1 Scheduling Visits - Administration: 3 days - Technical: 2 days - Research: 1 day 3.1.1.2 Organizing Logistics - Administration: 5 days - Technical: 2 days - Research: 1 day 3.1.1.3 Developing Necessary Materials - Administration: 2 days - Technical: 3 days - Research: 2 days 3.1.1.4 Creating Informational Materials - Administration: 2 days - Technical: 3 days - Research: 2 days 3.1.1.5 Developing Agenda for Visits - Administration: 3 days - Technical: 2 days - Research: 1 day 3.1.1.6 Preparing Background Information - Administration: 2 days - Technical: 1 day - Research: 2 days 3.1.1.7 Preparing Educational Materials - Administration: 2 days - Technical: 3 days - Research: 2 days 3.1.1.8 Conducting Site Tours - Administration: 2 days - Technical: 1 day - Research: 1 day 3.1.1.9 Preparing Presentations - Administration: 2 days - Technical: 3 days - Research: 1 day 3.1.1.10 Organizing Interactive Activities - Administration: 2 days - Technical: 3 days - Research: 1 day 3.1.1.11 Preparing Informal Sessions - Administration: 2 days - Technical: 2 days - Research: 1 day 3.1.1.12 Observing Practices in Business Informatics - Administration: 2 days - Technical: 2 days - Research: 2 days 3.1.1.13 Participating in Workshops and Conferences - Administration: 3 days - Technical: 2 days - Research: 3 days 3.1.1.14 Conducting Virtual Visits - Administration: 2 days - Technical: 3 days - Research: 2 days ### Activity 3.2 (Study Visits) 3.2.1 Identifying Educational Goals - Administration: 2 days - Technical: 1 day - Research: 2 days 3.2.2 Determining Scope of Simulation - Administration: 2 days - Technical: 1 day - Research: 2 days 3.2.3 Developing Business Scenario - Administration: 3 days - Technical: 5 days - Research: 3 days 3.2.4 Creating Storyline - Administration: 2 days - Technical: 3 days - Research: 2 days 3.2.5 Engaging Facilitators and Mentors - Administration: 2 days - Technical: 1 day - Research: 1 day 3.2.6 Developing Scripts - Administration: 2 days - Technical: 3 days - Research: 2 days 3.2.7 Creating Background Materials - Administration: 2 days - Technical: 2 days - Research: 2 days 3.2.8 Designing Digital Platforms - Administration: 3 days - Technical: 10 days - Research: 3 days 3.2.9 Preparing Physical Materials - Administration: 2 days - Technical: 3 days - Research: 2 days 3.2.10 Promoting Simulation Event - Administration: 2 days - Technical: 2 days - Research: 1 day 3.2.11 Setting Up Registration Process - Administration: 2 days - Technical: 1 day - Research: 1 day 3.2.12 Organizing Orientation Sessions - Administration: 2 days - Technical: 2 days - Research: 1 day 3.2.13 Distributing Preparation Materials - Administration: 1 day - Technical: 1 day - Research: 1 day 3.2.14 Organizing Physical and Virtual Space - Administration: 3 days - Technical: 4 days - Research: 2 days 3.2.15 Testing Technical Systems - Administration: 2 days - Technical: 3 days - Research: 1 day 3.2.16 Conducting Introductory Session - Administration: 1 day - Technical: 1 day - Research: 1 day 3.2.17 Facilitating the Simulation - Administration: 2 days - Technical: 3 days - Research: 1 day 3.2.18 Monitoring Interactions and Progress - Administration: 2 days - Technical: 2 days - Research: 1 day 3.2.19 Conducting Reflection Sessions - Administration: 1 day - Technical: 2 days - Research: 1 day ### Activity 3.3 (Panel Discussions) 3.3.1 Setting Up Space - Administration: 2 days - Technical: 2 days - Research: 1 day 3.3.2 Developing Promotional Materials - Administration: 2 days - Technical: 1 day - Research: 1 day 3.3.3 Welcoming Participants - Administration: 1 day - Technical: 1 day - Research: 1 day 3.3.4 Facilitating the Discussion - Administration: 1 day - Technical: 1 day - Research: 1 day 3.3.5 Allowing Audience Questions - Administration: 1 day - Technical: 1 day - Research: 1 day ### Activity 3.4 (Blockchain Technology Panel) 3.4.1 Setting Up Space - Administration: 2 days - Technical: 2 days - Research: 1 day 3.4.2 Developing Promotional Materials - Administration: 2 days - Technical: 1 day - Research: 1 day 3.4.3 Welcoming Participants - Administration: 1 day - Technical: 1 day - Research: 1 day 3.4.4 Facilitating the Discussion - Administration: 1 day - Technical: 1 day - Research: 1 day 3.4.5 Allowing Audience Questions - Administration: 1 day - Technical: 1 day - Research: 1 day ### 4.1.1 Identifikacija i regrutovanje ključnih aktera - Administracija: 5 dana - Tehnički deo: 2 dana - Istraživanje: 3 dana ### 4.1.2 Dodela uloga i odgovornosti unutar tima - Administracija: 3 dana - Tehnički deo: 1 dan - Istraživanje: 1 dan ### 4.2.1 Prikupljanje inputa od fakulteta, studenata i industrijskih partnera - Administracija: 5 dana - Tehnički deo: 2 dana - Istraživanje: 3 dana ### 4.2.2 Procena trenutnog stanja objekata, opreme i resursa - Administracija: 4 dana - Tehnički deo: 3 dana - Istraživanje: 0 dana ### 4.3.1 Kreiranje sveobuhvatnog plana - Administracija: 5 dana - Tehnički deo: 8 dana - Istraživanje: 2 dana ### 4.3.2 Osiguranje detaljnih specifikacija - Administracija: 3 dana - Tehnički deo: 5 dana - Istraživanje: 2 dana ### 4.4.1 Identifikacija i odabir dobavljača - Administracija: 5 dana - Tehnički deo: 3 dana - Istraživanje: 2 dana ### 4.4.2 Kupovina i nabavka opreme i softverskih licenci - Administracija: 3 dana - Tehnički deo: 2 dana - Istraživanje: 0 dana ### 4.5.1 Identifikacija i osiguranje odgovarajuće lokacije na kampusu - Administracija: 4 dana - Tehnički deo: 1 dan - Istraživanje: 0 dana ### 4.5.2 Renoviranje i postavljanje fizičkog prostora - Administracija: 6 dana - Tehnički deo: 4 dana - Istraživanje: 0 dana ### 4.6.1 Postavljanje hardverske opreme - Administracija: 2 dana - Tehnički deo: 5 dana - Istraživanje: 0 dana ### 4.6.2 Instalacija i konfiguracija potrebnog softvera - Administracija: 2 dana - Tehnički deo: 6 dana - Istraživanje: 0 dana ### 4.7.1 Postavljanje cloud naloga - Administracija: 2 dana - Tehnički deo: 3 dana - Istraživanje: 0 dana ### 4.7.2 Implementacija sigurnosnih mera - Administracija: 3 dana - Tehnički deo: 4 dana - Istraživanje: 0 dana ### 4.8.1 Organizovanje probnog lansiranja - Administracija: 4 dana - Tehnički deo: 1 dan - Istraživanje: 2 dana ### 4.8.2 Prikupljanje povratnih informacija - Administracija: 1 dan - Tehnički deo: 1 dan - Istraživanje: 3 dana ### 4.9.1 Planiranje zvaničnog događaja - Administracija: 5 dana - Tehnički deo: 2 dana - Istraživanje: 1 dan ### 4.9.2 Predstavljanje laboratorijskih kapaciteta - Administracija: 3 dana - Tehnički deo: 2 dana - Istraživanje: 1 dan |
|  | P2 |  |  |  |  |  |  |  | ### Act. 2.1.1 - Administracija: 8 dana - Tehnička podrška: 5 dana ### Act. 2.1.2 - Administracija: 5 dana - Tehnička podrška: 4 dana ### Act. 2.2.1 - Administracija: 10 dana - Tehnička podrška: 7 dana ### Act. 2.2.2 - Administracija: 7 dana - Tehnička podrška: 5 dana ### Act. 2.4.1 - Administracija: 6 dana - Tehnička podrška: 4 dana ### Act. 2.4.2 - Administracija: 8 dana - Tehnička podrška: 5 dana ### Act. 2.5.1 - Administracija: 6 dana - Tehnička podrška: 3 dana ### Act. 2.5.2 - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 2.6.1 - Administracija: 4 dana - Tehnička podrška: 3 dana ### Act. 2.6.2 - Administracija: 4 dana - Tehnička podrška: 2 dana ### Act. 2.7.1 - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 2.7.2 - Administracija: 6 dana - Tehnička podrška: 4 dana ### Akt. 3.1.1 - Administracija: 12 dana - Tehnička podrška: 8 dana #### Detaljno po podaktivnostima: - 3.1.1.1 Zakazivanje posete: 3 dana administracije - 3.1.1.2 Organizovanje logistike: 4 dana administracije - 3.1.1.3 Razvoj potrebnog materijala: 2 dana administracije - 3.1.1.4 Kreiranje informacionog materijala: 2 dana administracije - 3.1.1.5 Razvoj agende za posetu: 2 dana administracije - 3.1.1.6 Priprema pozadinske informacije: 2 dana administracije - 3.1.1.7 Priprema obrazovnog materijala: 2 dana administracije - 3.1.1.8 Sprovođenje obilaska objekta: 2 dana administracije - 3.1.1.9 Priprema prezentacija: 3 dana administracije - 3.1.1.10 Organizacija interaktivnih aktivnosti: 3 dana administracije - 3.1.1.11 Priprema za neformalne sesije: 2 dana administracije - 3.1.1.12 Posete za observaciju: 2 dana administracije - 3.1.1.13 Učestvovanje u radionicama: 3 dana administracije - 3.1.1.14 Sprovođenje virtuelnih poseta: 3 dana administracije ### Akt. 3.2 - Administracija: 15 dana - Tehnička podrška: 6 dana #### Detaljno po podaktivnostima: - 3.2.1 Identifikacija specifičnih obrazovnih ciljeva: 2 dana - 3.2.2 Određivanje opsega simulacije: 2 dana - 3.2.3 Razvoj detaljnog poslovnog scenarija: 3 dana - 3.2.4 Kreiranje priče: 2 dana - 3.2.5 Angažovanje facilitator-a i mentora: 2 dana - 3.2.6 Razvoj skripti: 2 dana - 3.2.7 Kreiranje pozadinskih materijala: 2 dana - 3.2.8 Dizajniranje digitalnih platformi: 3 dana - 3.2.9 Priprema fizičkih materijala: 2 dana - 3.2.10 Promocija događaja simulacije: 2 dana - 3.2.11 Postavljanje procesa registracije: 2 dana - 3.2.12 Organizovanje orijentacionih sesija: 2 dana - 3.2.13 Distribucija pripremnih materijala: 1 dan - 3.2.14 Organizovanje prostora: 2 dana - 3.2.15 Testiranje tehničkih sistema: 2 dana - 3.2.16 Održavanje uvodne sesije: 2 dana - 3.2.17 Facilitation of the simulation: 3 dana - 3.2.18 Praćenje interakcija: 2 dana - 3.2.19 Održavanje sesija za refleksiju: 2 dana ### Akt. 3.3 - Administracija: 10 dana - Tehnička podrška: 5 dana #### Detaljno po podaktivnostima: - 3.3.1 Postavljanje prostora: 2 dana - 3.3.2 Razvoj promotivnih materijala: 2 dana - 3.3.3 Dobrodošlica učesnicima: 2 dana - 3.3.4 Facilitacija panel diskusije: 3 dana - 3.3.5 Omogućavanje vremena za pitanja: 1 dan ### Akt. 3.4 - Administracija: 10 dana - Tehnička podrška: 5 dana #### Detaljno po podaktivnostima: - 3.4.1 Postavljanje prostora: 2 dana - 3.4.2 Razvoj promotivnih materijala: 2 dana - 3.4.3 Dobrodošlica učesnicima: 2 dana - 3.4.4 Facilitacija panel diskusije: 3 dana - 3.4.5 Omogućavanje vremena za pitanja: 1 dan ### 4.1 Team Formation and Role Assignment 4.1.1 Identifikacija i regrutovanje ključnih aktera - Administracija: 5 dana (za identifikaciju, sastanke i angažovanje). - Tehnička podrška: 0 dana (nema tehničkih zahteva). 4.1.2 Dodela uloga i odgovornosti unutar tima - Administracija: 3 dana (za definisanje uloga i organizaciju sastanaka). - Tehnička podrška: 0 dana (nema tehničkih zahteva). ### 4.2 Gathering Inputs and Assessing Current Resources 4.2.1 Prikupljanje inputa od fakulteta, studenata i industrijskih partnera - Administracija: 7 dana (za sprovođenje anketa i fokus grupa). - Tehnička podrška: 2 dana (za pomoć u analizi podataka). 4.2.2 Procena trenutnog stanja objekata i opreme - Administracija: 5 dana (za pregled infrastrukture i pripremu izveštaja). - Tehnička podrška: 3 dana (za pomoć u analizi i proceni resursa). ### 4.3 Comprehensive Planning for the Laboratory and Center 4.3.1 Kreiranje sveobuhvatnog plana - Administracija: 10 dana (za kreiranje i razradu plana). - Tehnička podrška: 3 dana (za konsultacije oko tehničkih aspekata). 4.3.2 Osiguranje da plan uključuje detaljne specifikacije - Administracija: 5 dana (za prikupljanje i finalizaciju specifikacija). - Tehnička podrška: 3 dana (za konsultacije sa IT stručnjacima). ### 4.4 Vendor Selection and Procurement 4.4.1 Identifikacija i odabir dobavljača - Administracija: 7 dana (za istraživanje i pregovaranje). - Tehnička podrška: 0 dana (nema tehničkih zahteva). 4.4.2 Kupovina i nabavka opreme i licenci - Administracija: 5 dana (za obradu narudžbenica i koordinaciju). - Tehnička podrška: 1 dan (za pomoć u postavkama opreme). ### 4.5 Location Setup on Campus 4.5.1 Identifikacija i osiguranje odgovarajuće lokacije - Administracija: 4 dana (za identifikaciju i dobijanje odobrenja). - Tehnička podrška: 0 dana (nema tehničkih zahteva). 4.5.2 Renoviranje i postavljanje fizičkog prostora - Administracija: 6 dana (za planiranje i organizaciju renoviranja). - Tehnička podrška: 2 dana (za podršku tokom postavljanja infrastrukture). ### 4.6 Hardware and Software Installation 4.6.1 Postavljanje servera i radnih stanica - Administracija: 2 dana (za koordinaciju sa IT timom). - Tehnička podrška: 5 dana (za instalaciju i konfiguraciju opreme). 4.6.2 Instalacija i konfiguracija potrebnog softvera - Administracija: 2 dana (za koordinaciju i praćenje). - Tehnička podrška: 4 dana (za instalaciju i testiranje softvera). ### 4.7 Cloud Infrastructure Setup 4.7.1 Postavljanje cloud naloga - Administracija: 2 dana (za kreiranje naloga i koordinaciju). - Tehnička podrška: 2 dana (za konfiguraciju cloud resursa). 4.7.2 Implementacija sigurnosnih mera - Administracija: 1 dan (za praćenje usklađenosti). - Tehnička podrška: 3 dana (za postavljanje i testiranje sigurnosnih protokola). ### 4.8 Pilot Launch and Feedback Collection 4.8.1 Organizovanje probnog lansiranja - Administracija: 5 dana (za planiranje i organizaciju). - Tehnička podrška: 3 dana (za asistenciju tokom testiranja). 4.8.2 Prikupljanje povratnih informacija - Administracija: 3 dana (za analizu povratnih informacija). - Tehnička podrška: 2 dana (za podršku u implementaciji promena). ### 4.9 Official Launch Event Planning 4.9.1 Planiranje zvaničnog događaja - Administracija: 7 dana (za organizaciju i pripreme). - Tehnička podrška: 1 dan (za asistenciju na događaju). 4.9.2 Predstavljanje laboratorijskih kapaciteta - Administracija: 2 dana (za pripremu prezentacija). - Tehnička podrška: 1 dan (za asistenciju tokom demonstracija). |
|  | P3 |  |  |  |  |  |  |  | ### Act 2.1.1 - Administracija: 15 dana - Definisanje funkcionalnosti, okupljanje tima, organizacija sastanaka. - Tehnička podrška: 5 dana - Podrška u razvoju MVP-a, testiranje i iteracije. ### Act 2.1.2 - Administracija: 10 dana - Organizacija testiranja, prikupljanje povratnih informacija, analiza. - Tehnička podrška: 4 dana - Tehnička asistencija tokom testiranja i analize podataka. ### Act 2.2.1 - Administracija: 20 dana - Planiranje i dokumentacija procesa razvoja, kreiranje priručnika. - Tehnička podrška: 6 dana - Razvoj dodatnih funkcionalnosti i podrška u dokumentaciji. ### Act 2.2.2 - Administracija: 15 dana - Planiranje integracije i organizacija sastanaka sa IT timovima fakulteta. - Tehnička podrška: 5 dana - Tehnička podrška tokom testiranja kompatibilnosti i integracije. ### Act 2.4.1 - Administracija: 12 dana - Organizacija pilot instalacije, prikupljanje povratnih informacija. - Tehnička podrška: 4 dana - Podrška u monitoringu performansi tokom pilot faze. ### Act 2.4.2 - Administracija: 18 dana - Planiranje i organizacija šire implementacije sistema, obuka korisnika na fakultetu. - Tehnička podrška: 6 dana - Tehnička asistencija tokom instalacije u svim relevantnim institucijama. ### Act 2.5.1 - Administracija: 15 dana - Praćenje performansi i evaluacija KPI-eva. - Tehnička podrška: 4 dana - Pomoć u analizi performansi koristeći analitičke alate. ### Act 2.5.2 - Administracija: 10 dana - Planiranje i organizacija redovnih ažuriranja na osnovu povratnih informacija. - Tehnička podrška: 3 dana - Asistencija u implementaciji poboljšanja i ažuriranja. ### Act 2.6.1 - Administracija: 12 dana - Planiranje i izvođenje revizija i provere usklađenosti. - Tehnička podrška: 3 dana - Podrška tokom revizija i analize rezultata. ### Act 2.6.2 - Administracija: 8 dana - Ažuriranje sigurnosnih protokola i komunikacija sa relevantnim akterima. - Tehnička podrška: 3 dana - Tehnička asistencija u primeni ažuriranja i revizija dokumentacije. ### Act 2.7.1 - Administracija: 10 dana - Razvoj rasporeda održavanja i ažuriranja. - Tehnička podrška: 2 dana - Pomoć u izradi rasporeda i definisanju procedure. ### Act 2.7.2 - Administracija: 10 dana - Planiranje budućih iteracija i dizajniranje novih funkcionalnosti. - Tehnička podrška: 3 dana - Tehnička asistencija u dizajnu i planiranju sistema. ### Act 3.1.1 - Administracija: 30 dana - Planiranje i zakazivanje, organizacija logistike, kreiranje agende. - Tehnička podrška: 10 dana - Razvoj i priprema obrazovnog materijala, podrška tokom poseta. ### Act 3.1.2 - Administracija: 25 dana - Organizacija poseta, razvoj potrebnog materijala, kreiranje agende. - Tehnička podrška: 8 dana - Priprema obrazovnih materijala i podrška tokom diskusija. ### Act 3.2.1 - Administracija: 15 dana - Definisanje obrazovnih ciljeva i opsega simulacije. - Tehnička podrška: 5 dana - Razvoj i podrška u kreiranju poslovnog scenarija. ### Act 3.2.2 - Administracija: 20 dana - Razvoj detaljnog scenarija i priprema materijala. - Tehnička podrška: 6 dana - Angažovanje facilitatora i priprema digitalnih platformi. ### Act 3.2.3 - Administracija: 10 dana - Organizacija orijentacionih sesija i promocija događaja. - Tehnička podrška: 4 dana - Testiranje tehničkih sistema i održavanje uvodnih sesija. ### Act 3.2.4 - Administracija: 12 dana - Organizacija fizičkog i virtuelnog prostora. - Tehnička podrška: 5 dana - Pomoć tokom simulacije i praćenje napretka učesnika. ### Act 3.3.1 - Administracija: 10 dana - Postavljanje prostora i razvoj promotivnih materijala. - Tehnička podrška: 3 dana - Tehnička priprema i podrška tokom diskusije. ### Act 3.3.2 - Administracija: 8 dana - Dobrodošlica učesnicima i facilitacija diskusije. - Tehnička podrška: 2 dana - Podrška u postavljanju pitanja i interakciji sa panelistima. ### Act 3.4.1 - Administracija: 12 dana - Organizacija prostora i razvoj promotivnih materijala. - Tehnička podrška: 3 dana - Tehnička priprema i podrška tokom diskusije. ### Act 3.4.2 - Administracija: 8 dana - Dobrodošlica učesnicima i facilitacija diskusije. - Tehnička podrška: 2 dana - Omogućavanje interakcije i pitanja publike. ### 4.1 Identifikacija i regrutovanje ključnih aktera - Administracija: 5 dana - Tehnička podrška: 0 dana ### 4.2 Prikupljanje inputa od fakulteta, studenata i industrijskih partnera - Administracija: 7 dana - Tehnička podrška: 0 dana ### 4.3 Procena trenutnog stanja objekata, opreme i resursa - Administracija: 5 dana - Tehnička podrška: 0 dana ### 4.4 Kreiranje sveobuhvatnog plana - Administracija: 10 dana - Tehnička podrška: 0 dana ### 4.5 Osiguranje da plan uključuje detaljne specifikacije - Administracija: 5 dana - Tehnička podrška: 5 dana ### 4.6 Identifikacija i odabir dobavljača - Administracija: 7 dana - Tehnička podrška: 0 dana ### 4.7 Kupovina i nabavka potrebne opreme - Administracija: 10 dana - Tehnička podrška: 0 dana ### 4.8 Identifikacija i osiguranje odgovarajuće lokacije - Administracija: 3 dana - Tehnička podrška: 0 dana ### 4.9 Renoviranje i postavljanje fizičkog prostora - Administracija: 5 dana - Tehnička podrška: 10 dana ### 4.10 Postavljanje servera, radnih stanica, mrežnih uređaja - Administracija: 0 dana - Tehnička podrška: 7 dana ### 4.11 Instalacija i konfiguracija potrebnog softvera - Administracija: 0 dana - Tehnička podrška: 7 dana ### 4.12 Postavljanje cloud naloga i konfiguracija cloud resursa - Administracija: 0 dana - Tehnička podrška: 3 dana ### 4.13 Implementacija sigurnosnih mera - Administracija: 0 dana - Tehnička podrška: 5 dana ### 4.14 Organizovanje probnog lansiranja laboratorije - Administracija: 5 dana - Tehnička podrška: 5 dana ### 4.15 Prikupljanje povratnih informacija - Administracija: 5 dana - Tehnička podrška: 0 dana ### 4.16 Planiranje i organizacija zvaničnog događaja lansiranja - Administracija: 7 dana - Tehnička podrška: 0 dana |
|  | P4 |  |  |  |  |  |  |  | ### Act. 2.1.1 - Razvijanje minimalno održivog proizvoda (MVP) - Administracija: 10 dana - Tehnička podrška: 7 dana ### Act. 2.1.2 - Početno testiranje korisnika i prikupljanje povratne informacije - Administracija: 8 dana - Tehnička podrška: 5 dana ### Act. 2.2.1 - Razvijanje kompletnog sistema - Administracija: 12 dana - Tehnička podrška: 8 dana ### Act. 2.2.2 - Integracija sa postojećim univerzitetskim sistemima - Administracija: 10 dana - Tehnička podrška: 6 dana ### Act. 2.4.1 - Instalacija pilot sistema - Administracija: 6 dana - Tehnička podrška: 4 dana ### Act. 2.4.2 - Instalacija sistema u svim relevantnim institucijama - Administracija: 10 dana - Tehnička podrška: 5 dana ### Act. 2.5.1 - Praćenje i procena performanse sistema - Administracija: 8 dana - Tehnička podrška: 5 dana ### Act. 2.5.2 - Implementacija poboljšanja na osnovu povratnih informacija - Administracija: 6 dana - Tehnička podrška: 4 dana ### Act. 2.6.1 - Provera usklađenosti i sigurnosne revizije - Administracija: 7 dana - Tehnička podrška: 5 dana ### Act. 2.6.2 - Ažuriranje sigurnosnih protokola - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 2.7.1 - Definisanje rasporeda održavanja i ažuriranja - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 2.7.2 - Priprema budućih iteracija proizvoda - Administracija: 6 dana - Tehnička podrška: 4 dana ### Act. 3.1.1 - Posete univerzitetima i institucijama Zakazivanje posete: - Administracija: 5 dana - Tehnička podrška: 3 dana Organizovanje logistike: - Administracija: 7 dana - Tehnička podrška: 4 dana Razvoj potrebnog materijala: - Administracija: 6 dana - Tehnička podrška: 3 dana Kreiranje informacionog materijala: - Administracija: 5 dana - Tehnička podrška: 3 dana Razvoj agende za posetu: - Administracija: 6 dana - Tehnička podrška: 3 dana Priprema pozadinske informacije: - Administracija: 4 dana - Tehnička podrška: 2 dana Priprema obrazovnog materijala: - Administracija: 5 dana - Tehnička podrška: 3 dana Sprovođenje obilaska objekta: - Administracija: 4 dana - Tehnička podrška: 3 dana Priprema prezentacija od strane ključnih ličnosti: - Administracija: 5 dana - Tehnička podrška: 2 dana Organizacija interaktivnih aktivnosti: - Administracija: 5 dana - Tehnička podrška: 3 dana Priprema za neformalne sesije: - Administracija: 4 dana - Tehnička podrška: 2 dana Posete univerzitetima za observaciju: - Administracija: 5 dana - Tehnička podrška: 3 dana Učestvovanje u radionicama i konferencijama: - Administracija: 5 dana - Tehnička podrška: 3 dana Sprovođenje virtuelnih poseta: - Administracija: 5 dana - Tehnička podrška: 3 dana ### Act. 3.2.1 - 3.2.19 - Simulacija Identifikacija specifičnih obrazovnih ciljeva: - Administracija: 4 dana - Tehnička podrška: 2 dana Određivanje opsega simulacije: - Administracija: 4 dana - Tehnička podrška: 2 dana Razvoj detaljnog poslovnog scenarija: - Administracija: 5 dana - Tehnička podrška: 3 dana Kreiranje priče: - Administracija: 4 dana - Tehnička podrška: 2 dana Angažovanje facilitator-a i mentora: - Administracija: 3 dana - Tehnička podrška: 2 dana Razvoj skripti: - Administracija: 5 dana - Tehnička podrška: 3 dana Kreiranje pozadinskih materijala: - Administracija: 4 dana - Tehnička podrška: 2 dana Dizajniranje digitalnih platformi: - Administracija: 5 dana - Tehnička podrška: 4 dana Priprema fizičkih materijala: - Administracija: 4 dana - Tehnička podrška: 3 dana Promocija događaja simulacije: - Administracija: 4 dana - Tehnička podrška: 2 dana Postavljanje procesa registracije: - Administracija: 4 dana - Tehnička podrška: 2 dana Organizovanje orijentacionih sesija: - Administracija: 5 dana - Tehnička podrška: 3 dana Distribucija pripremnih materijala: - Administracija: 3 dana - Tehnička podrška: 2 dana Organizovanje fizičkog i virtuelnog prostora: - Administracija: 5 dana - Tehnička podrška: 3 dana Testiranje svih tehničkih sistema: - Administracija: 4 dana - Tehnička podrška: 3 dana Održavanje uvodne sesije: - Administracija: 3 dana - Tehnička podrška: 2 dana Facilitacija simulacije: - Administracija: 5 dana - Tehnička podrška: 4 dana Praćenje interakcija i napretka studenata: - Administracija: 4 dana - Tehnička podrška: 2 dana Održavanje sesija za refleksiju: - Administracija: 3 dana - Tehnička podrška: 2 dana ### Act. 3.3 - 3.4 - Panel diskusije Postavljanje prostora: - Administracija: 3 dana - Tehnička podrška: 2 dana Razvoj promotivnih materijala: - Administracija: 3 dana - Tehnička podrška: 2 dana Dobrodošlica učesnicima: - Administracija: 2 dana - Tehnička podrška: 1 dan Facilitacija panel diskusije: - Administracija: 3 dana - Tehnička podrška: 2 dana Omogućavanje vremena za pitanja: - Administracija: 2 dana - Tehnička podrška: 1 dan ### 4.1 Identifikacija i Regrutovanje - 4.1.1 Identifikacija i regrutovanje ključnih aktera: 10 dana - 4.1.2 Dodela uloga i odgovornosti: 5 dana ### 4.2 Prikupljanje Informacija - 4.2.1 Prikupljanje inputa: 10 dana - 4.2.2 Procena trenutnog stanja: 5 dana ### 4.3 Planiranje - 4.3.1 Kreiranje sveobuhvatnog plana: 15 dana - 4.3.2 Detaljne specifikacije: 5 dana ### 4.4 Nabavka - 4.4.1 Identifikacija i odabir dobavljača: 10 dana - 4.4.2 Kupovina i nabavka: 10 dana ### 4.5 Lokacija - 4.5.1 Identifikacija lokacije: 5 dana - 4.5.2 Renoviranje i postavljanje: 15 dana ### 4.6 Instalacija - 4.6.1 Postavljanje hardvera: 10 dana - 4.6.2 Instalacija softvera: 10 dana ### 4.7 Cloud Infrastruktura - 4.7.1 Postavljanje cloud naloga: 5 dana - 4.7.2 Sigurnosne mere: 5 dana ### 4.8 Testiranje - 4.8.1 Organizovanje probnog lansiranja: 7 dana - 4.8.2 Prikupljanje povratnih informacija: 5 dana ### 4.9 Zvanično Lansiranje - 4.9.1 Planiranje događaja: 7 dana - 4.9.2 Predstavljanje laboratorije: 3 dana |
|  | P5 |  |  |  |  |  |  |  | ### Act. 2.1: Developing Minimum Viable Product (MVP) - Administration: 10 days - Defining requirements, assembling teams, and coordinating internal reviews. - Technical: 15 days - Designing, building, and iterating the MVP based on feedback. ### Act. 2.2: Complete System Development - Administration: 12 days - Planning features, documenting processes, and creating training materials. - Technical: 18 days - Expanding the MVP, ensuring scalability, and integrating systems. ### Act. 2.4: Pilot System Installation - Administration: 8 days - Coordinating pilot launch, scheduling feedback sessions, and managing logistics. - Technical: 12 days - Installing the pilot, monitoring performance, and collecting user feedback. ### Act. 2.5: System Performance Monitoring - Administration: 6 days - Overseeing monitoring processes, compiling reports, and coordinating feedback. - Technical: 10 days - Analyzing performance metrics and implementing improvements. ### Act. 2.6: Compliance Checks and Security Audits - Administration: 8 days - Planning audit schedules and documenting compliance processes. - Technical: 10 days - Conducting audits, updating security protocols, and documenting findings. ### Act. 2.7: Maintenance and Future Iterations - Administration: 7 days - Developing maintenance schedules and planning future updates. - Technical: 12 days - Designing scalable features and preparing for future growth. ### Act. 3.1: University Visits for Business Simulation Practices - Administration: 15 days - Scheduling visits, organizing logistics, and preparing materials. - Technical: 20 days - Developing educational content, conducting facility tours, and coordinating interactive activities. ### Act. 3.2: Educational Goals and Simulation Development - Administration: 10 days - Identifying educational goals, determining simulation scope, and organizing orientation sessions. - Technical: 25 days - Developing business scenarios, creating digital platforms, and testing systems. ### Act. 3.3: Panel Discussion Organization - Administration: 8 days - Setting up logistics, welcoming participants, and developing promotional materials. - Technical: 12 days - Facilitating discussions and managing panel interactions. ### Act. 3.4: Blockchain Technology Panel Discussion - Administration: 8 days - Organizing space, welcoming participants, and creating promotional materials. - Technical: 10 days - Facilitating discussions on blockchain and managing audience interactions. ### 3.1.1 Posete univerzitetima i institucijama Zakazivanje posete - Administracija: 2 dana - Tehnički deo: 0 dana Organizovanje logistike - Administracija: 4 dana - Tehnički deo: 0 dana Razvoj potrebnog materijala - Administracija: 2 dana - Tehnički deo: 0 dana Kreiranje informacionog materijala - Administracija: 2 dana - Tehnički deo: 0 dana Razvoj agende za posetu - Administracija: 1 dan - Tehnički deo: 0 dana Priprema pozadinske informacije - Administracija: 1 dan - Tehnički deo: 0 dana Priprema obrazovnog materijala - Administracija: 2 dana - Tehnički deo: 0 dana Sprovođenje obilaska objekta - Administracija: 0 dana - Tehnički deo: 1 dan Priprema prezentacija - Administracija: 0 dana - Tehnički deo: 2 dana Organizacija interaktivnih aktivnosti - Administracija: 0 dana - Tehnički deo: 1 dan Priprema za neformalne sesije - Administracija: 1 dan - Tehnički deo: 0 dana Posete univerzitetima za observaciju - Administracija: 0 dana - Tehnički deo: 2 dana Učestvovanje u radionicama i konferencijama - Administracija: 0 dana - Tehnički deo: 3 dana Sprovođenje virtuelnih poseta - Administracija: 0 dana - Tehnički deo: 1 dan ### 3.1.2 Studijske posete panel diskusijama Zakazivanje posete - Administracija: 2 dana - Tehnički deo: 0 dana Organizovanje logistike - Administracija: 4 dana - Tehnički deo: 0 dana Razvoj potrebnog materijala - Administracija: 2 dana - Tehnički deo: 0 dana Kreiranje informacionog materijala - Administracija: 2 dana - Tehnički deo: 0 dana Razvoj agende za posetu - Administracija: 1 dan - Tehnički deo: 0 dana Priprema pozadinske informacije - Administracija: 1 dan - Tehnički deo: 0 dana Priprema obrazovnog materijala - Administracija: 2 dana - Tehnički deo: 0 dana Sprovođenje obilaska objekta - Administracija: 0 dana - Tehnički deo: 1 dan Priprema prezentacija - Administracija: 0 dana - Tehnički deo: 2 dana Organizacija interaktivnih aktivnosti - Administracija: 0 dana - Tehnički deo: 1 dan Priprema za neformalne sesije - Administracija: 1 dan - Tehnički deo: 0 dana Posete univerzitetima za observaciju - Administracija: 0 dana - Tehnički deo: 2 dana Učestvovanje u radionicama i konferencijama - Administracija: 0 dana - Tehnički deo: 3 dana Sprovođenje virtuelnih poseta - Administracija: 0 dana - Tehnički deo: 1 dan ### 3.2 Poslovna simulacija Identifikacija ciljeva - Administracija: 2 dana - Tehnički deo: 0 dana Opseg simulacije - Administracija: 2 dana - Tehnički deo: 0 dana Razvoj scenarija - Administracija: 3 dana - Tehnički deo: 0 dana Kreiranje priče - Administracija: 2 dana - Tehnički deo: 0 dana Angažovanje facilitator-a - Administracija: 2 dana - Tehnički deo: 0 dana Razvoj skripti - Administracija: 3 dana - Tehnički deo: 0 dana Pozadinski materijali - Administracija: 2 dana - Tehnički deo: 0 dana Digitalne platforme - Administracija: 0 dana - Tehnički deo: 4 dana Fizički materijali - Administracija: 2 dana - Tehnički deo: 0 dana Promocija - Administracija: 2 dana - Tehnički deo: 0 dana Registracija - Administracija: 2 dana - Tehnički deo: 0 dana Orijentacione sesije - Administracija: 1 dan - Tehnički deo: 0 dana Distribucija materijala - Administracija: 1 dan - Tehnički deo: 0 dana Organizacija prostora - Administracija: 2 dana - Tehnički deo: 0 dana Testiranje sistema - Administracija: 0 dana - Tehnički deo: 2 dana Uvodna sesija - Administracija: 1 dan - Tehnički deo: 0 dana Facilitacija - Administracija: 0 dana - Tehnički deo: 1 dan Praćenje interakcija - Administracija: 0 dana - Tehnički deo: 1 dan Sesije za refleksiju - Administracija: 0 dana - Tehnički deo: 1 dan ### 3.3 i 3.4 Panel diskusije Postavljanje prostora - Administracija: 2 dana - Tehnički deo: 0 dana Razvoj promotivnih materijala - Administracija: 2 dana - Tehnički deo: 0 dana Dobrodošlica i predstavljanje - Administracija: 1 dan - Tehnički deo: 0 dana Facilitacija diskusije - Administracija: 0 dana - Tehnički deo: 1 dan Vreme za pitanja - Administracija: 0 dana - Tehnički deo: 1 dan ### 4.1.1 Identifikacija i regrutovanje ključnih aktera Identifikacija ključnih aktera - Administracija: 3 dana - Tehnički deo: 0 dana Zakazivanje inicijalnih sastanaka - Administracija: 2 dana - Tehnički deo: 0 dana Angažovanje aktera - Administracija: 2 dana - Tehnički deo: 0 dana ### 4.1.2 Dodela uloga i odgovornosti unutar tima Definisanje specifičnih uloga - Administracija: 2 dana - Tehnički deo: 0 dana Dokumentovanje i komunikacija uloga - Administracija: 1 dan - Tehnički deo: 0 dana Organizacija redovnih timskih sastanaka - Administracija: 2 dana - Tehnički deo: 0 dana ### 4.2.1 Prikupljanje inputa od fakulteta, studenata i industrijskih partnera Sprovođenje anketa ili fokus grupa - Administracija: 3 dana - Tehnički deo: 0 dana Dokumentovanje i analiza ključnih funkcija - Administracija: 2 dana - Tehnički deo: 1 dan ### 4.2.2 Procena trenutnog stanja objekata, opreme i resursa Pregled postojećih objekata - Administracija: 2 dana - Tehnički deo: 0 dana Analiza nedostataka - Administracija: 2 dana - Tehnički deo: 1 dan Priprema izveštaja o trenutnom stanju - Administracija: 2 dana - Tehnički deo: 0 dana ### 4.3.1 Kreiranje sveobuhvatnog plana Nacrtanje detaljnog projektog plana - Administracija: 3 dana - Tehnički deo: 0 dana Uspostavljanje vremenskog okvira - Administracija: 2 dana - Tehnički deo: 0 dana Razvijanje detaljnog budžeta - Administracija: 3 dana - Tehnički deo: 0 dana ### 4.3.2 Osiguravanje detaljnih specifikacija Uključivanje tehničkih specifikacija - Administracija: 2 dana - Tehnički deo: 3 dana Konsultacije sa IT stručnjacima - Administracija: 1 dan - Tehnički deo: 2 dana ### 4.4.1 Identifikacija i odabir dobavljača Istraživanje potencijalnih dobavljača - Administracija: 3 dana - Tehnički deo: 0 dana Zahtev za ponude i pregovaranje - Administracija: 2 dana - Tehnički deo: 0 dana ### 4.4.2 Kupovina i nabavka potrebne opreme Slanje narudžbenica - Administracija: 2 dana - Tehnički deo: 0 dana Koordinacija sa finansijskim odeljenjem - Administracija: 1 dan - Tehnički deo: 0 dana Praćenje isporuke i instalacije - Administracija: 2 dana - Tehnički deo: 1 dan ### 4.5.1 Identifikacija i osiguranje odgovarajuće lokacije Identifikacija prostora na kampusu - Administracija: 2 dana - Tehnički deo: 0 dana Osiguranje odobrenja - Administracija: 1 dan - Tehnički deo: 0 dana ### 4.5.2 Renoviranje i postavljanje fizičkog prostora Renoviranje prostora - Administracija: 1 dan - Tehnički deo: 3 dana Postavljanje prostora - Administracija: 1 dan - Tehnički deo: 2 dana ### 4.6.1 Postavljanje servera, radnih stanica i mrežnih uređaja Saradnja sa IT odeljenjem - Administracija: 1 dan - Tehnički deo: 2 dana Osiguranje mrežne sigurnosti - Administracija: 0 dana - Tehnički deo: 2 dana ### 4.6.2 Instalacija i konfiguracija potrebnog softvera Instalacija softvera za AI i DevOps - Administracija: 0 dana - Tehnički deo: 3 dana Testiranje integracije - Administracija: 0 dana - Tehnički deo: 1 dan ### 4.7.1 Postavljanje cloud naloga Kreiranje cloud naloga - Administracija: 1 dan - Tehnički deo: 1 dan Konfiguracija cloud infrastrukture - Administracija: 0 dana - Tehnički deo: 2 dana ### 4.7.2 Implementacija sigurnosnih mera Uspostavljanje sigurnosnih protokola - Administracija: 1 dan - Tehnički deo: 2 dana Postavljanje backup-ova i nadzora - Administracija: 0 dana - Tehnički deo: 1 dan ### 4.8.1 Organizovanje probnog lansiranja Planiranje probnog lansiranja - Administracija: 2 dana - Tehnički deo: 1 dan Sprovođenje testiranja opreme - Administracija: 0 dana - Tehnički deo: 1 dan ### 4.8.2 Prikupljanje povratnih informacija Prikupljanje povratnih informacija - Administracija: 1 dan - Tehnički deo: 0 dana Prilagođavanje na osnovu povratnih informacija - Administracija: 1 dan - Tehnički deo: 1 dan ### 4.9.1 Planiranje zvaničnog događaja lansiranja Planiranje velikog događaja - Administracija: 3 dana - Tehnički deo: 0 dana Priprema agende - Administracija: 2 dana - Tehnički deo: 0 dana ### 4.9.2 Predstavljanje laboratorijskih kapaciteta Demonstracija ključnih tehnologija - Administracija: 1 dan - Tehnički deo: 2 dana Isticanje benefita za učesnike - Administracija: 1 dan - Tehnički deo: 0 dana |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| QUALITY PLAN | P1 |  |  |  |  |  |  |  | ### 5.1 Defining third mission metrics - Administracija: 6 dana - Tehnički deo: 2 dana - Istraživanje: 4 dana ### 5.2 Internal monitoring - Administracija: 5 dana - Tehnički deo: 3 dana - Istraživanje: 2 dana 5.3 Monitoring of defined metrics - Administracija: 4 dana - Tehnički deo: 2 dana - Istraživanje: 3 dana |
|  | P2 |  |  |  |  |  |  |  | ### 5.1 Defining Third Mission Metrics - Administracija: 10 dana - Formiranje tima, organizacija radionica i diskusija, dokumentacija metrika. - Tehnička podrška: 2 dana - Asistencija u razvoju alata za prikupljanje podataka. ### 5.2 Internal Monitoring - Administracija: 8 dana - Razvijanje procesa i alata, dodeljivanje odgovornosti, organizacija obuka. - Tehnička podrška: 3 dana - Podrška u izradi i testiranju alata za monitoring. ### 5.3 Monitoring of Defined Metrics - Administracija: 6 dana - Implementacija sistema, planiranje vremenskih okvira, izrada izveštaja. - Tehnička podrška: 4 dana - Pomoć u prikupljanju i analizi podataka, podrška u prilagođavanju metrika. |
|  | P3 |  |  |  |  |  |  |  | ### 5.1 Definisanje metrika treće misije - Administracija: 7 dana - Tehnička podrška: 0 dana ### 5.2 Interno praćenje - Administracija: 10 dana - Tehnička podrška: 5 dana ### 5.3 Praćenje definisanih metrika - Administracija: 5 dana - Tehnička podrška: 3 dana |
|  | P4 |  |  |  |  |  |  |  | ### 5.1 Defining Third Mission Metrics Team Formation: Assemble a diverse team from administration, faculty, and relevant departments - Administracija: 5 dana - Tehnički deo: 0 dana Workshops and Discussions: Conduct workshops to identify relevant metrics aligned with institutional goals - Administracija: 5 dana - Tehnički deo: 5 dana Documentation: Clearly document the identified metrics ensuring they meet SMART criteria - Administracija: 3 dana - Tehnički deo: 2 dana ### 5.2 Internal Monitoring Monitoring System Development: Establish processes and tools for data collection - Administracija: 2 dana - Tehnički deo: 8 dana Assign Responsibilities: Designate departments/individuals for data collection and reporting - Administracija: 2 dana - Tehnički deo: 1 dan Training Sessions: Conduct training for involved parties on monitoring tools - Administracija: 2 dana - Tehnički deo: 3 dana Internal Audits: Schedule and conduct regular audits to assess system effectiveness - Administracija: 2 dana - Tehnički deo: 3 dana ### 5.3 Monitoring of Defined Metrics Implementation of Monitoring System: Begin regular data collection and analysis - Administracija: 2 dana - Tehnički deo: 8 dana Establish Timeline for Reporting: Create a timeline for monthly/quarterly reporting - Administracija: 3 dana - Tehnički deo: 2 dana Feedback Loop Creation: Set up a system for reviewing results and informing decision-making - Administracija: 2 dana - Tehnički deo: 3 dana Adjust Metrics/Approach: Review and adjust metrics as necessary - Administracija: 2 dana - Tehnički deo: 3 dana |
|  | P5 |  |  |  |  |  |  |  | ### 5.1 Defining Third Mission Metrics Opis: Okupite tim stručnjaka iz institucije, uključujući predstavnike administracije, fakulteta i relevantnih departmana, kako biste definisali metrike treće misije. Vremenski okvir: - Administracija: 10 dana - Tehnički deo: 5 dana ### 5.2 Internal Monitoring Opis: Uspostavite sistem za interno praćenje definisanih metrika treće misije. Razvijte procese i alate za redovno prikupljanje podataka. Vremenski okvir: - Administracija: 8 dana - Tehnički deo: 7 dana ### 5.3 Monitoring of Defined Metrics Opis: Implementirajte sistem praćenja započinjanjem redovnog prikupljanja i analize podataka na osnovu metrika treće misije. Vremenski okvir: - Administracija: 6 dana - Tehnički deo: 4 dana |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| DISSEMINATION & EXPLOITATION | P1 |  |  |  |  |  |  |  | ### 6.1 Design of project visual identity - Administracija: 5 dana - Tehnički deo: 3 dana - Istraživanje: 2 dana ### 6.2 Design/upgrade of website - Administracija: 4 dana - Tehnički deo: 5 dana - Istraživanje: 2 dana ### 6.3 Defining institutional policies to promote third mission - Administracija: 6 dana - Tehnički deo: 2 dana - Istraživanje: 4 dana ### 6.4 Good practices on Tech transfer and Innovation - Administracija: 3 dana - Tehnički deo: 2 dana - Istraživanje: 5 dana ### 6.5 10 Info days and other events - Administracija: 10 dana - Tehnički deo: 3 dana - Istraživanje: 2 dana ### 6.6 Final Conference on university third mission - Administracija: 7 dana - Tehnički deo: 4 dana |
|  | P2 |  |  |  |  |  |  |  | ### 6.1 Design of Project Visual Identity - Administracija: 10 dana - Formiranje kreativnog tima, organizacija sesija za brainstorming, prezentacija i finalizacija dizajna. - Tehnička podrška: 3 dana - Pomoć u izradi vizualnih elemenata i dokumentaciji stilskih smernica. ### 6.2 Design/Upgrade of Website - Administracija: 12 dana - Definisanje strukture sajta, koordinacija sa dizajnerima, razvijanje sadržaja i testiranje. - Tehnička podrška: 5 dana - Tehnička pomoć pri razvoju, optimizaciji i testiranju sajta. ### 6.3 Defining Institutional Policies to Promote Third Mission - Administracija: 10 dana - Saradnja sa liderima, revizija postojećih politika, konsultacije i izrada novih politika. - Tehnička podrška: 2 dana - Pomoć u dokumentovanju i prezentovanju novih politika. ### 6.4 Good Practices on Tech Transfer and Innovation - Administracija: 8 dana - Istraživanje, izrada izveštaja, konsultacije sa partnerima i deljenje preporuka. - Tehnička podrška: 2 dana - Asistencija u prikupljanju i analizi podataka o dobrim praksama. ### 6.5 10 Info Days and Other Events - Administracija: 15 dana - Planiranje, organizacija, promocija događaja, prikupljanje povratnih informacija. - Tehnička podrška: 4 dana - Pomoć u tehničkom delu organizacije događaja (npr. AV oprema). ### 6.6 Final Conference on University Third Mission - Administracija: 12 dana - Formiranje komisije, razvijanje plana konferencije, promocija i prikupljanje povratnih informacija. - Tehnička podrška: 3 dana - Tehnička pomoć tokom konferencije i u vezi sa dokumentovanjem njenih rezultata. |
|  | P3 |  |  |  |  |  |  |  | ### 6.1 Dizajn vizuelnog identiteta projekta - Administracija: 8 dana - Tehnička podrška: 2 dana ### 6.2 Dizajn/upgrade web stranice - Administracija: 10 dana - Tehnička podrška: 7 dana ### 6.3 Definisanje institucionalnih politika za promociju treće misije - Administracija: 12 dana - Tehnička podrška: 2 dana ### 6.4 Dobre prakse u transferu tehnologije i inovacijama - Administracija: 6 dana - Tehnička podrška: 3 dana ### 6.5 Organizacija 10 informativnih dana i drugih događaja - Administracija: 15 dana - Tehnička podrška: 5 dana ### 6.6 Finalna konferencija o trećoj misiji univerziteta - Administracija: 10 dana - Tehnička podrška: 4 dana |
|  | P4 |  |  |  |  |  |  |  | ### 6.1 Dizajn vizuelnog identiteta projekta - Administracija: 5 dana - Formiranje tima i organizovanje brainstorming sesija. - Prikupljanje i evaluacija povratnih informacija. - Tehnički Deo: 7 dana - Razvoj dizajn koncepata (logo, boje, tipografija). - Dokumentovanje vizuelnog identiteta u stilu vodiča. ### 6.2 Dizajn/upgrejd web stranice Administracija: 4 dana - Definisanje strukture sajta i koordinacija sa timom. - Organizacija sadržaja i promocija sajta. Tehnički Deo: 10 dana - Rad sa web dizajnerima na kreiranju ili unapređivanju sajta. - Testiranje funkcionalnosti i optimizacija za SEO. ### 6.3 Definisanje institucionalnih politika za treću misiju Administracija: 8 dana - Revizija postojećih politika i konsultacije sa zainteresovanim stranama. - Priprema i komunikacija novih politika. Tehnički Deo: 2 dana - Nema značajnijih tehničkih aspekata, fokus na dokumentaciju. ### 6.4 Dobre prakse u transferu tehnologije i inovacijama Administracija: 5 dana - Istraživanje i organizacija obuka na osnovu prikupljenih informacija. Tehnički Deo: 5 dana - Priprema izveštaja o dobrim praksama i preporukama za implementaciju. ### 6.5 10 Informativnih dana i drugih događaja Administracija: 10 dana - Planiranje i organizacija svih događaja, uključujući promociju. Tehnički Deo: 4 dana - Osiguravanje tehničke podrške tokom događaja. ### 6.6 Završna konferencija o trećoj misiji univerziteta Administracija: 7 dana - Formiranje komiteta i promocija konferencije. Tehnički Deo: 3 dana - Organizacija tehničkih aspekata konferencije. |
|  | P5 |  |  |  |  |  |  |  | ### 6.1 Design of Project Visual Identity Opis: Okupite kreativni tim da razvije vizuelni identitet projekta, uključujući logo, shemu boja, tipografiju i druge dizajnerske elemente. Vremenski okvir: - Administracija: 8 dana - Tehnički deo: 5 dana ### 6.2 Design/Upgrade of Website Opis: Radite sa dizajnerima i programerima na izradi ili unapređenju web stranice projekta, osiguravajući da je usklađena s vizuelnim identitetom. Vremenski okvir: - Administracija: 7 dana - Tehnički deo: 10 dana ### 6.3 Defining Institutional Policies to Promote Third Mission Opis: Saradnja sa institucionalnim liderima na definisanju politika koje promovišu treću misiju univerziteta. Vremenski okvir: - Administracija: 12 dana - Tehnički deo: 5 dana ### 6.4 Good Practices on Tech Transfer and Innovation Opis: Istražite i dokumentujte dobre prakse u tehnologiji transfera i inovacijama, prikupljajući informacije iz literature i studija slučaja. Vremenski okvir: - Administracija: 10 dana - Tehnički deo: 7 dana ### 6.5 10 Info Days and Other Events Opis: Planirajte i organizujte seriju od 10 informativnih dana i drugih događaja za promociju ciljeva projekta. Vremenski okvir: - Administracija: 15 dana - Tehnički deo: 10 dana ### 6.6 Final Conference on University Third Mission Opis: Zaključite projekat visoko profilisanom završnom konferencijom fokusiranom na treću misiju univerziteta. Vremenski okvir: - Administracija: 12 dana - Tehnički deo: 8 dana |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| MANAGEMENT | P1 |  |  |  |  |  |  |  | ### 7.1 Overall project management - Administracija: 7 dana - Tehnički deo: 5 dana - Istraživanje: 3 dana ### 7.2 Local management - Administracija: 6 dana - Tehnički deo: 4 dana - Istraživanje: 2 dana ### 7.3 SC meetings - Administracija: 4 dana - Tehnički deo: 2 dana - Istraživanje: 1 dan |
|  | P2 |  |  |  |  |  |  |  | ### 7.1 Overall Project Management - Administracija: 15 dana - Uspostavljanje okvira za upravljanje projektom, razvoj plana, definisanje uloga i komunikacijskih protokola, kao i redovno ažuriranje plana. - Tehnička podrška: 5 dana - Pomoć pri implementaciji projektnog menadžment alata (Gantt dijagrami, softver za upravljanje zadacima). ### 7.2 Local Management - Administracija: 12 dana - Identifikacija lokalnih koordinatora, razvoj smernica i lokalnog menadžment priručnika, kao i planiranje redovnih sastanaka. - Tehnička podrška: 3 dana - Asistencija pri uspostavljanju komunikacijskih kanala i alata za lokalne timove. ### 7.3 SC Meetings - Administracija: 10 dana - Planiranje i organizacija sastanaka, priprema agende, distribucija dokumenata i vođenje zapisnika. - Tehnička podrška: 2 dana - Pomoć pri tehničkoj podršci tokom sastanaka (npr. AV oprema, videokonferencije). |
|  | P3 |  |  |  |  |  |  |  | ### 7.1 Ukupno upravljanje projektom - Administracija: 10 dana - Tehnička podrška: 5 dana ### 7.2 Lokalne menadžment - Administracija: 8 dana - Tehnička podrška: 3 dana ### 7.3 Sastanci upravljačkog odbora (SC) - Administracija: 6 dana - Tehnička podrška: 2 dana |
|  | P4 |  |  |  |  |  |  |  | ### 7.1 Opšte upravljanje projektom Administracija: 10 dana - Uspostavljanje okvira za upravljanje projektom, uključujući definisanje ciljeva, isporuka i rokova. - Razvoj sveobuhvatnog plana upravljanja projektom i komunikacija sa zainteresovanim stranama. Tehnički Deo: 5 dana - Implementacija projektnog menadžment alata (Gantt dijagrami, softver za upravljanje zadacima). - Redovno ažuriranje plana i praćenje napretka. ### 7.2 Lokalne upravljanje Administracija: 8 dana - Identifikacija lokalnih koordinatora i pružanje smernica o njihovim ulogama. - Razvoj lokalnog menadžment priručnika i organizacija redovnih prozora za izveštavanje. Tehnički Deo: 3 dana - Razvoj i implementacija alata za praćenje lokalnih aktivnosti. ### 7.3 Sastanci Upravnog Odbora (SC) Administracija: 5 dana - Organizacija sastanaka Upravnog Odbora, uključujući izradu agendi i distribuiranje dokumenata. - Vođenje zapisnika i praćenje akcija između sastanaka. Tehnički Deo: 2 dana - Priprema tehničkih materijala za sastanke i podrška tokom diskusija. |
|  | P5 |  |  |  |  |  |  |  | ### 7.1 Overall Project Management Opis: Usmjerite okvir za upravljanje projektom od početka do završetka, definišući ciljeve, isporučive rezultate, vremenske okvire i ključne prekretnice. Vremenski okvir: - Administracija: 10 dana - Tehnički deo: 5 dana ### 7.2 Local Management Opis: Kreirajte smernice za lokalno upravljanje, identifikujući lokalne koordinatore projekta koji će nadgledati dnevne aktivnosti. Vremenski okvir: - Administracija: 8 dana - Tehnički deo: 4 dana ### 7.3 SC Meetings Opis: Planirajte i organizujte sastanke Upravnog odbora (SC) kako biste osigurali efikasno upravljanje i donošenje odluka. Vremenski okvir: - Administracija: 6 dana (uključujući pripremu i izradu izveštaja) - Tehnički deo: 3 dana |
| SUBTOTAL |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |

Please insert rows as necessary

# PART F – Quality of the Project Team and Cooperation Arrangements

# F.1 Background of partnership and the proposal preparation

Please provide shortly the history of cooperation between partners (if any). How the idea of the project was developed and which/ who among partners contributed to the proposal development. (limit 3.000 characters)

The partners involved in this project have a strong foundation of collaboration, both in education and research, across several fields such as IT, engineering, and business. Over the years, the consortium members have established ties through joint research projects, exchange programs, and participation in academic conferences. These partnerships have laid the groundwork for the development of this project and ensured that the consortium shares common goals for the modernization of higher education. History of Cooperation: 1. Serbian Universities and EU Partners: o Universities such as Državni Univerzitet u Novom Pazaru, Univerzitet u Nišu, and Elektrotehnički Fakultet u Beogradu have previously collaborated with European universities like Technical University of Berlin and IT University of Copenhagen on Erasmus+ projects and research programs focused on digital transformation, IT infrastructure development, and curriculum modernization. o These collaborations were instrumental in establishing a shared understanding of the challenges faced by Serbian universities in terms of digital transformation and the need for updated curricula. 2. AVT Business School and Ekonomski Fakultet u Beogradu: o AVT Business School has worked closely with the University of Belgrade (Faculty of Economics) on joint seminars, student exchange programs, and workshops in the field of Business Informatics and digital business transformation. This previous cooperation created a foundation for deeper collaboration in curriculum development and student internships in the proposed project. 3. Istanbul Technical University: o Istanbul Technical University has partnered with Serbian universities on regional projects that focus on innovation and technology transfer, particularly in the engineering and IT sectors. This partnership has promoted knowledge exchange between the two regions, leading to the inclusion of ITU in the current project proposal. Development of the Project Idea: The idea for this project originated during discussions among Serbian universities and their European partners about the gaps in IT infrastructure, outdated curricula, and the lack of practical industry partnerships in Serbian higher education. Recognizing the critical need to modernize Serbian institutions to align with global trends, the partners began brainstorming potential solutions. 1. Contributions to Proposal Development: o Technical University of Berlin and IT University of Copenhagen contributed their expertise in digital transformation, advising on the technological infrastructure and e-management systems needed for Serbian universities. o AVT Business School and Dublin Business School provided insights into the modernization of business curricula and the integration of digital tools like blockchain and AI into educational programs. o The Serbian universities, including Univerzitet u Nišu and Državni Univerzitet u Novom Pazaru, contributed by identifying the specific needs of their institutions, such as updating engineering and IT programs and establishing industry-relevant internships.

If relevant, please explain how and to which extent the project benefits from the experience and participation of non–academic partners. (limit 3.000 characters)

The project greatly benefits from the participation of non-academic partners, such as local businesses, tech companies, and SMEs, which play a critical role in aligning academic training with real-world industry demands. Their involvement ensures that the educational outcomes of the project are relevant to the workforce, enhancing the employability of students and bridging the gap between academia and industry. This synergy is key to the project's success. Contributions of Non-Academic Partners: Industry Insights and Practical Relevance: Non-academic partners provide valuable insights into industry trends, particularly in IT, digital transformation, AI, machine learning, and blockchain. This ensures that curriculum updates, training programs, and research initiatives reflect current industry needs. Tech companies and SMEs help co-design internship programs, giving students hands-on experience in real-world environments. This practical relevance prepares students for the job market by equipping them with industry-required skills. Development of Internship Programs and Industry Collaboration: Modernizing internship programs is a core component of the project, and non-academic partners are instrumental in offering placements and shaping internship structures. Their involvement ensures that internships go beyond formalities and provide meaningful learning experiences, allowing students to apply classroom knowledge to real-world challenges in areas like software engineering and digital innovation. Technology Transfer and Innovation: Non-academic partners, especially tech companies, facilitate the transfer of technology and innovation to academic settings. Through collaboration on research and development (R&D) projects, they ensure that universities stay at the forefront of technological advancements. For instance, businesses involved in blockchain or AI will help design research projects and set up laboratories, accelerating the adoption of cutting-edge technologies in academia and enhancing the universities' research capacities. Advisory and Mentorship Roles: Non-academic partners will also serve as advisors and mentors in various project activities. Their expertise will guide curriculum development, ensuring it reflects both theoretical knowledge and the practical skills required in modern businesses. Industry leaders will contribute to workshops and panel discussions, mentoring students and faculty and providing insights into industry challenges and expectations. Extent of the Impact: Improving Employability: By integrating non-academic expertise, the project ensures that students graduate with job-ready skills. This increases employability and makes universities more attractive to prospective students seeking programs with strong industry ties. Enhanced University-Industry Collaboration: The project fosters stronger collaborations between universities and industry, benefiting students and enabling universities to contribute directly to innovation and regional economic growth through technology transfer and R&D.

Please explain the role and the participation of the Programme Country partners and their support in the development of the different activities (e.g. in the development of the curricula) and (limit 3.000 characters)

The Programme Country partners are essential to the success of the project by providing expertise, guidance, and collaboration across various activities. Their participation ensures the alignment of the project with international standards and supports the development of innovative solutions tailored to the specific needs of Serbian universities. With their experience in curriculum modernization, digital transformation, research, and university-industry collaboration, these partners contribute in multiple ways. Role and Participation of Programme Country Partners: 1. Technical University of Berlin (Germany): The Technical University of Berlin is a leader in digital transformation and technology-driven education, making its involvement crucial for developing IT infrastructure and digital learning platforms at Serbian universities. Berlin's expertise in blockchain, AI, and cloud computing will help Serbian partners design and implement advanced e-management systems and digital labs. The university will also collaborate on curriculum development, ensuring that programs in software engineering and business informatics align with global best practices. Support in Activities: • Development and implementation of digital transformation labs. • Co-design of curricula for AI, machine learning, and blockchain technology. • Providing guidance on integrating new technologies into educational and administrative systems. 2. IT University of Copenhagen (Denmark): Renowned for its focus on IT systems and digital innovation, IT University of Copenhagen will advise on curriculum development in IT-related fields such as DevOps and cloud computing. Its support will enhance the research and teaching capacities of Serbian universities, ensuring that advanced methodologies and cutting-edge digital tools are incorporated into academic programs. Support in Activities: • Assisting in designing and implementing cloud computing labs. • Providing expertise for curriculum modernization in software engineering and IT. • Collaborating on joint research initiatives and academic programs. 3. AVT Business School (Denmark): Specializing in business and innovation, AVT Business School contributes significantly to the modernization of business-related curricula in Serbian institutions. AVT ensures that the latest trends in fintech, digital business transformation, and entrepreneurship are integrated into academic programs. Additionally, it assists in creating practical projects and case studies that provide students with a global perspective on business environments. Support in Activities: • Contributing to curriculum development in business informatics and digital transformation. • Providing international case studies and insights into global business trends. • Supporting Serbian institutions in building partnerships with industry. 4. Dublin Business School (Ireland): Dublin Business School’s expertise in business informatics and its strong connections with the tech sector make it a valuable partner in fostering university-industry collaboration. It will help Serbian universities strengthen their ties with local and international businesses, improve internship programs, and facilitate research collaborations.

# F.2 Cooperation arrangements, management and communication

Please define the organisation of the implementation of the project and the division of tasks between the partners. Please explain the allocation of resources for each activity. Explain also how the tasks are distributed amongst the partners and how project "ownership" is ensured (limit 3.000 characters).

The organization of the project implementation is designed to ensure smooth collaboration between all partners, with a clear division of tasks and allocation of resources that align with each institution's expertise and role in the project. The project is structured into work packages, each led by a specific partner, to streamline the coordination and execution of activities. Division of Tasks Between Partners: 1. Državni Univerzitet u Novom Pazaru (Coordinator): As the project coordinator, Državni Univerzitet u Novom Pazaru is responsible for overall project management, ensuring timely progress and proper allocation of resources. They also oversee communication between partners, organize meetings, and handle administrative tasks related to reporting and budget management. Additionally, they lead the efforts in curriculum modernization for their specific programs in computer technologies and economics, as well as the establishment of AI and blockchain labs. Responsibilities: o Overall project coordination and communication. o Curriculum development for AI, machine learning, and blockchain. o Oversight of digital transformation labs in Novi Pazar. 2. Univerzitet u Nišu (Faculty of Electronic Engineering): Univerzitet u Nišu will lead the development of IT labs for AI, DevOps, and cloud computing, and take charge of research activities. Their role involves guiding other partners on implementing advanced IT infrastructure, collaborating on research projects, and developing curriculum updates for engineering and IT courses. Responsibilities: o Lead the development of AI, cloud computing, and DevOps labs. o Guide research initiatives and curriculum updates for engineering programs. o Collaborate on industry-university R&D projects. 3. Elektrotehnički Fakultet u Beogradu (University of Belgrade - Faculty of Electrical Engineering): This partner focuses on developing IT systems and curriculum updates for AI, blockchain, and machine learning in electrical engineering. They are responsible for implementing the advanced IT infrastructure needed to support the faculty's academic programs and lead university-industry collaborations in these technical areas. Responsibilities: o Implement IT systems for AI and blockchain. o Oversee curriculum updates in electrical engineering. o Facilitate university-industry collaboration in digital transformation. 4. Univerzitet u Kragujevcu (Faculty of Mechanical Engineering): The Faculty of Mechanical Engineering will focus on modernizing engineering curricula and establishing AI and automation labs. They will take a lead role in ensuring that students gain practical experience through internships and hands-on projects in collaboration with industry partners. Responsibilities: o Develop modern engineering curricula focused on AI and automation. o Establish research labs for practical student training. o Lead efforts in expanding internships and industry ties. 5. Ekonomski Fakultet u Beogradu (University of Belgrade - Faculty of Economics): The Faculty of Economics is tasked with curriculum modernization in fintech, blockchain, and digital business transformation.

Please explain the overall project and partnership management making specific reference to the management plan and how decisions will be taken. Please describe how permanent and effective communication and reporting will be ensured as well as the measures put in place for conflict resolution (limit 2.000 characters).

The overall project and partnership management is structured to ensure efficient coordination, timely decision-making, and effective communication among all partners. The management plan is based on a collaborative approach, with clear roles and responsibilities for each partner, and is overseen by the Project Coordinator, Državni Univerzitet u Novom Pazaru. Management Plan and Decision-Making: A Steering Committee (SC), composed of representatives from each partner institution, will be the primary decision-making body. The SC will meet quarterly to review progress, discuss challenges, and make key decisions regarding project direction. Day-to-day decisions will be made by the Project Coordinator, in consultation with relevant partners. Major strategic decisions, such as budget adjustments or changes in project activities, will require approval from the SC. Communication and Reporting: Permanent and effective communication will be ensured through: • Monthly virtual meetings to monitor progress and address any issues. • A shared online platform for document exchange, collaboration, and tracking deliverables. • Regular progress reports submitted by each partner to the Project Coordinator, who will consolidate them into comprehensive reports for the SC and funders. Conflict Resolution: To manage conflicts, a clear protocol will be in place. Initial conflicts will be addressed through bilateral discussions between the involved parties. If unresolved, the issue will be escalated to the Project Coordinator, who will mediate a solution. If necessary, the conflict will be brought before the Steering Committee, which will make a final decision based on the best interest of the project. This structured management approach ensures clear communication, collaborative decision-making, and a proactive method for resolving conflicts, all contributing to the smooth implementation of the project.

# F.3 Organisations and activities

This part must be completed separately by each organisation participating in the project (applicant and partners with its affiliated entities (if any)).

☒

| Partner number ☒ |  |  |  |  | P1 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym |  |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List ofsubjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List ofsubjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project anddefine clear the activities to be held in your institution(limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment( only for Partner Country institutions) Please fill in if you are applying for this type of project anddefine clear the activities to be held in your institution(limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |

Please copy and paste tables as necessary

# F.4 List of Associated Partners

(Where applicable)

Capacity-building projects can involve associated partners who contribute to the implementation of specific project tasks/activities or support the dissemination and sustainability of the project. Associated Partners cannot be responsible for core activities of the project (e.g. management, coordination, monitoring, leader of a work group etc.).No financial contribution from the project grant will be allocated to these organisations.

☐

| Name of organisation | Type of institution | Website | City | Country | Role in the project | Activities and related Work Packages |
| --- | --- | --- | --- | --- | --- | --- |

Please insert rows as necessary

# PART G – Impact and Sustainability

# G.1 Expected impact of the project

Please explain which target groups will use the project outputs /products /results. Describe how the target groups will be reached and involved during the life of the project and afterwards and how the project will benefit the target group at local, regional, national and/or regional level. Please structure your description according to the different levels of impact and stakeholders.

☐

| # | Project results | Who will they impact at national, regional level? | How? |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

Please insert rows as necessary

Overview of short term impact indicators (during the project EU funding period)

☐

| Short term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |

Please insert rows as necessary

Overview of long term impact indicators (after the projects EU funding period)

☐

| Long term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |

Please insert rows as necessary

# G.2 Dissemination and exploitation strategy

Please explain how the dissemination will be organisedduring and after the project's lifetime. Define each target group and what communication channels will be used to reach them and when.

☒

| Target Group | Means of Communication to Reach These Target Groups | When | Indicators to measure the effectiveness of the means of communication |
| --- | --- | --- | --- |

Please insert rows as necessary

# G.3 Sustainability

Explain how exploitation activities will ensure optimal use of the results within the project's lifetime and afterwards. Explain how the impact of the project will be sustained beyond its lifetime. Please list the outcomes that you consider sustainable and describe the strategy to ensure their long lasting use beyond the project's lifetime. Also explain how the results will be mainstreamed and multiplied at national/regional level. Describe the strategy foreseen to attract co-funding and other forms of non-EU support for the project.

☐

| Sustainable Outcomes | Strategy to ensure their sustainability | Resources necessary to achieve this | Where will these resources be obtained? |
| --- | --- | --- | --- |

Please insert rows as necessary

# PART H - Other EU grants

Please list the projects for which the organisations involved in this application have received financial support from EU programmes.

☒

| Programme or initiative | Reference number | Beneficiary Organisation | Title of the Project |
| --- | --- | --- | --- |

Please insert rows as necessary.

Please list other EU grant proposalssubmitted by your organisation, or by any partner organisation in this project proposal. For each grant application, please mention the EU Programme concerned and the amount requested.

☐

| Programme concerned | Beneficiary Organisation | Amount requested |
| --- | --- | --- |

Please insert rows as necessary.

# PART I- Check List

Please make sure that you fully completed each part of this application form, as follows:

☒

☐	PART D - RELEVANCE OF THE PROJECT

☐	PART E - QUALITY OF THE PROJECT DESIGN AND IMPLEMENTATION

☐	E.4 Logical Framework Matrix

☐	E.5 Workplan

☐	E.6 Work packages

☐	PART F - Quality of the Project Team and Cooperation Arrangements

☐	PART G - Impact and Sustainability

☐	PART H - Other EU grants

☐	PART I - CHECK LIST

Please see Programme Guide, Part B for your action, Table A – Project Implementation (amounts in Euro per day) Programme Countries and Table B - Project Implementation (amounts in Euro per day) Partner Countries.